DRC

Terms of Reference (TOR)

for

Data collection services in South Europe for the 4Mi data collection initiative on mixed migration dynamics (MMC)

# Who is the Danish Refugee Council?

The Danish Refugee Council

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

The Mixed Migration Centre

Part of DRC, the Mixed Migration Centre (MMC) is a leading source for independent and high-quality data, research, analysis and expertise on mixed migration. The MMC aims to increase understanding of mixed migration, to positively impact global and regional migration policies, to inform evidence-based protection responses for people on the move and to stimulate forward thinking in public and policy debates on mixed migration. The MMC's overarching focus is on human rights and protection for all people on the move. The three overall objectives of the MMC are:

- To contribute to a better, more nuanced and balanced understanding of mixed migration (knowledge)

- To contribute to evidence-based and better-informed migration policies and debates (policy)

- To contribute to effective evidence-based protection responses for people on the move (programming)

MMC is a global network, with regional hubs in Africa, Asia, Europe and Latin America hosted in DRC regional offices, and a small central team in Geneva. MMC is part of, and governed by, DRC. While its institutional link to DRC ensures MMC's work is grounded in operational reality, it acts as an independent source of data, research, analysis and policy development on mixed migration for policy makers, practitioners, journalists, and the broader humanitarian sector. The position of MMC does not necessarily reflect the position of DRC. For more information on MMC visit our website here: www.mixedmigration.org

# Purpose of the consultancy

The Danish Refugee Council based in Geneva seeks proposals from consultants to conduct quantitative data collection (survey administration) and qualitative data collection (semi-structured migrant interviews) in Greece, Italy, Spain and another country in the Western Balkans region.

# Background

The 4Mi data collection initiative

4Mi is one of MMC’s flagship project. 4Mi collects data through in-depth structured interviews, focusing on protection risks and the conditions and experiences faced by people on the move, as well as their motivation for migration. 4Mi fills information gaps around protection and vulnerabilities with a view to informing policy and humanitarian programmatic response as well as enhancing sector understanding and knowledge on migration dynamics.

Regional context

In Europe, MMC has carried out 4Mi data collection in Europe since 2019, and has since engaged in a number of other research initiatives and projects, all available here. In addition, MMC is committed to respond to changing dynamics and pressing needs for evidence-based programming and policy development in the region.

# Objective of the consultancy

The purpose of this consultancy is to conduct quantitative data collection (survey administration) and qualitative data collection (semi-structured migrant interviews) in Spain, South and North-East of Italy, North of Greece, and another country in the Western Balkans regions to be identified during inception.

While the funding for data collection in Spain and South of Italy is already confirmed, the activities outlined in this TOR concerning North of Greece, North-East of Italy and the Western Balkans are conditional to the confirmation of funding in April/May 2025.

The consultant will be required to conduct and deliver a total of 2200 surveys and 40 semi-structured migrant interviews as per MMC’s methodology and research objectives and in close cooperation with the MMC team.

Research objectives

MMC will engage in a new data collection along three key routes of entry in Europe:

1) the Atlantic route, with quantitative and qualitative data to be collected in Spain;

2) The Central Mediterranean Route (CMR), with quantitative and qualitative data to be collected in the South of Italy.

3) The Eastern Mediterranean and Western Balkans route (EM/WBR), with quantitative and qualitative data to be collected in North of Greece, North-East of Italy (Friuli Venezia-Giulia), and a third country across the Western Balkans (subject to funding confirmation).

Quantitative data collection will be carried out using the 4Mi core survey developed by MMC. The questionnaire will cover the following topics:

- Profile: age, nationality, religion, sex, socio-economic status, etc.

- Route and journey conditions: country of departure, transit countries, number of people travelling together, etc.

- Drivers, aspirations and destination intentions: reasons for leaving, decision-making, determination to reach destination, etc.

- Protection risks: perceived risks and dangerous locations, perpetrators, etc.

- Assistance: type of assistance needed, assistance providers, locations where assistance is most needed, etc.

- Smugglers: services provided by smugglers, contacts with smugglers, payment arrangements, refugees’ and migrants’ perceptions of smugglers, etc.

- Financing the journey: sums paid, access to money while travelling, bribes paid, etc.

- Access to information: sources of information used before and during the journey, phone and internet access, social media use, etc.

Additionally, a set of questions will be added to the 4Mi core migrant survey, to further understand the dynamics of smuggling (cost, number of smugglers, use of smugglers to cross borders across countries, and general perception) used by migrants entering Europe through the Atlantic route, CMR and EM/WBR (smuggling module).

Quantitative data analysis will be complemented by a set of semi-structured migrant interviews (40)with migrants with the same profile of survey respondents, specifically focusing on smuggling.

Target population

Survey respondents will be selected based on the following criteria:

- 18+ years old.

- Refugees and migrants both in regular and irregular status.

- Arrived in the country of data collection since a maximum period of two years.

MMC is expecting the sample to respect as much as possible gender balance.

Locations for data collection and nationalities

The surveys’ and qualitative interviews’ breakdown by countries/locations of data collection is the following:

  - Spain (Atlantic Route): 600 surveys and 10 semi-structured migrant interviews to be carried out in Spain with respondents arrived via the Atlantic Route;

  - South of Italy (Central Mediterranean Route): 400 surveys and 10 semi-structured migrant interviews to be carried out in Southern Italy with respondents arrived via the CMR;

  - North of Greece, North-East of Italy (on the Italian side of the border with Slovenia), and another country along the Western Balkans route (Eastern Mediterranean Route and Western Balkans):  1200 surveys and 20 semi-structured migrant interviews with migrants arrived via the EM/WBR, This component is conditional to the confirmation of funding that MMC foresees to receive in April/May 2025.

Exact locations for data collection and nationalities of respondents will be agreed during the inception phase of the project, following discussion between the selected contractor and MMC.

Data collection modalities

Surveys are planned to be conducted face-to-face through electronic data collection (text-based survey solution on phones/tablets). Enumerators shall have a good command of English to receive the training in this language.

Semi-structured migrant interviews will be conducted face-to-face. The consultant is responsible for the translation in English of the extended notes taken during the semi-structured migrant interviews.

# Scope of work and Methodology

Specifically, the consultant is expected to:

- Designate one project focal point for overall coordination, and one data collection field Coordinator per each of the three routes; set up regular reporting and discussion with MMC, especially during the data collection phase to ensure efficient data collection and high-quality standards. Frequency and modalities of reporting will be established during the inception of the project.

- Recruit, contract and supervise a network of enumerators in line with the MMC’s SOPs;

- Organize a in person training for enumerators (that will be facilitated by MMC), providing an adequate venue, transport and accommodation to participants as needed;

- Collect a total of 2,200 surveys in electronic format (ODK), and 40 semi structured interviews according to the workplan agreed upon in advance with MMC. Data collection will be split into two phases.

  - Phase 1. Data collection in Spain (Atlantic Route), entailing the collection of 600 surveys and 10 Semi-structured migrant interviews.

  - Phase 2. Data collection in South of Italy (Central Mediterranean Route, CMR) entailing 400 surveys and 10 Semi-structured migrant interviews.

  - Phase 3 Data collection in North-East of Italy, North of Greece and a third country in the Western Balkans region (Eastern Mediterranean and Western Balkans route, EM/WBR), entailing the collection of overall 1,200 surveys and 20 Semi-structured migrant interviews.

- Translate the semi-structured migrant interviews guidelines from English to any other relevant languages, if needed; identify respondents, conduct the interview and translate in English the notes taken during the interview;

- Identify respondents and use the survey provided to conduct the quantitative interviews.

- Cover potential phone credit and transportation prices for the enumerators.

- Provide phones or tablet (hardware) to the enumerators for electronic data collection.

- Ensure that the methodological guidelines shared by MMC are applied

MMC will provide:

- Methodology and research tools for quantitative (survey) and qualitative (semi structures interview guidelines) data collection, in English and other relevant languages, already coded in ODK format.

- Facilitation of training for enumerators on relevant concepts, methodology, the questionnaire, principles and ethics of research in the field, and the Code of Conduct.

- The backend infrastructure (server, ONA administration) for electronic data collection on the phones provided by the consultant.

- MMC retains the final acceptance of individual surveys, with sole responsibility of data validation and cleaning of the incoming data.

General requirements:

- The consultant is responsible for all aspects of data security and data protection for the duration of the contract.

- When designating the data collection Field Coordinators for this project, the consultant should ensure that each Field Coordinator has direct supervision over the enumerators to secure a direct line of communication and reactivity between both parties.

- The consultant is responsible for adhering to ethical guidelines detailed in the research protocol.

- The consultant is responsible for providing insurance and ensuring compliance regarding human resources.

- The consultant shall adhere to the suppliers’ Code of Conduct.

# Deliverables

The Consultant will submit the following deliverables:

| Phase |  | Expected deliverables | Number of days |  | Indicative description tasks |
| --- | --- | --- | --- | --- | --- |
| Phase 1: data collection in Spain (Atlantic Route) |  |  |  |  |  |
| Phase 1.1 Inception data collection in Spain (Atlantic Route) |  | Inception report | 5 |  | An inception report detailing modalities for carrying out the tasks including data collection locations, respondents’ recruitment strategies, composition of the coordination and data collection team, suggested coordination mechanism between the implementing partner and MMC, and all the other elements needed for an effective implementation of the activities and proper coordination with MMC. |
| Phase 1.2 Pilot data collection in Spain (Atlantic Route) |  | Field pilot report | 2 |  | Test of the survey followed by a short report on the field pilot for potential methodological/technical adjustments to be discussed with MMC before data collection. |
| Phase 1.3 Data collection in Spain (Atlantic Route) |  | Survey dataset for Spain (Atlantic Route) plus notes of qualitative interviews | 72 |  | Collection of 600 high-quality quantitative interviews in the agreed locations, in electronic format. Surveys are expected to be collected from the beginning of the data collection period and consistently throughout it. Collection of 10 high quality qualitative interviews with migrants arrived via the Atlantic. Semi structured migrant interviews transcripts or notes should be in English (regardless of the language used for the interview). |
| Phase 1.4 |  | All data collection documentation | 2 |  | Full documentation regarding data collection, including notes and observations on any changes or modifications. |
| Phase 2: data collection in Southern Italy (CMR) |  |  |  |  |  |
| Phase 2.1 Inception data collection in South of Italy (CMR) |  | Inception report | 5 |  | An inception report detailing modalities for carrying out the tasks including composition of the team, suggested coordination mechanism between the implementing partner and MMC, and all the other elements needed for an effective implementation of the activities and proper coordination with MMC. |
| Phase 2.2 Pilot data collection in South of Italy (CMR) |  | Field pilot report | 2 |  | Test of the survey followed by a short report on the field pilot for potential methodological/technical adjustments to be discussed with MMC before data collection. |
| Phase 2.3 Data collection in South of Italy (CMR) |  | Survey dataset for South of Italy (CMR) plus notes of qualitative interviews | 49 |  | Collection of 400 high-quality quantitative interviews in the agreed locations, in electronic format. Surveys are expected to be collected from the beginning of the data collection period and consistently throughout it. Collection of 10 high quality qualitative interviews, with migrants arrived via the CMR. Semi structured migrant interviews transcripts or notes should be in English (regardless of the language used for the interview). |
| Phase 2.4 Wrap up |  | All data collection documentation | 2 |  | Full documentation regarding data collection, including notes and observations on any changes or modifications. |
| Phase 3: data collection in North of Greece, Western Balkans, and North-East of Italy (Friuli Venezia-Giulia) for the EMR/WB, provided that funding for this activity is confirmed |  |  |  |  |  |
| Phase 3.1 Inception data collection in North of Greece, Western Balkans, and North-East of Italy (Friuli Venezia-Giulia) for the EMR/WB | Inception report |  |  | 5 | An inception report detailing modalities for carrying out the tasks including composition of the team, suggested coordination mechanism between the implementing partner and MMC, and all the other elements needed for an effective implementation of the activities and proper coordination with MMC. |
| Phase 3.2 Pilot data collection in North of Greece, Western Balkans, and North-East of Italy | Field pilot report |  |  | 2 | Test of the survey followed by a short report on the field pilot for potential methodological/technical adjustments to be discussed with MMC before data collection. |
| Phase 3.3 Data collection North of Greece, Western Balkans, and North-East of Italy for the EMR/WB | Survey dataset for the EMR/WBR plus notes of qualitative interviews |  |  | 148 | Collection of 1,200 high-quality quantitative interviews in the agreed locations, in electronic format. Surveys are expected to be collected from the beginning of the data collection period and consistently throughout it. Collection of 20 high quality qualitative interviews, with migrants arrived via the EM/WBR. Semi structured migrant interviews transcripts or notes should be in English (regardless of the language used for the interview). |
| Phase 3.4 Wrap up | All data collection documentation |  |  | 2 | Full documentation regarding data collection, including notes and observations on any changes or modifications. |

To carry out the above-mentioned deliverables, it is expected that the applicant will identify the following positions within the team:

  - Project manager, responsible for the overall implementation of the project and coordination with MMC.  This essential role requires sizable and in-depth experience in managing disperse field data collection teams, ensuring access to respondents and gatekeepers, and extensive experience in coordinating various stakeholders.

  - Field coordinator(s), responsible for the supervision of the enumerators team(s) and for ensuring that data collection proceeds successfully. MMC foresees one Field coordinator per each route to be covered by data collection.

  - Enumerators, directly responsible for collecting the surveys. Ideally, enumerators team should ensure that for each route and/or language group, respondents can access a female enumerator.

The consultant will provide the documentation by email in Excel format (database of quantitative surveys) and Word format (field pilot report, final notes and observations).

# Duration, timeline, and payment

| Activities | Period envisaged |
| --- | --- |
| Contractualization of the data collection consultant | April-May 2025 |
| Phase 1: data collection in Spain (Atlantic Route) |  |
| Definition of methodological & operational details (data collection sites, respondent recruitment criteria, etc.) (jointly between MMC and consultant) for the data collection in Spain | May 2025 |
| Training of enumerators (organized by consultant, content provided by MMC) | May 2024 |
| Field pilot (2 days) for data collection in Spain | Beginning of June 2025 |
| Data collection of 600 surveys in Spain and 10 semi-structured migrant interviews Surveys are expected to be collected from the beginning of the data collection period and consistently throughout it, with an average weekly quota to be established | June to August 2025 |
| Phase 2: data collection in Southern Italy (CMR) |  |
| Definition of methodological & operational details (data collection sites, respondent recruitment criteria, etc.) (jointly between MMC and consultant) for the data collection in South of Italy | June 2025 |
| Field pilot (2 days) for data collection in South of Italy | Late August-beginning of September 2025 |
| Data collection of 400 surveys in South of Italy, and 10 semi-structured migrant interviews | September to December 2025 |
| Phase 3: data collection in North of Greece, Western Balkans, and North-East of Italy (Friuli Venezia-Giulia) for the EMR/WB, provided that funding for this activity is confirmed. Please note that Phase 3 takes place at the same time of Phase 2. |  |
| Definition of methodological & operational details (data collection sites, respondent recruitment criteria, etc.) (jointly between MMC and consultant) for the data collection in North of Greece, Western Balkans, and North-East of Italy | June 2025 |
| Field pilot (2 days) for data collection in North of Greece, Western Balkans, and North-East of Italy | Late August-beginning of September 2025 |
| Data collection of 1200 surveys collection in North of Greece, Western Balkans, and North-East of Italy and 20 semi-structured migrant interviews | September to December 2025 |

MMC’s cleaning and validation process of incoming data is approximately of 1 month turnaround time. This needs to be accounted for by the consultant when establishing individual enumerators’ payment schedule.

Estimated start date of consultancy: 18th April 2025

Payment for the consultancy will be made as follows:

- 20% upon contract signature.

- 30% upon satisfactory receipt of the 600 surveys and transcripts/notes of 10 semi-structured migrant interviews transcripts collected in Spain.

- 25% upon satisfactory receipt of the 400 surveys and transcripts/notes of 10 semi-structured migrant interviews transcripts collected in South of Italy.

- 25% upon satisfactory receipt of the remaining 1200 surveys collected in North of Greece, Western Balkans, and North-East of Italy and transcripts/notes of 20 semi-structured migrant interviews transcripts, as well as final data collection documentation.

Date of submission of the finalized dataset and final report: 31st December 2025

MMC estimates that the above activities will require approximately 300 days of work over the indicated period.

# Eligibility, qualification, and experience required

- Research organizations, universities, think-tanks, NGOs, CSOs, or consultancy companies with extensive track record in conducting surveys with recently arrived migrants.

- Legal and operational ability to independently carry out data collection and expertise with data collection specifically using an electronic survey tool and respecting the highest research standards.

- Proven expertise in researching / implementing projects on migration, human rights, and/or social justice;

- A proven experience in engaging with migrants;

- Languages: English is essential, other relevant languages would be a plus;

- The selected organization will have to sign and comply with DRC’s Code of Conduct.

# Technical supervision

The assessment shall be completed in close cooperation with MMC Europe. The selected consultant will work under the supervision of Giulia Bruschi, Data and Research Project Manager, MMC Europe,  email address: giulia.bruschi@mixedmigration.org.

# Location and support

The assignment will take place across the mentioned countries. All interviews are to be conducted face-to-face.

The Consultant will be expected to arrange transportation, accommodation (when relevant, for instance for the initial enumerators training), adequate equipment (including data collection devices such as tablets or phones), phone credit, and insurance for its team, and to make adequate provision in the Financial Proposal.

# Travel

No travel besides movements to and across the areas of research is expected for this consultancy. In case the consultant expects team members to come from abroad, it is responsible for all logistical, administrative and financial arrangements, and make adequate provision in the Financial proposal.

# Submission process

Please see Request for Proposal (RFP) section III, clause A.

Candidates should submit an application including:

- Documents requested in the Request for Proposal (RFP), section III, clause A

- Cover Letter

- CVs of the Project Manager and Field Coordinator(s), including references of previous relevant works (max. 4 pages)

- Technical proposal (max 10 pages) including: proposed approach and workplan, proposed profiles for the team (team leader, enumerators…)

- Financial proposal: budget (in CHF), which shall cover all costs over the course of the consultancy. The budget should be broken down as described below:

A. Consultancy fees – daily and total

B. Technical costs – phones, etc.

C. Travel costs, if applicable

D. Miscellaneous (e.g. insurance, printing, etc. – please specify in the financial proposal)

# Evaluation of bids

The evaluation process consists of three stages: 1) Administrative, 2) Technical and 3) Financial. This process is explained in the Request for Proposal (RFP), section III.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.

# Terms and Conditions

- The consultant(s) will report directly to Giulia Bruschi, Data and Research Project Manager, with regular updates and sharing of partial data and feedback and observations at intervals before the final deadlines for deliverables. They are also likely to interact with other MMC Europe staff, and partners to the project.

- All information presented, obtained and produced is to be treated as the client’s property and is considered as confidential for all purposes other than what is outlined in these ToR. Upon signing the contract, the selected consultant will be required to sign a confidentiality agreement. The material prepared by the consultant cannot be sold, used or reproduced in any manner (partially or in full) by the consultant without prior permission from MMC.