DRC

Terms of Reference (TOR)

for

Evaluation of the Danish Refugee Council Mine Action and Cluster Munition Programme II (MACM) Programme 2020 - 2024

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and  supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

The Humanitarian Disarmament & Peacebuilding core sector seeks to contribute to the fields of disarmament and peacebuilding through a focus on the safety and security of the displaced and conflict affected populations. This work is guided by a bottom-up, rights-based approach, which emphasizes the rights of conflict affected and displaced communities to safety and security. Community level activities include but are not limited to reducing the threat of landmines and explosive remnants of war, reducing the tensions which lead to conflict, and improving transparency and accountability in the relationships between local communities and duty bearers, such as local security providers.

# Purpose of the consultancy

The Danish Refugee Council seeks proposals from a consultant to evaluate the project which DRC Humanitarian Disarmament and Peacebuilding (HDP) have undertaken under the Mine Action and Cluster Munition Programme II, funded by the Ministry of Foreign Affairs of the Netherlands, and assess the extent to which DRC met the overall and specific objectives of the grant.

# Background

The MACM II programme sits within the Security and Rule of Law (SRoL) policy of the Ministry of Foreign Affairs of the Netherlands for “the catalytic and enabling contributions to Human Security having a direct and significant impact on lives and livelihoods. Released land can be used for agricultural purposes, enabling the socioeconomic situation in communities to improve. In addition, mine action can contribute to the safe return of internally displaced persons (IDP) and refugees and can support the resilience of vulnerable communities. With the mine action programme, the Netherlands contributes to SDG 16.1 ‘Reducing all forms of violence and related deaths’”.

The programme is managed by the Stabilization unit of the of the Ministry of Foreign Affairs of the Netherlands. It started in September 2020 and ends at the end of August 2024 although in one country activities ended in August 2023.

As stated in the Terms of Reference of the Midterm evaluation Mine Action and Cluster Munitions Programme 2020-2024, Appendix 3, the MACM II programme contributes to:

1.The promotion of human security and reduce the risk of physical violence against civilians through the implementation of the following activities:

• Clearance (i.e., surveying, mapping, marking and clearing) of mines, ERW, UXO, AXO and cluster munitions.

• Destruction of stockpiled mines, ERW, UXO, AXO and cluster munitions including dismantling production and storage facilities.

• Assistance to victims and their families, including rehabilitation and reintegration.

• Awareness raising and education of local populations about the risks of mines, ERW, UXO, AXO and cluster munitions/explosive ordnance risk education (EORE),

2. Capacity development of national and local mine action organisations/authorities to effectively address mine/IED-related concerns.

3. Strengthening the position of women as actors in reconstruction, peace processes, and socio-economic development.

In line with the MACM II objectives outlined above, DRC contributes to their achievement by striving to achieve the following outcomes: (1) Risk of harm reduced through safe behaviour and land release; (2) Productive land use improves livelihoods and access to basic services for men and women; (3) mine action is better managed and regulated, coordination increases transition of sector to national/local ownership; (4) quality of life for male and female victims improves.

# Objective of the consultancy

The purpose of this consultancy is to assess the degree of fulfilment of the specific aim of, and the results achieved by the project detailed below:

Title:  Mine Action and Cluster Munition Programme II

Implementing agency: Danish Refugee Council (DRC)

Donor: Ministry of Foreign Affairs of the Netherlands

Period of the grant: 1 September 2020 – 31 August 2024

Thematic areas:  Building on the external evaluation commissioned by the MoFA of the Netherlands, conducted in 2023, this evaluation will focus on key thematic areas: the extent to which humanitarian mine action activities have been integrated with peacebuilding and other DRC’s core sectors, namely protection and economic recovery; how localization and partnerships with local and national stakeholders have been sought and implemented, innovative practices as well as how effective gender & diversity based, inclusive approaches have been.

Geographical areas covered by the evaluation: The evaluation will extend across five (5) countries covered by the grant: Afghanistan, Libya, South Sudan, Sudan, and Ukraine.

Actors’ management and participation: It is expected that the evaluation will involve meeting (either face to face or through virtual interviews) with a variety of stakeholders in some countries of operation. This includes, but is not limited to:

- Project participants (beneficiaries) either in group or individually,

- Representatives from relevant national authorities,

- International programme staff,

- National programme staff,

- Management and support staff in DRC HDP HQ in Copenhagen, Denmark and Brussels, Belgium

- MoFA of the Netherlands

The evaluator/evaluation team will be expected to identify a diversified and representative group of interviewees based on diversity factors in a given context to ensure a comprehensive analysis and assessment.

Intended use of the evaluation findings and recommendations:

DRC HDP as well as their respective country offices will utilise the findings of the evaluation to inform and guide future planning and implementation of similar projects/programming. Also, the evaluation will help to ensure complementarity with other interventions in the mine action sector and enable mine action agencies to better communicate the impact of their work and how demining is linked to overall development and humanitarian responses. For the MoFA of the Netherlands, it will provide an external and independent report on the effectiveness, efficiency and sustainability of the use of their funding under this grant.

Scope of work and Methodology

This evaluation should provide a clear response to the following:

- To what extent did the project activities undertaken by DRC HDP under the remit of this project meet, at an individual country level and taken as a whole, deliver:

- The expected overall objective, and

- The expected specific outcomes of this grant?

Such assessment should be conducted based on the OECD DAC criteria: coherence, effectiveness, efficiency, impact and sustainability.

- What additional outcomes were achieved that have strengthened DRC HDP global and country strategies?

- What are the lessons learned from the implementation of this project, both at the global and individual country levels?

- To what extent this project was underpinned by gender and diversity mainstreaming considerations and how effective has this approach been?

- To what extent did this project align with efforts to seek integration between Humanitarian Mine Action activities and Peacebuilding, Protection and Economic Recovery?

- To what extent innovative practices and technologies have been developed, tested, and adopted over the implementation period of this project?

- To what extent this programme allowed to seek, develop, test and foster locally-led responses to make communities safer? Were partners included in the design, implementation and monitoring of activities? Have they taken part in capacity strengthening sessions? Have they received funding to implement activities? To what extent does locally-led sustainable development (LLSD) lead to better Security and Rule of Law (SRoL) outcomes – and what are the concrete and feasible ways to do it?

- Along the evaluation, further consideration and assessment of the following elements is expected:

- Coordination between DRC HDP and the MoFA of the Netherlands.

- Coordination across DRC’s core sectors

- Adaptation in response to contextual challenges including the impact of the Covid-19 pandemic, the restriction of access to Libya, the Taliban take over in Afghanistan, the war outbreak in Sudan, the unfolding of the war in Ukraine, as well climate related challenges in South Sudan.

- To what extent project activities have contributed to improve mine action management and regulation? To what extent coordination increased the transition of the HMA sector to national/local ownership? How is the link between achieved local level SRoL results, and intended national level and institutional outcomes best supported?

An inception phase of 15 working days will allow to develop an interview guide in agreement with DRC HDP. The evaluators should also engage with the MoFA of the Netherlands during the inception phase to understand expectations.

The Consultant/the team of consultants will be required to prepare a detailed methodology and work plan indicating how the objectives of the project will be achieved, and the support required from DRC.

It is envisaged that projects will be assessed through a desk review, interviews, and min 1 / max 2 field missions. Field missions are expected in two countries upon discussion with the DRC HDP team in HQs.

The methodology to be used is to be defined by the evaluator/evaluation team as part of their submission of their application and should be designed to effectively respond to the questions raised above.

Activities are expected to include, but not be limited to:

- Desk top review of all relevant documents provided by DRC and available from other sources

- Primary data collection from staff teams and key stakeholders through field visits in two countries.

- Review and discussion of initial findings with the DRC HDP evaluation management team

- Submission of draft/final report

Supporting documentation available:

- Original proposal, including logical framework (in English)

- Annual Reports for 2020-2021 and 2022 (in English)

- Project Mid-Term Evaluation 2023, commissioned by the Dutch MoFA (in English)

- The inception report 2020

- Work Plans, Budgets and budget reallocation requests for the years 2021, 2022, 2023 and 2024(in English)

- Evaluator/Evaluation team can also request additional documentation

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 Review | Presentation | Sourcing Documentation | 10 working days |
| Phase 2 Analysis | Draft report | Working meetings, discussions, collect data Min 1 / Max 2 field visits Prepare first draft report. Feedback from DRC to submit the final report | 30 working days |
| Phase 3 Reporting | Final report | Including an executive summary, key findings, and recommendations with a focus on Integrated approaches, Innovation and Localization | 10 working days |
| Phase 3 Reporting | Formal presentation of results/findings | PPT and formal presentation of results and findings to DRC HDP and the MFA of the Netherlands. | 1 working day |

The Consultant will provide the documentation by email in Word, Excel, PowerPoint.

The evaluator/evaluation team is required to deliver one evaluation report addressing the key evaluation criteria and questions as detailed above in section 3. Prior to the completion of the final evaluation report a formal presentation of results, based on the draft report, to the evaluation management teams, as well as to senior members of staff in relevant programmes. Offering an opportunity for feedback which can be considered within the final report. The final report should also be presented to the Dutch MoFA (which can be done online).

The evaluation report structure and presentation are to be suggested by potential evaluators/evaluation team as part of their submission. All written communications with DRC, including the final report, are to be in English.

The final report will be the property of DRC and the Dutch MoFA and must not be circulated to other parties by the author or any other parties without prior consent by all actors.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 2 months.

The evaluation is to be undertaken between January and May 2024. The evaluation will include a maximum of 10 days of fieldwork in min 1 / max 2 selected countries. Locations may change based on the current global context and travel restrictions. The evaluator/evaluation team will organise his/her/their own travel. All travel expenses will be reimbursed based on actual cost and submission of expense documentation.

The consultant shall be prepared to complete the assignment no later than 15 May 2024.

DRC plan on making two payments linked to the main milestones

A down payment equal to 10% at the beginning of the evaluation work.

A final payment upon delivery of the full and satisfactory findings/report, at the end of phase 3.

# Proposed Composition of Team

DRC will accept proposals from one evaluator or a team of evaluators.

# Eligibility, qualification, and experience required

## Essential:

- Experience of successfully undertaking similar evaluations for international NGOs in conflict/post conflict countries

- Research skills and knowledge of good practice in evaluation

- Interpersonal skills that evoke trust and are gender and culturally sensitive

- Strong verbal and written English language skills

- A knowledge of the humanitarian mine action sector and how it links with humanitarian action and socio-economic development.

## Desirable:

- Experience of carrying out evaluations of multi-year, multi-country grants

Eligibility:

The consultant/team of consultants will be home-based except during in-country visits.

It is kindly requested to submit two reference contacts from previous projects in the Technical Bid form Annex A.1.

# Technical supervision

The selected consultant will work under the supervision of:

- Camilla Roberti, Global Advisor Humanitarian Disarmament and Peacebuilding, Camilla.roberti@drc.ngo

- Rune Bech Persson, Global Advisor Training and Innovation, rune.bech.persson@drc.ngo

The evaluator/evaluation team will be expected to report regularly to the DRC HQ based evaluation management team on the progress of the evaluation and any issues arising. They will be available to respond to questions and provide any appropriate practical support. A timetable for reporting will be finalised following selection of the evaluator/evaluation team, the establishing of the work plan and the signing of a contract.

While visiting programmes, the evaluator/evaluation team will be under the responsibility of the Country Director/Head of Programme who will ensure that visits to relevant sites are facilitated and supported, and that any necessary in-country information is made available for analysis. This individual will also hold overall responsibility to assist the evaluator(s) in their work, for instance by setting up appropriate meetings with external actors, where possible and if requested by the evaluator.

# Location and support

The assignment will be homebased.

The Consultant will provide her/his own computer and mobile telephone.

# Travel

Min 1 travel, max 2 travels will be required to visit country offices and conduct an in-person evaluation.

The Consultant will therefore be expected to arrange transportation, insurance, food and to make adequate provision in the Financial Proposal.

# Submission process

Refer to the RFP document name of the document.

# Evaluation of bids

Please refer to the RFP letter invitation.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.

Annex

| Country | RE | NTS | TS | EOD | Clear. | VA | Capacity strengthening of local/national actors |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DRC HDP |  |  |  |  |  |  |  |
| Afghanistan | X | X | X |  | X | X | X |
| Libya | X | X | X | X | X |  | X |
| South Sudan | X | X | X | X | X |  | X |
| Sudan | X | X | X |  |  |  | X |
| Ukraine | X |  |  |  |  | X | X |