DRC

Terms of Reference (TOR)

for

Evaluation of the Diaspora Project Support

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

Via its Diaspora Programme, DRC has since 2010 engaged directly with diaspora actors to facilitate and strengthen their constructive engagement in support of persons affected by displacement and conflict. DRC recognizes diaspora as crucial transnational civil society actors playing a significant role, for people affected by displacement. Diasporas contribute to building resilience, responding to emergencies, and supporting early and long-term recovery. They are essential actors in support of durable solutions to displacement and in addressing root causes of displacement.

# Purpose of the consultancy

The DRC in Denmark seeks proposals from consultants to conduct an evaluation of the Diaspora Project Support (DiPS), funded by the Strategic Partnership (SPA) with Danida. The purpose of the evaluation is to assess if and to what extent partner diaspora organisations have enhanced their capacity to take impactful action to respond to needs of affected populations in their countries of origin, namely Afghanistan and Somalia. The evaluation shall help inform the DiPS’ Theory of Change (ToC) for DRC’s next strategic period - Strategy 2030. The development of the DRC Strategy 2030 will commence in the beginning of 2025 and have a strong focus on localisation. Thus, the evaluation seeks to capture learning and recommendations that can inform the strategic planning regarding the Diaspora Programme, including on how localisation ambitions can be fostered through the Diaspora Programme.

# Background

The Diaspora Programme is part of the DRC’s Localisation Unit. One of the main projects in DRC’s Diaspora Programme is the Danida-funded DiPS, through which DRC supports diaspora organisations in Denmark to conduct relief, rehabilitation and development activities in Somalia and Afghanistan, and to further enhance their capacities to function as diaspora civil society organisations.  The DiPS Programme has been running since 2010 in different countries. The last external evaluation was conducted in 2019. Since 2020, 61 Somali and Afghan diaspora organisations have received funding from the DiPS Fund, while 9 new partners have been preliminarily approved and are expected to start implementation during the fall of 2024. The diaspora organisations work through local partners in Afghanistan and Somalia to implement the projects. The DiPS fund is approximately DKK 1.7 million annually. Besides the financial contribution to projects, DiPS provides project management support to diaspora organisations and needs-based capacity development for Somali and Afghan diaspora organisations in Denmark, such as organisational development.

# Objective of the consultancy

The objectives of the consultancy are:

- Re-examine earlier projects in Somalia and Afghanistan (from 2020 onwards) to identify possible outcome/impact level effect for people of concern. Assess programme assumptions related to: 1) Relevance and local ownership; 2) Cost effectiveness; and 3) Sustainability.

- Explore the link between localisation and diaspora engagement and provide a comparison of the different “diaspora-led models” to DRC’s approach to working directly with national and local partners. Identify possible diaspora added value in fostering localisation and provide recommendations for how DRC can support localisation through the Diaspora Programme.

- Facilitate Theory of Change workshop with relevant staff in the DRC Localisation Unit and the DiPS Advisory Board (elected representatives from Afghan and Somali diaspora in Denmark) to inform the next strategic period (Strategy 2030).

# Scope of work and Methodology

The suggested methodology is to be presented by the consultant in the proposal. Methods expected include in-depth document review and key informant and small group interviews.

To re-examine earlier projects, interviews are expected to be conducted with DRC DiPS staff in HQ, Somalia and Afghanistan, diaspora partners and their local partners, local stakeholders and people of concern in project target areas.  To further understand the link between localisation and diaspora engagement and comparing approaches, interviews should be conducted with the Global Civil Society Partnership Advisor and partnership/localisation focal points in Afghanistan and Somalia, and DRC management (Head of Localisation Unit and Head of the Diaspora Programme).  Key documents for the in-depth review include: partner project documents and reports, DIPS ToC, Logframe, reporting, previous evaluations, DiPS guidelines for development and implementation of projects, DRC’s Global Civil Society Engagement Strategy and Implementing Partner Policy.

Depending on the security situation, field visits may be considered. DRC will, in consultation with the consultant, arrange or reimburse costs related to tickets and accommodation.  As field visits depend on the security situation, the evaluation must be planned in a manner where interviews can be held remotely on Zoom and/or Teams. Consultants may also utilize DRC monitoring staff in the country or consider contracting a local data collection firm.

The scope of the evaluation will include the combined portfolio of the 70 grants and partnerships supported through DiPS from 2020 onwards in Afghanistan, Somalia, and neighbouring countries. These grants are at different stages of development and implementation. The assessment of possible outcome/impact level effect will focus on a sample size of the 37 projects, which have finalized implementation. The sample size shall help inform an indicator on “% of DiPS supported projects with outcome/impact level effect for people of concern in Somalia, Afghanistan, and neighboring countries”. The consultant is expected to develop a selection methodology taking into consideration balanced geographical and sectoral representation. Furthermore, the selection should include different “diaspora-led models” including: 1) Diaspora organisations working through local NGOs with considerable capacity; 2) Diaspora organisations working with local authorities and ministries; 3) Diaspora organisations working with local civil society groups with limited capacity.

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 | Inception report | The inception report should set out the conceptual framework to be used in the evaluation, the key evaluation questions and methodology, including information on data sources and collection, sampling and key indicators. The inception report should also include information on timeline, team composition (or roles and responsibilities). | 5 days |
| Phase 2 | Data collection | Document review and interviews. Based on the data collection, the consultant should produce a document presenting key findings in bullet points for each evaluation question to inform the ToC workshop. | 10 days |
| Phase 2 | ToC workshop | Based on the initial findings, the consultant(s) shall facilitate a ToC workshop with relevant staff in the DRC Localisation Unit and Advisory Board to inform the next strategic period (Strategy 2030). The workshop is expected to be around 3 hours. | 2 days |
| Phase 3 | Draft evaluation report | Prior to drafting the report, the consultant(s) should share a report outline to make sure the format fits DRC’s needs. The consultant(s) shall share a draft evaluation report with the DRC DiPS team for feedback. A meeting will be arranged to discuss feedback prior to the finalization of the report. | 10 days |
| Phase 3 | Final evaluation report | The final evaluation shall follow the objectives outlined in this ToR and include recommendations for improvement and strategic considerations. | 2 days |
| Phase 3 | Presentation of report | Key findings and recommendations must be presented in a webinar incl. Q&A and discussion of recommendations (2 hours). | 1 day |

# Duration, timeline, and payment

The evaluation is expected to take approximately 30 working days. The draft evaluation report must be shared with DRC by the 1st of December 2024.  The evaluation must be finalized and presented by the 20th of December 2024. Payment will be received upon submission of the final evaluation report. 15% of the payment will be received upon submission and approval of the inception report.

# Proposed Composition of Team

Consultant or team of consultants.

# Eligibility, qualification, and experience required

Essential:

- Significant demonstrated experience with conducting reviews and evaluations for humanitarian and development organisations;

- Experience working with Theory of Change approaches and solid MEAL skills;

- In-depth understanding of the localisation agenda;

- Ability to work in a multicultural context as a flexible and respectful team player;

- Politically and culturally sensitive with qualities of patience, openness, and inclusion;

- Excellent English facilitation and writing/reporting skills are necessary.

## Desirable

- Experience working with civil society, especially volunteer organizations, diaspora or ethnic minority organisation’s engaging in development and/or humanitarian initiatives;

- Experience working with partner-led projects in a development or humanitarian context;

- Contextual knowledge on the situations in Afghanistan and Somalia;

- Previous experience collaborating/working with DRC.

# Technical supervision

The selected consultant will work under the supervision of:

- Marie Sønderholm Christensen, DiPS Coordinator, marie.christensen@drc.ngo

# Location and support

The Consultant(s) may be based on Denmark or remotely. The consultant(s) are expected to have their own office space and provide her/his own computer, mobile telephone, and other technical equipment needed.

# Travel

If travel is required, DRC will, in consultation with the consultant, arrange or reimburse costs related to tickets and accommodation. Costs for travel should therefore not be part of the financial offer.

# Submission process

Please refer to the RFP invitation letter.

# Evaluation of bids

Please refer to the RFP invitation letter.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.