DRC

Terms of Reference (TOR)

for

Consultancy for a study on migrants smuggling trends and dynamics in the Western Balkans

# Who is the Danish Refugee Council?

The Danish Refugee Council

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

The Mixed Migration Centre

Part of DRC, the Mixed Migration Centre (MMC) is a leading source for independent and high-quality data, research, analysis and expertise on mixed migration. The MMC aims to increase understanding of mixed migration, to positively impact global and regional migration policies, to inform evidence-based mixed migration responses for people on the move and to stimulate forward thinking in public and policy debates on mixed migration. The MMC's overarching focus is on human rights and protection for all people on the move. The three overall objectives of the MMC are:

- To contribute to a better, more nuanced and balanced understanding of mixed migration (knowledge)

- To contribute to evidence-based and better-informed migration policies and debates (policy)

- To contribute to effective evidence-based protection responses for people on the move (programming)

The MMC is a global network, with regional hubs in Africa, Asia, Europe and Latin America hosted in DRC regional offices, and a small central team in Geneva. The MMC is part of, and governed by, DRC. While its institutional link to DRC ensures MMC's work is grounded in operational reality, it acts as an independent source of data, research, analysis and policy development on mixed migration for policy makers, practitioners, journalists, and the broader humanitarian sector. The position of the MMC does not necessarily reflect the position of DRC. For more information on MMC visit our website here: www.mixedmigration.org

# Purpose of the consultancy

The Mixed Migration Centre Europe based in the DRC office in Geneva seeks proposals from a consultant for a study on migrant smuggling trends and dynamics and highlight solutions in the Western Balkans in support of DRC’s Europe Regional Program: Protecting Rights at Boarders (PRAB).

# Background

Regional context

Protecting Rights at Borders (PRAB) is an initiative that consists of protection and legal aid groups who focus on ensuring human rights are upheld at both the European Unions (EU's) external and internal borders. Pushbacks at Europe’s borders: a continuously ignored crisis is the eighth report in the series published by PRAB, an initiative aiming to document evidence of the use of illegal pushbacks in the context of border management in Europe. The initiative, through its collaborative efforts, also serves to advance strategic litigation across borders for people affected by widespread and systematic pushbacks and other rights violations at Europe’s doorstep. Data is gathered by nongovernmental organisations (NGOs) and grassroot initiatives across Europe, who have joined forces in the PRAB initiative to create a solid evidence-base, anchored in direct observation and interviews with persons on the move.

MMC Europe is currently operational in Europe through several data collection initiatives. MMC Europe is collecting data in Italy, Greece and Spain on a number of different initiatives focusing on various topics, including: impact of irregularity on access to services and employment; migration-related decision making along journeys in Europe; understanding of mixed movements and the associated protection risks for refugees and migrants arriving through the Western Mediterranean and Atlantic routes; discrimination for people of migratory background in access to housing.

Previous research on smuggling dynamics in the Western Balkans

MMC EU conducted a study on mixed migration trends and dynamics in the Western Balkans in May 2023, which included a section on smuggling of migrants. The study provides good basic information on smuggling trends and dynamics in the WB, at the time of the data collection for the study (early 2023). This includes:

Smuggling networks: Human smuggling involves various roles such as package dealers, fixers, gatekeepers, prospectors, accommodation providers, complicit police, and escrow managers, often forming consolidated networks with ties to organized crime.

Contacts, contracts, and fees: Smuggling arrangements are made through word of mouth, online platforms, or intermediaries, with fees varying based on the route and services offered, often facilitated through informal money transfer systems like hawala.

Payment means and financing: Payment methods for smuggling services include full pre-payment with escrow, debt-financed arrangements, and pay-as-you-go cash payments, with funds sourced from loans, savings, commissions, and asset sales.

Efforts to counter smuggling: Law enforcement agencies in the Western Balkans, sometimes in collaboration with EU entities, conduct arrests and operations targeting smugglers, but face challenges including legal disparities, police corruption, weak border security, and overwhelmed resources.

Since the time of the previous study the situation has been evolving. On the one hand, anti smuggling operation have increased. However, smuggling networks have adapted, became more sophisticated and irregular migration continue, with 3,049 people recorded using the Western Balkans route into Europe, the first two months of 2024.  Meantime in April  the new migration and asylum EU pact has been approved and the reform may, according to some analyst, encourage pushbacks at Serbia’s borders, worsening a broader rule-of-law crisis.  In addition, a recent EU project to Support to Strengthen the Fight against Migrant Smuggling and Trafficking in Human Beings in the Western Balkans (EU4FAST) was recently launched on this route.

# Objective of the consultancy

Purpose of the study

The primary objectives of the consultant will be to produce a state-of-the-art study into migrants smuggling trends and dynamics to and through the Western Balkans, updating and enriching the information already published in the above-mentioned report and taking stock of the above-mentioned developments. The study is expected to include analysis of the impact of latest developments on the risks experienced by people on the move on the Western Balkan routes and provide recommendations on how to minimize them.

Key research questions

General mixed migration trends and dynamics

- How has migration to and through the Western Balkans evolved in the last year? How it is expected to further evolve?

- Who is undertaking mixed migration journeys? What are their socio-demographic profiles?

- What are the main factors influencing the decision to migrate to or through the Western Balkans?

- What are the main routes, migration hubs, border-crossing points and modes of transportation into and through the region?

- What are the risks people on the move are exposed to during their journey? How risks can be mitigated, also consider existing coping mechanisms put in place by migrants and/or their recommendations??

- What are people’s movement intentions? Do they intend to stay in the region, or do they wish to migrate onwards to Western Europe? For what reasons? What’s the impact of migration policies on their choice of final destination? Are there any other factors influencing their decisions? Are migrants aware of the EU Pact, and has that impacted their decision?

Specific migrant smuggling trends and dynamics

- What are the specific roles, interactions, and organizational structures within existing human smuggling networks in the Western Balkans, and how they have evolved over the last year?

- How do migrants and smugglers establish contacts, negotiate contracts, and agree on fees for smuggling services in the Western Balkans, and what are the implications of these arrangements on the use of smugglers?

- What are the predominant methods and sources of financing used by migrants to pay for smuggling services in the Western Balkans, and how do different financing mechanisms impact the vulnerability of smuggled migrants?

- What are the risks irregular migrants are exposed to in the context of smuggling? Who are the perpetrators of violations?

- How effective are the current law enforcement efforts in the Western Balkans in countering migrant smuggling? How do they impact on the vulnerability of smuggled/irregular migrants?

- How anti-smuggling operations are they expected to evolve along with the implementation of the new EU Pact and what kind of impact will they have on smuggling routes and people on the move?

Scope of work and Methodology

The consultant is expected to use a combination of desk research, compiling secondary (data) sources, in-country key-informant / stakeholder interviews and interviews with refugees and migrants moving to and through the Western Balkans.

Ideally, the consultant will identify a few  relevant migration hubs (3 to 4) to conduct fieldwork. Additionally, interviews will be conducted in capital cities and remotely. The pool of interviewed stakeholders ideally will be a mix of:  administrative bodies / law enforcement at both national and European level (i.e. anti-smuggling task force, Europol, Interpol, the European Migrant Smuggling Centre (EMSC), Frontex, European Commission, etc..), journalists and experts specialized in smuggling/anti-smuggling, representatives of local CSOs, humanitarians working with (I)NGOs and UN agencies. In total the consultant is expected to conduct a minimum of 15 stakeholder interviews and 10 interviews with refugees and migrants.

In writing up the study, the consultant is expected to follow MMC’s editorial guidelines.

Time frame

From the signature of the contract:

- 1 weeks for the inception report (more detailed description of the research approach and methodology; literature review and data sources; key interview locations; proposed key informants to be interviewed and interview tools; indicative guidelines for interviews with KIIs; draft table of content of final report) including the integration of comments/inputs by MMC;

- 1 week for validation of the inception report and integration of comments by MMC;

- 3 weeks for interviews with stakeholders as well as refugees and migrants moving to and through the Western Balkans;

- 1 week for data analysis, report drafting and submission of the first draft of the report;

- 1 week for submission of the final draft, integration comments/inputs by MMC;

- The transcript of qualitative stakeholder and refugee and migrant interviews should be submitted within two weeks after the submission of the final report.

Number of working days: approx. 30 days

Estimated start date of consultancy:   17rd May 2024

Date of submission of the final report:  28st June 2024

The Consultant will be required to prepare a detailed methodology and work plan indicating how

the objectives of the project will be achieved, and the support required from DRC-MMC.

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 Inception | Inception report | Inception report including a literature review, a clarification of the methodology and a workplan, a mapping of potential actors to meet, a plan of field trip as well as a proposed outline of the final report | 5 working days |
| Phase 2 Data collection and analysis | Transcripts and weekly updates | Transcripts of qualitative interviews with stakeholders, refugees and migrants as per the workplan and field visit, weekly updates to the MMC/DRC team. | 18 working days |
| Phase 3 Reporting | Final report | Final report developed using the outline included in the inception report and Power Point presentation highlighting key findings | 7 working days |

The Consultant will provide the documentation by email in Word format.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 32 working days.

The consultant shall be prepared to complete the assignment no later than 28th   June 2023.

Payment schedule:

30% at the submission of the inception report

70% at the submission and acceptance by DRC of the final report and PowerPoint presentation.

# Proposed Composition of Team

Not applicable.

# Eligibility, qualification, and experience required

## Essential:

- Advanced degree (Master or PhD) in migration studies or the social sciences, with expertise in qualitative and quantitative research methods.

- A minimum of five years of experience in designing and leading research on migration and similar relevant topics.

- A proven knowledge and understanding (e.g. through prior publications) of mixed migration dynamics in Europe and the Balkans.

- Familiarity with the Western Balkans context and proven access to relevant stakeholders in the region.

- Excellent analytical and reporting skills.

- Excellent command of spoken and written English

## Desirable:

- Familiarity with the MMC 4Mi Methodology.

- Previous experience with MMC or DRC.

# Technical supervision

The assessment shall be completed in close cooperation with DRC Regional Protection Coordinator (RPC) and MMC Europe. The selected consultant will work under the supervision of:

Head of MMC Europe, Roberto Forin, roberto.forin@mixedmigration.org

Technical Supervision of DRC RPC, Ranya Ghadban, Ranya.ghadban@drc.ngo

# Location and support

The assignment will be entirely home-based with a field mission to be conducted by the consultant in the target country of research. MMC and DRC will not provide any support in terms of accommodation, furniture of an office space or logistical support for the duration of the assignment. The consultant will provide her/his own computer and mobile telephone.

Although MMC will support the consultant in the identification of potential respondents throughout its network, the consultant is responsible for the identification of relevant respondents to fulfil the objectives of the research project.

# Travel

The assignment will require the consultant to conduct a field mission in the target country of research, in order to conduct the appropriate data collection tasks. Details of the travel (duration, exact locations, specific objectives to meet the mission’s goals) will be discussed based on the technical proposal submitted by the selected consultant, and after a security assessment of the travel plan.

MMC and DRC will not provide any support in terms of accommodation, furniture of an office space or logistical support for the duration of the travel. The Consultant will therefore be expected to arrange transportation, accommodation, insurance, food and to make adequate provision in the Financial Proposal.

# Submission process

Please see Request for Proposal (RFP) section V

# Evaluation of bids

The evaluation process consists of three stages: 1) Administrative, 2) Technical and 3) Financial. This process is explained in the Request for Proposal (RFP), section III.

Only proposals that administratively compliant and reached minimum technical score (14 points) will be contacted for an interview with the panel to ensure their understanding of the consultancy services.