DRC

Terms of Reference (TOR)

for

Concept Note and Proposal Development

Denmark’s “Whole of Route Programme - Assisting People on the Move and Preventing Irregular Migration Through a Whole-of-Route Approach”

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the Consultancy

The Danish Refugee Council is seeking the services of a Consultant to provide expert technical advice on matters pertaining to mixed migration and to support in the preparations for, coordination, design and writing of a concept note and proposal, in response to Danish MFA’s “Whole of Route Programme – Assisting People on the Move and Preventing Irregular Migration Through a Whole-of-Route Approach,” for which a call for proposals is anticipated to be released in mid-September.

The programme is anticipated to contribute towards ensuring that migration along the three main Mediterranean (and Atlantic) routes is safer and people on the move have access to information, direct assistance and services, which help them make safer decisions and be in less vulnerable situations. The programme design will be in line with and informed by international human rights standards, HRBA, gender, youth and climate change where relevant and other Danish MFA priorities in relation to migration.

The specific objective of the programme is to contribute to the prevention of irregular migration and ensure that people on the move along the migration routes are less vulnerable through accessing higher quality services and information required to make better informed and less risky decisions along migratory routes.

The programme is furthermore anticipated to include four main outcomes:

Outcome 1: Potential migrants (before and during their journey) make better informed decisions about possible migration.

Outcome 2: People on the move access protection systems and services as well as livelihood opportunities in a timely and rights-based manner where they are.

Outcome 3: Local duty bearers and systems along the routes deliver better quality services in an inclusive and sustainable way to better protect people on the move, and make migration more safe, orderly and rights-based.

Outcome 4: Dis-information relating to migration is reduced.

# Background

DRC is well positioned to respond to the anticipated call for proposals given the organisation’s experience designing and implementing similar protection-centered and routes-based programming assisting people on the move and communities affected by mixed migration. Furthermore, DRC and its potential partners have well established presence along the routes and hot spots anticipated to be prioritized in the call for proposals. The organization has undertaken preliminary work in the development of a draft concept, which this consultancy will build up and further tailor to the specificities of the upcoming call for proposals.

# Objective of the consultancy

The main objective of this Consultancy is to support DRC and partners in preparing for, coordinating, designing and writing a proposal to respond to the anticipated call for proposals for Danish MFA’s “Whole of Route Programme – Assisting People on the Move and Preventing Irregular Migration Through a Whole-of-Route Approach.”

The Consultancy is anticipated to be divided into two phases, which will entail the following:

Phase One | Pre-Release of the Call for Proposals (August – Early-September)

- Review donor guidelines and instructions to ensure the concept note is developed in full alignment with donor expectations, formats and regulations or based what is known to-date.

- Undertake a comprehensive desk review to identify knowledge gaps in DRC’s existing draft concept pertaining to the context, needs and risks associated with the anticipated call for proposals and expected geographical priorities.  The desk review will also assess DRC and partner organisations’ past results and lessons learned relevant to the anticipated call for proposals based on the Danish MFA’s “Whole of Route Programme” document.

- Organize and facilitate a virtual design workshop in advance of the release of the call for proposals to:

  - Assess DRC and partners’ existing draft concept note against "The Whole of Route Programme" document.

  - Ensure the concept note is inclusive of and aligned with the MFA's cross-cutting priorities (HRBA, LNOB, gender, youth, HDP-Nexus, climate change and environment).

  - Agree on design principles (centrality of protection, value for money, systems-thinking approach, etc.).

  - Develop a draft theory of change.

  - Refine regional and country contextualization, prioritization and identification of gaps that need to be addressed.

  - And, commence the process of identifying and documenting risks and mitigation actions.

- Further develop and/or revise DRC and partners’ existing concept note with the “Whole of Route Programme" document. This will entail:

  - Developing a "best guess" concept note narrative structure and guidance informed by the “Whole of Route Programme" document and its associated assessment criteria.

  - Coordination and collection of global inputs within DRC and between partners.

  - Coordination and collection of inputs from DRC’s regions and country offices.

  - Consolidation and leading the final writing of narrative inputs, ensuring coherence and clarity in the overall concept in alignment with the “Whole of Route Programme" document.

  - Coordination and internal and partner review and validation of the concept note, including both technical quality assurance and compliance reviews.

- With support from DRC and partner MEAL staff, contribute to the development of a results framework and MEAL plan by:

  - Helping to design a MEAL architecture that aligns with the concept note.

  - Developing a draft MEAL framework.

- With support from DRC and partner finance staff contribute to the development of an indicative budget and ensure the budget and the concept note are aligned.

Phase Two | Post-Release of the Call for Proposals (Mid-September – October)

- Asses draft concept note, developed in phase one, against the call for proposal criteria and develop an updated work plan and roles and responsibilities matrix.

- In coordination with the assigned DRC focal points on partnership, develop and/or finalize partnership capacity statements against call for proposal requirements.

- Organize and facilitate a design workshop to:

  - Finalize route selection against the call for proposal criteria.

  - Update mapping of partners against the final route selection.

  - Refine the theory of chance against the call for proposal criteria.

  - Identify programmatic gaps, modifications and additional required of the draft concept note developed during phase one and workshop the design revisions.

- Further develop and ensure alignment of the concept note developed during phase one of the consultancy with the call for proposals. This will entail:

  - Coordinating DRC and partners for additional inputs and revisions necessary for full proposal development.

  - Leading the overall writing of narrative revisions and additions for the full proposal and any associated annexes.

  - Coordinating, reviewing and consolidating geographic-specific and technical inputs from DRC and partners.

  - Coordinate DRC and partner reviews and validation of the full proposal, including technical and compliance quality assurance reviews.

- With support from DRC and partner MEAL staff, contribute to the refinement of the results framework and MEAL plan by:

  - Finalizing the design a MEAL architecture.

  - Finalizing the proposals accompanying MEAL framework.

- With support from DRC and partner finance staff, finalize budget development and ensure the budget and final proposal are aligned. DRC will take responsibility for final quality assurance of the budget, but the consultant is expected to the identification and detailing the different costs and budget lines required to effectively and efficiently resource the concept.

# Scope of Work and Methodology

The Consultant will be required to prepare a detailed methodology and work plan indicating how the objective of the consultancy will be achieved, and the support required from DRC.

At the start of the consultancy, the Consultant will review and familiarize themselves with existing documentation from the Danish MFA, DRC (including the Mixed Migration Center) and partners. The Consultant will be provided with a debrief on the work to the “Whole of Route Programme," as well as mixed migration related initiatives undertaken by DRC and its partners, which are relevant to the programme.

The Consultant is expected to hold regular, scheduled coordination meetings with key DRC stakeholders (to be identified collectively between the Consultant and DRC’s focal point[s] for this initiative) to ensure progress against the agreed workplan and to adapt when and as needed.

The final proposal and budget submitted by the Consultant must be developed to a standard that can be readily submitted to the donor following technical review.

# Deliverables

The Consultant will submit the following deliverables as mentioned below. The Consultant will provide all documentation by email as well as upload to DRC’s Share Point site, to which access will be provided.

| Deliverables | Due Date |
| --- | --- |
| Phase One ¦ Pre-Release of the Call for Proposals |  |
| - Detailed work plan incorporating all requirements and deliverables | Day 3 |
| - Desk review | Day 10 |
| - Organization and facilitation of virtual pre-release design workshop | Day 15 |
| - Development and/or revision of DRC and partners’ existing concept note, including draft results framework, MEAL plan and indicative budget | Day 25 |
| Phase Two ¦ Post-Release of the Call for Proposals |  |
| - Develop updated work plan and roles and responsibilities matrix against the call for proposals | Day 30 |
| - Develop partnership capacity statements | Day 40 |
| - Organization and facilitation of in-person design workshop | Day 40 |
| - Refinement of phase one concept note and development and finalization of a full proposal for submission to donor, including draft results framework, MEAL plan and indicative budget | Day 55 |

# Duration, Timeline, and Payment

The consultancy will run between August and October 2024. This consultancy includes 60 working days. The consultancy will be home-based, not requiring travel. However, the Consultant will require significant interaction with DRC HQ staff based in Copenhagen, regions and country operations and, therefore, is expected to manage time zones suitable for DRC and partner staff.

Deliverables

| Deliverables | Due Date | Associated Payment |
| --- | --- | --- |
| Phase One ¦ Pre-Release of the Call for Proposals |  |  |
| - Detailed work plan incorporating all requirements and deliverables | Day 3 |  |
| - Desk review | Day 10 |  |
| - Organization and facilitation of virtual pre-release design workshop | Day 15 |  |
| - Development and/or revision of DRC’s existing concept note, including draft results framework, MEAL plan and indicative budget | Day 25 | 50% |
| Phase Two ¦ Post-Release of the Call for Proposals |  |  |
| - Develop updated work plan and roles and responsibilities matrix against the call for proposals | Day 30 |  |
| - Develop partnership capacity statements | Day 40 |  |
| - Organization and facilitation of in-person design workshop | Day 40 |  |
| - Refinement of phase one concept note and finalization of a full proposal for submission to donor, including draft results framework, MEAL plan and indicative budget | Day 55 | 50% |

# Proposed Composition of Team

Interested teams or consultants are expected to include list of positions required in the consultant team.

# Eligibility, Qualifications, and Experience Required

## Essential:

- A minimum of five (5) years of relevant experience related to mixed migration, with specific experience in designing and implementing routes-based approaches.

- Experience developing proposals with multi-partner submissions and demonstrated ability to effectively collaborate and coordinate across partners and diverse geographies and contexts in a timely manner.

- Demonstrated knowledge of the use of the latest version of Danida donor formats is an added advantage.

## Desirable:

- Master’s Degree in migration studies, International Human Rights Law, humanitarianism, international development or related advanced degree.

- Previous experience developing similar multi-country, regional and global proposals and budgets.

- Strong and practical understanding of Danida policies and donor guidelines.

- Strong facilitation skills and ability to coordinate, collaborate, analyse and draw out technical input from partners, working remotely.

- Excellent analytical, interpersonal, communication and reporting skills.

- Ability to work across multiple time zones.

- Exceptional English writing skills.

Interested teams or consultants are expected to submit the following items in response to these terms of reference:

- Updated CV(s)

- A technical proposal (no more than 5 pages) that covers:

(i) the consultant’s suitability for the assignment, (ii) suggested process, approach and methodology, and (iii) Workplan

- A budget covering daily consulting fees in USD inclusive of applicable taxes (see section below on ‘proposal evaluation’ for details)

- A statement of availability for the duration of the consultancy

- One or more work sample(s) of similar assignments, and

- Completed DRC Supplier Profile Registration Form.

# Technical supervision

The selected consultant will work under the supervision of Patrick Phillips, Head of Unit for Programme Quality and Integration.

# Location and Support

The assignment will be home-based over the course of 60 working days. DRC’s HQ based in will be available to provide support in coordinating and contacting DRC staff and partners. However, the Consultant is expected to manage time zones suiting DRC staff based in Western and Eastern Africa, the Middle East and Europe.

# Travel

Travel for this consultancy is only anticipated for the phase two design workshop, which is expected to entail 5 to 7 days hosted in a DRC regional or country office.

# Submission Process

Please refer to the Invitation letter.

# Evaluation of Bids

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services. For the award of this project, the evaluation criteria below will govern the selection of offers received. The evaluation is made on a technical and financial basis.

The proposed offers by bidders will be evaluated using, inter alia, the following criteria, and points will be allocated in the scale from 1 to 10 for each of the criteria stipulated below, whereas the weighting is as follows:

| 1. Consultant qualifications (50 %) (Documented with the filled-out Supplier Registration Form and a list of least one similar assignment executed, including sample(s), as well as CV.) | - Documented experience in designing and implementing mixed-migration and routes-based programming (25%) - Documented experience in developing high-value proposals in response to funding opportunities from major international donors (25%) |
| --- | --- |
| 2. Proposed services (50 %) (Documented with the technical proposal) | - Content of the proposal suitable for and meeting the requirements outlined in the terms of reference (25%) - Proposed methodology (25%) |
| Total | 100% |

All bidders must obtain an average score of at least five for the total technical scoring, in order to proceed to the financial evaluation.  The financial offer will then be weighed against the technical offer.

The total cost of the financial offer should be mentioned in the Annex A.2, while the breakdown of the budget should be attached separately. The budget should be broken down as described below:

A. Consultancy fees – daily and total, inclusive of VAT; in DKK.

B. Technical costs – tool development, analysis, etc

C. Travel costs, if applicable (international or domestic costs incurred only upon pre approval of travel; proof must be submitted for payment and that DRC will only reimburse actual cost as per DRC’s internal guidelines)

D. Miscellaneous (e.g. visa fees, immunizations, printing – please specify in the financial proposal)

GRAND TOTAL FOR FINANCIAL OFFER

Confidentiality

All information presented, obtained and produced is to be treated as DRC’s property and is considered as confidential for all other purposes than what is outlined in the terms of reference.

The selected consultant is upon signing of the contract required to sign a confidentiality agreement (Annex H_NDA). The material prepared by the consultant cannot be sold, used or reproduced in any manner (partially or in full) by the consultant without prior permission from DRC.