DRC

Terms of Reference (TOR)

for

Cash and Markets Enhanced Preparedness and Response Capacity

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The Headquarters of the Danish Refugee Council seeks proposals from to support a Global Consultancy to improve our Cash and Markets Preparedness and Response Capacity processes and tools across DRC’s Response Framework.

# Background

DRC promotes Cash and Voucher Assistance (CVA) when appropriate and feasible as an optimal assistance modality – to maximise recipients’ dignity, flexibility, and choice to meet self-prioritised needs. CVA is a tool we leverage to address both immediate basic needs but also durable solution outcomes. DRC implements multipurpose cash assistance as well as sectoral cash assistance across it five core sectors, i.e. Protection, Economic Recovery, Humanitarian Disarmament and Peacebuilding, Shelter & Settlement and Camp Coordination and Camp Management (CCCM).

In today’s world, displacement is driven by a multiplicity of intertwined political, social, environmental, economic factors. Rapid and slow onset natural disasters overlap with man-made disasters. Already displaced populations experience new shocks and stresses over time. In light of these trends, humanitarian assistance is more than ever challenged, and on the backdrop of an increasingly wider humanitarian financing gap overall, it is imperative that we find ways to accelerate disaster risk reduction and early recovery, while continuing to deliver timely, efficient and scalable basic needs response.

In 2023, DRC conducted an internal review of its Emergency Response capacity. The review identified a need for enhanced preparedness and response capacity in order for DRC to be better equipped to address the complexity of the shocks people of concern face.

An integral part of this capacity enhancement exercise will include defining how we can best support local actors and systems in responding to and recovering from these multilayered shocks. Whilst in immediate stages of a rapid on-set emergency, it is challenging to capitalise on opportunities to coordinate and leverage with local actors and systems to meet basic and protection needs, in the Early Recovery phase, we intend to, where justified and safe to do so, move towards utilising response options that seek to use, support and strengthen local capacities (through local actors) where they may exist and can be safely utilised. We also believe that by investing more systematically in pre-crisis systems analyses and preparedness plans, we’ll be in a better position to work with and through local actors as early as possible in the response, hence significantly accelerating recovery and ensuring accountability.

As part of DRC’s Strategy 2025, DRC has a strategic commitment to increasing the systematic uptake and use of Market Systems Approaches to support programming across the displacement cycle and thus across DRC’s Response Framework (Emergency Response, Durable Solutions and Root Causes). Within DRC, Market Systems Approaches currently encapsulates both market-based programming and market systems development due to DRC’s position working with people of concern across the displacement cycle which requires holistic use of systems thinking in both humanitarian and longer-term development or resilience programming. In addition, DRC recognises the application of systems thinking for both economic and social systems and its relevance across DRC’s five core sectors – Protection, Economic Recovery (Decent Livelihoods, Financial Inclusion, Food Security), Shelter & Settlement (includes WASH), Humanitarian Disarmament and Peacebuilding (includes demining), and CCCM.

DRC’s strategy seeks to support country offices to take the practical steps to embedding this within their practices.

# Objective of the consultancy

This Consultancy will seek to enhance DRC’s approach to identifying and leveraging opportunities (with justification) for systems-based approaches as part of our emergency and early recovery programming. This will be done through:

- An assessment of DRC’s current CVA and Market-Based Programming (MBP) preparedness capacity and;

- An improvement of DRC’s CVA and MBP toolbox (processes and tools) in support of our Emergency and Early Recovery programming

# Scope of work and Methodology

The Consultancy will be divided into 3 main activities:

Activity 1 – Assessment of DRC’s current CVA and MBP preparedness and response capacity

The Consultant will propose a methodology to assess the operational preparedness for CVA and MBP across DRC’s HQ, and its regional and country operations.

Key considerations should include (but are not limited to):

- Country office ability (competency, capacity, financing) to conduct and utilise pre-crisis analysis (e.g. development of crisis scenarios)

- Extent to which systems-thinking is built into preparedness plans (e.g. identification / analysis of critical market systems, potential list of market support interventions and pre-positioning for their implementation, etc.)

- Strengths of Stakeholders Mapping, including potential local partnerships and positioning on coordination platforms

- Required funding access for anticipatory action and preparedness activities

- CVA and MBP capacity among Programme/MEAL, Operations and Support staff; incl. familiarity with DRC’s Modality Due Diligence (MDD) tool

- State of contracting with Financial Service Providers to deliver CVA

- Summary of critical best practices / operationalisation tips from external organisations / institutions

Expected deliverables:

- 10-page max report using a SWOT model, with technical, operational and strategic recommendations to reinforce DRC CVA and MBP preparedness processes and tools – if significant discrepancies are identified across regions, the Consultant will be expected to provide separate recommendations per region

- 4 online regional workshops to present and debate findings and recommendations

Activity 2 – Development of a Modality Due Diligence Plus (MDD+) tool (and accompanying Standard Operating Procedure (SOP))

After familiarising him/herself with DRC’s existing MDD tool, the Consultant will develop a second version of the tool, aimed at guiding and incentivising country operations to identify opportunities / entry-points for market support activities (beyond CVA/MPCA) early on in the response designed for use by typical humanitarian field teams, not market systems experts. The Consultant is expected to focus on the user experience in terms of the design of the tool (content, language, look, integration/reference to related materials) to make sure it meets the needs of field teams.

The Consultant will propose a methodology to collect internal (and, if relevant, external) suggestions on the structure and content of the tool and its accompanying SOP.

Expected deliverables:

- A draft MDD+ tool and SOP

- One test of the draft tool (which could either be a remote rollout of the tool with a country office or a feedback session with a group of relevant staff) and recommendations for further testing and rollout

Activity 3 – Ad-hoc CVA expertise

Expected deliverable: no concrete outputs can be defined in advance of the work, but the consultant is expected to dedicate up to 5 days to providing ad-how CVA expertise based on country requests.

The Consultant will work directly with the Head of the Global Economic Recovery Unit and the Global Inclusive Markets Advisor, as well as relevant members of the Economic Recovery Core Group (Global and Regional staff focal point for CVA and MBP competency areas).

Work Risks and Mitigations:

- Risk: The Consultancy will be carried out during the always busy months of the end of the year, when country and regional operations have limited bandwidth to absorb additional work.

  - Mitigation: The Global Unit will proactively prepare a comprehensive desk review and ensure a selection country / regional staff are ready to dedicate time to this effort.

- Risk: Staff not immediately responsible for Emergency Response and/or CVA delivery do not prioritise this work

  - Mitigation: While compartmentalising Cash and Markets in livelihoods programming still happens at times within DRC, it is increasingly understood and acknowledge across the organisation that Cash and Markets are relevant across sectors and functions. The relevant cross-cutting staff, including Emergency Coordinators, will be active contributors to this work.

# Deliverables

The Consultant(s) will submit the following deliverables as mentioned below.

| Phase | Expected deliverables | Maximum expected timeframe |
| --- | --- | --- |
| Phase 1 Inception | - Kick-Off Meeting - Inception report | 2 days |
| Phase 2 Activity 1 | - 10-page report SWOT analysis and recommendations - 4 online workshops | 20 days |
| Phase 3 Activity 2 | - A draft MDD+ tool and SOP - One test run of the MDD+ tool and recommendations for future testing and rollout | 13 days |
| Ongoing Activity 3 | - Proof of strategic and technical support provided to regional and country offices (e.g. minutes of meeting, reviewed documents, log of calls, etc.) | 5 days |

# Duration, timeline, and payment

The consultant shall be prepared to complete the assignment, preferably by the 25th of January 2024 and as such should be able to start initial work in November 2023.

The expected level of efforts is 40 days, though applicants are welcome to suggest a different LoE to deliver the outputs by the delivery deadline.

All work will be done remotely.

Payment will be in tranches, coinciding with the satisfactory completion of deliverables at different stages of the project:

- Tranche 1 – upon completion of Phase 2

- Tranche 2 – upon completion of all deliverables

# Proposed Composition of Team

The composition of the team will be to the discretion of the Consultant. Individuals are encouraged to apply.

Should the Consultant be sub-contracting work to other Consultants rather than submitting a joint proposal, this must be made clear (including the risks of doing so) within the proposal. Quality assurance mechanisms of deliverables must be explained as part of the proposals.

# Eligibility, qualification, and experience required

## Essential:

- Proven experience in conducting an Organisational Cash and Voucher Assistance Readiness Analysis

- Proven experience in designing and implementing or quality assuring CVA programming

- Proven experience in conducting market systems analysis in early recovery and protracted crisis contexts to support uptake and use of market-based programming

- Confidence in applying generic techniques for market-based programming to any sector with assistance from sector specialists if and when needed (it is likely that this Consultancy will focus on programming related to MPCA, food security, livelihoods, protection, WASH, and shelter)

- Proven experience / understanding of at least one method of market analysis in emergency contexts – RAM, EMMA, PCMA

- Experience in pivoting programmes from in-kind/direct humanitarian assistance to forms of market-based programming

- Experience in market-based programming beyond just CVA. Examples of design and implementation of market support interventions required as evidence for the proposal.

- Understanding of the institutional, operational and contextual challenges of utilising MBP (e.g. the Consultant must have experience beyond field level to inform the strategic discussions on this topic)

- Understanding of emergency response programming and humanitarian principles

## Desirable:

- Understanding of Emergency Preparedness and Response Plans (EPRPs) to inform market-based programming integration opportunities within preparedness activities

- Understanding of Sphere / HSP companion guides and application to MBP including MiSMA and MERS

- Qualification:

  - At least Degree in Master’s level in relevant degree (Bachelor’s level will be considered if sufficient work experience to support application)

- Experience:

  - A minimum of 7 years of work in the humanitarian sector with large proportion delivering or improving programme quality through application of market-based programming.

- Skills and knowledge:

  - Working with displacement-affected communities in emergency and early recovery response environments in different contexts – urban, remote and camps.

- Language requirements:

  - Written and spoken fluency in English

  - Working knowledge of French is an advantage

# Technical supervision

The selected consultant will work under the supervision of:

- Katie Whitehouse, Global Inclusive Markets Advisor

- Solenne Delga, Head of Global Economic Recovery Unit

# Location and support

Remotely (100%)

The Consultant will provide her/his own computer and mobile telephone.

# Travel

No travel is foreseen for this work.

# Submission process

Please Refer to the RFP document and invitation letter.

# Evaluation of bids

Please refer to the RFP letter invitation.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.

DRC’s 2030 Localisation Vision reads as follows: “By 2030, DRC’s main modality of implementation is one where DRC systematically supports, facilitates and strengthens local actors and systems in their lead role in crisis response and in the advancement of durable solutions for people affected by conflict and displacement. DRC is able to implement directly when relevant analysis shows that it is necessary and adds value in a given context and situation”.