DRC

Terms of Reference (TOR)

for

Pro Bono mapping Consultancy

- Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

DRC is a global Legal Aid actor with an operational presence in more than 40 countries. Throughout our global presence we work with partners, including civil society, private sector and states and authorities. By 2025, DRC aims to expand our Legal Aid activities, reaching more than 600.000 people with legal aid services.

- Purpose of the consultancy

Danish Refugee Council´s Asylum & Refugee Rights Division and the Global Protection Unit - under the Department of Strategy, Programme & Learning - based in Copenhagen, HQ seeks proposals from a consultant to conduct a mapping of pro bono needs and opportunities within the Danish Refugee Council (the "Project") and to produce a report detailing the findings from the mapping. The Project shall have the aim of expanding access to Legal Aid for conflict- and displacement-affected people.

- Background

The need for legal aid interventions in conflict and displacement contexts is significant – both in the immediate emergency and displacement situation, while people are on the move, in protracted displacement situations and as an important component in supporting and facilitating displacement solutions programming and response. DRC has worked with legal aid for many years in its international operations around the world as well as in Denmark through its Asylum Division.

DRC sees a great need to engage with private sector actors to expand access to legal aid for conflict- and displacement-affected people. However, in DRC’s experience pro bono support requests require an organisational capacity and resources to facilitate both the mapping of needs, coordination, and follow-up for support to be successful. DRC has very limited financing at global level to facilitate the coordination and planning of pro bono assistance between law firms and field colleagues, as the majority of funding goes directly to country operations. Country operations provide direct legal aid services to conflict- and displacement-affected people and legal aid environment building with authorities and other legal aid actors; however, they do not have the capacity, resources, or structure for coordinating pro bono requests.

Furthermore, DRC also sees an opportunity for a stronger focus on how pro bono support can be most appropriately used in humanitarian settings and how the private sector, including law firms, can engage in addressing the very large an unmet legal aid needs that exist through the support of existing humanitarian coordination structures.

- Objective of the consultancy

The objective of this consultancy is to in accordance with instructions from the DRC, and with advisory support of a Secondee, an experienced pro-bono lawyer, provided by the international law firm Herbert Smith Freehills LLP ("Herbert Smith Freehills") be responsible for conducting a mapping of pro bono needs and opportunities within the Danish Refugee Council and to produce a report detailing the findings from the mapping together with a short presentation of the cross-cutting findings.

- Scope of work and Methodology

The consultant will lead the project and be required to prepare a detailed methodology and work plan indicating how the objectives of the project will be achieved, and the support required from DRC.

In carrying out the Project, the Consultant, with the advisory support of the Secondee, will:

- Focus on DRC's legal aid programming in South Sudan, Poland, Colombia and Iraq (with the possibility of adding Yemen and Lebanon, if time allows).

- Attend guidance calls with a Danish Refugee Council supervisor, during which the supervisor will give a thorough introduction to DRC’s legal aid programming and the questions that the mapping will seek to clarify.

- Review DRC legal aid documents, including DRC’s Legal Aid Resource Pack, country legal aid needs assessments and strategic plans etc.

- Interview relevant Danish Refugee Council staff engaged in legal aid, at global, regional and country level, including:

  - DRC Asylum & Refugee Rights Division.

  - DRC Global Protection Unit.

  - DRC Regional Protection Coordinators, Country Protection Managers and Country Legal Aid Specialists/Legal Aid Team leaders and other relevant staff.

  - It may also be relevant to interview external actors, for instance national legal aid partners, UNHCR and/or authorities.

- Prepare and facilitate one joint one-day meeting/workshop together with the Secondee, the supervisor and relevant field staff in one of the focus countries.

- Identify needs and opportunities for pro bono assistance and prepare a written analysis in the following areas for each country/region in focus:

- Asylum & refugee law, civil documentation, and housing, land and property, including alternative dispute resolution methods.

- Legal analysis in a given country affected by crisis.

- Provision of legal aid services to conflict- and displacement-affected people (including training of Danish Refugee Council staff, drafting relevant information material etc).

- Legal aid environment-building activities (advocacy, law and policy engagement, training and capacity-building, strategic litigation as well as other engagement with human rights mechanisms); and

- Other legal aid intervention areas of relevance to DRC legal aid programming.

- Produce a presentation of the cross-cutting findings based on the country mapping, including reflections on how DRC can optimize pro bono partnerships in legal aid programming.

- Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Suggested timeframe |
| --- | --- | --- | --- |
| Phase 1 Review | Preparation | In cooperation with secondee: - Review relevant legal aid documents, - Attend guidance calls with DRC supervisor, - Identify and contact sources | 3 working days |
| Phase 2 (Deliverables in any given order) | Work-shop and inception report | - Prepare and facilitate one-day meeting with the Secondee, the supervisor and relevant field staff to prepare an inception report. - The inception report will include a detailed work plan, a list of interview questions and the outline of the final report structure. | 3-4 working days |
| Phase 2 Data collection and Analysis | Data collection and Analysis | In cooperation with secondee: - Desk-review. - Interviews and other data collection. | 10 working days |
| Phase 3 Reporting | Final report and presentation of findings | - Prepare first draft report. - Feedback from DRC to submit the final report. - Submission of final report. - Short Power point presentation of findings in a webinar. | 7-8 working days |

- Duration, timeline, and payment

The consultant shall be prepared to complete the assignment no later than 1 December 2023.

The expected number of working days is an estimated 25 days; however, the consultant is welcome to propose otherwise in accordance with the task. The expected completion of the consultancy is 1 December 2023

A final draft of the final report for internal review by the Legal Aid Project Group is expected by 16 November 2023. and the final product to be presented at a webinar at the latest 1 December 2023.

| Deliverables | Due Date | Approved by | Payment |
| --- | --- | --- | --- |
| - Inception report and workshop | 15 Sept. 2023 | DRC | 30% |
| - Final report and Power Point presenting findings and recommendations in webinar | 1 Dec. 2023 | DRC | 70% |

- Eligibility, qualification, and experience required.

The consultant is expected to have:

- Master’s degree or equivalent in social sciences, development studies, or another related subject.

- The consultant is expected to have at least 10–15 years of relevant experience, and proven expertise in displacement contexts, including with legal aid programming for conflict and displacement affected people.

- Have an established track record of successfully conducting similar exercises.

- Deep knowledge of and practical experience in qualitative analysis, especially in the Protection sector.

- Strong analytical skills

- Language skills:

  - Written and spoken fluency in English.

  - Working knowledge of Spanish and Arabic an advantage

- Technical supervision

The selected consultant will work under the supervision of Senior Legal advisor, Mary Lisa Jayaseelan, mary.lisa@drc.ngo

- Location and support

This is a home-based consultancy.

- Travel

No travel is expected for this consultancy, except possibly for the workshop.

- Submission process

Please refer to the RFP letter invitation.

- Evaluation of bids

Please refer to the RFP letter invitation.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.