DRC

Terms of Reference (TOR)

for

Consultancy for undertaking a Real-time-review of the Somali diaspora response to localized crises affecting hard-to-reach populations in Somalia

# Who is the Danish Refugee Council and DEMAC?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

DEMAC, the Diaspora Emergency Action & Coordination network, is an initiative hosted by the Diaspora Programme. DEMAC aims at enhancing diaspora emergency response capacity and coordination local actors with the institutional humanitarian system. The objective is to contribute to transforming the humanitarian landscape by laying the ground for a deeper understanding of diasporas as humanitarian actors with different modus operandi for the implementation of aid, identifying and opening potential spaces for engagement, cross-fertilization and increased coordination between diaspora and institutional relief providers.

DEMAC will use information gained from this research to raise awareness and explore avenues for collaboration between diaspora actors, institutional humanitarian actors, and local actors to address the impact of climate induced emergencies in Somalia. DEMAC’s website, and social media channels, as well as online and in person events and workshops will be the main avenues for dissemination.

To read more, please visit www.demac.org.

# Purpose of the consultancy

The purpose of the consultancy is to conduct a real-time review and mapping of the Somalia diaspora humanitarian response to crises in hard-to-reach areas of Somalia. The real-time-review (RTR) research format aims to provide a rapid overview of diasporas` responses to crisis and present the findings together with recommendations in a report and snapshot format, as carried out for flooding and landslides in Timor Leste (April 2021), the COVID-19 surge in Tunisia (July 2021), Myanmar (February 2021), the Taliban take-over in Afghanistan (Oct 2021, August 2022), and Ukraine (Feb-April 2022).  The RTRs focus on providing an immediate and top-line overview of the “Who is doing what, where, when, and for whom” of diaspora response and follow a common structure and methodology.

This consultancy will capture the impact, outreach, and organization of Somali diaspora emergency responses in hard-to-reach areas of Somalia during the period of May to July, 2023. Throughout decades of protracted crises and shocks, the global Somali diaspora have been consistent and agile emergency responders, which has been documented through research conducted by DEMAC and other actors (Diaspora Humanitarian Response and Engagement / Creating Opportunities to Work with Diasporas in Humanitarian Settings). Given the Somali diaspora’s significant engagement in humanitarian response and the substantial barriers to access in reaching both geographic areas and specific demographic groups in Somalia, the RTR will document the Somali diaspora’s response to one to three local crises in hard-to-reach areas of Somalia. The specific crises to be documented will be identified in collaboration with DEMAC and the consultant during the inception phase of the RTR.

The research will be used to enhance the knowledge and awareness within the humanitarian community about the significance and role played by Somali diaspora in responding to crises in hard-to-reach areas of Somalia.

The consultancy is expected to result in a synthetic real-time review report and a snapshot, analyzing findings and learnings from the Somali diaspora-led emergency response in hard-to-reach areas between May and July 2023, including recommendations on future programmatic approaches as to how to engage with diaspora during emergency response.

# Background

Somalia has suffered from re-occurring shocks and crises for the past decades. One of the main types of crises affecting that have and are expected to continue affecting Somalia are climate induced shocks such as drought, flooding, and locusts. During 2022, Somalia experienced its worst drought in over 40 years. The combined effects of drought and other drivers of insecurity such as conflict and inflation mean that over 8.3 million Somalis are likely to be acutely food insecure from April to June 2023. The drought is expected to continue into 2023 with particularly strong impacts in the regions of Banadir and Bay. While the consequences and threat of drought and famine remain prevalent, the Gu rainy season is currently ongoing and several areas of the country have been and continue to be affected by flash floods within the last weeks, leading to displacement, increases in waterborne disease, and disruptions to supply chains for the provision of basic commodities. Particularly affected areas include those near the Juba and Shabelle rivers, Bay and Banadir, and localized areas in Galmudug, Puntland, and Somaliland.  In addition to climate-induced shocks outbreaks of local and area-level conflicts are a re-occurring type of crisis in Somalia. Since August 2022, the Somali governments counterinsurgency against Al-Shabaab in Galmudug, Hiraan, and Middle Shabelle have led to a steep increases in the number of conflict related civilian casualties in Somalia. Despite recent gains in territory by the Somali security forces and allies, the situation continues to be dynamic with Al-Shabaab regaining control in some areas, inter- or intraclan-based conflict related to control of resources, and conflict-induced displacement. Current projections estimated that up to 450,000 people will be displaced as a result of conflict during 2023.

Humanitarian access in Somalia has long been challenging for humanitarian actors due to conflict and insecurity in areas where non-state armed groups control territory (NSAG), exclusion and marginalization of certain clans and demographic groups, and other security and bureaucratic impediments. While humanitarian actors, both local and international, strive for ways to access these populations, meeting the humanitarian needs of people in hard-to-reach locations or demographic groups continues to be a challenge. Conversely, these groups are often disproportionately affected by crises and have vast humanitarian needs. Populations in Somalia that are considered hard to reach based on their geographic locations primarily include those in areas fully or partially controlled by Al-Shabaab for example Middle and Lower Juba, Middle and Lower Shabelle, Hiraan, and Bay. In addition to people in hard-to-reach geographic areas, people from marginalized groups are also considered as hard-to-reach populations. Groups that can be considered marginalized can differ based on local political dynamics and structures but often include minority clan members that lack representation and are underserved in local and area-based decision-making structures.

Throughout the past decades of shocks and crises, the Somali diaspora have been key actors in responding to emergency and long-term needs in Somalia, often scaling up their support significantly during times of crisis. Previous research by DEMAC and other actors have documented diasporas’ engagement in emergency responses such as to the drought in 2016 as well as general trends for diaspora humanitarian responses including modalities, strengths, and gaps. Based on past research and engagement with the Somali diaspora by DEMAC and other actors, it is expected that the Somali diaspora engages in humanitarian response that reaches some hard-to-reach populations of Somalia. However, the modalities for these responses, which hard-to-reach populations they do or do not reach and to what extent, challenges, and gaps in their response are not well documented. Therefore, DEMAC is recruiting a research consultant to conduct a RTR of the Somali diaspora response to local crises affecting hard-to-reach populations in Somalia. The specific crises to be focused on through the RTR will be selected with the consultant during the inception phase of the research but could for example focus on local responses to flooding, drought, or displacement due to conflict and should include at least one climate-induced crisis.

# Objective of the consultancy

The purpose of the consultancy is to conduct a real-time review of the Somali diaspora response to crises in hard-to-reach areas in Somalia. The real-time review will be used to support the operational work of DEMAC, diaspora, local, and institutional humanitarian actors and the final product should therefore be practitioner-oriented and easily digestible piece.

The first two weeks of the consultancy will be done remotely by monitoring crowd funding platforms, social media, and direct contacts with identified diaspora organisations/networks to establish a snapshot of the initial diaspora engagement in terms of Who is currently engaged, What they are doing, Where they are engaged, When, and for Whom. During this stage the consultant will also work closely with DEMAC to narrow down and define the ongoing crises in hard-to-reach areas that will be the primary focus of the RTR.

After the first two weeks, the Consultant will shift to Somalia and from there further document the Who, What, Where, When, and for Whom, gathering information from local partners, beneficiaries, other stakeholders and to the extent possible from Money Transfer Organizations. A main focus will be to assess the extent and significance of the diaspora engagement as well as identification of the main gaps and needs in the diaspora response for hard-to-reach populations.

The Consultant shall ensure relevant presence in Somalia during the RTR, and in cases where the security situation allows, the affected areas. It is DEMAC’s experience from similar previous research, that the information solicited is often perceived to be sensitive as it relates to transfer of private funds, political dynamics, ethnic and religious networks etc. It is thus essential that the Consultant have local partners that have or can develop a strong level of trust with key informants while maintaining a necessary degree of objectivity. The Consultant must also have the ability to ensure protection and safe management of data collected.

The research shall be completed in consultation with the DEMAC team. It is anticipated that the consultant team will be in regular contact, on a weekly basis, with DEMAC contact point. It is also anticipated that the consultant team will confirm the list of key informant interviews (KII)s, including geographic locations, with the contact point. The contact point will take responsibility for ensuring timely responses to drafts and inputs to the consultant team. The research activities are expected to be conducted ideally within June 1st – July 31st, 2023. The information needed from the consultants includes:

- Brief summary of the context and situation with a focus on hard-to-reach populations in Somalia

- Number and locations of diaspora responses mapped

- Profile and structure of diaspora supporting the response, how they are organized, and if/how they differ from and/or identify as local actors

- Areas of intervention of diaspora responses mapped (sectors), including identification of areas and populations for which no or few interventions are identified

- Types, modalities, and sectors of diaspora responses

- Modalities for managing access and response constraints for i.e. fund transfer and monitoring of interventions

- Types of partnerships diaspora are engaged in, especially with local actors and communities

- Diaspora coordination with other diaspora, local actors and institutional humanitarian actors, including diaspora engagement in the cluster system, and strengths and challenges in coordination

- Approximative amount of total funding collected by diaspora and mapped for hard-to-reach areas

- Approximative number of Diaspora Organizations globally

- Size of the diaspora globally

- Strengths and potentials of the Somali diaspora response to respond to humanitarian needs of hard-to-reach (both geographic and demographic) populations

- Gaps and challenges of the Somali diaspora response to humanitarian needs of hard-to-reach (both geographic and demographic) populations

- 2-5 examples of diaspora`s responses for 1-3 hard-to-reach populations affected by crises, including focus on one climate-related crisis

- Diaspora perceptions and relation to humanitarian principles

- Relevant recommendations for supporting and improving the Somali diaspora-led response for hard-to-reach populations

It is necessary to have a consultant in the team that speaks and reads Somali for this research.

# Scope of work and Methodology

For the real-time review the Consultant will conduct:

- Quick Document review of existing of relevant documents, reports, analysis, crowdfunding and social media platforms and other available resources.

- Preliminary mapping of the humanitarian responses of the Somali diaspora for hard-to-reach populations (geographic and demographic). This preliminary mapping will be used to inform the selection of crises which will serve as cases for the RTR.

- Mapping of the humanitarian responses of the Somali diaspora in the crises selected for the RTR. This mapping will also provide the data for some basic quantitative data on the responses. (Social media monitoring, direct contacts)

- Adapt the DEMAC standard real-time-review methodology and prepare a workplan indicating how the objectives of the research will be achieved, and the support required from DEMAC.

- Semi-structured interviews with 20-25 representatives of diaspora across diverse countries of residence, local Somali actors, recipients of diaspora support in hard-to-reach areas, and relevant stakeholders

- Analysis of the data monitored and collected in a comprehensive report including key findings and recommendations.

Desk research and social media monitoring

Building on desk reviews conducted through previous DEMAC research in Somalia, the Consultant will carry out a rapid desk review of already existing information about diaspora humanitarian engagement in Somalia, with a focus on hard-to-reach areas. The desk research will also include a mapping of active diaspora groups engaged in humanitarian response in hard-to-reach areas. Desk research also focuses on social media monitoring and includes direct contact with identified diaspora organizations & networks to create a snapshot of the initial diaspora engagement.

Data collection

The Consultant will lead the adaptation of the already existing methodology from previous RTRs for qualitative and quantitative data collection and (as-needed) revise pre-existing tools to conduct key informant interviews with diaspora for the real-time review. The interviews shall, as a minimum, include the following themes: role(s), implementation of activities (modality, area, and sector), coordination, information sharing, impact, and outreach.

The Consultant will be responsible for the planning and implementation of the field data collection and analysis. This will include identifying and training of field consultants/researchers and data collectors when necessary/relevant. It is expected that field consultants/researchers/data collectors will have the needed language, technical skills, and access to the geographical areas. The Consultant is responsible for identifying, supervising, and coordinating in-country field consultants and informants and ensuring the quality of the data collected.

In drafting the report, the Consultant will adhere to the DEMAC editorial guidelines for written products and presentations, which will be provided as part of the contract.

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Expected deliverables | Indicative description tasks | Due date | Associated payment |
| --- | --- | --- | --- |
| Inception report | Inception report based on the two first weeks of desk review and social media monitoring. | 15 days after the start of the consultancy | 20% |
| Visual ‘Snapshot page’ | Data summarizing the main findings of the inception report, to be used by DEMAC for a 1 page visual highlight | 15 days after the start of the consultancy |  |
| Full internal Real-time review report | Max 20 pages excluding visualizations and annexes. The real-time review will be drafted based on the finding of data analysis and will contain: - An overview of findings from the data collected, - Highlights from the datasets, - Three to four in-depth analyses on relevant topics agreed with the DEMAC team, - A concluding section with an overview of hindrances and opportunities for diaspora engagement and recommendations for diaspora and their partners. | 30 days after the delivery of the inception report | 30% |
| Mapping of Syrian diaspora actors | Mapping in form of a table and part as an annex of the internal RTR report. | 30 days after the delivery of the inception report |  |
| Executive brief | 1-2 pager summary on main findings and key highlights for external audience. | 5 days after approval of internal report |  |
| Brief publishable report | Final publishable report of max 10 pages with key findings and recommendations. | 5 days after approval of internal report | 50% |
| Presentation and briefing | This will be made for DEMAC and any other relevant stakeholders. | 10 days after approval of internal report |  |

Payment will be provided upon completion of the deliverables according to the associated payment scheduling as seen above.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 60 days (45 working days). This can be subject to discussion and negotiation.

The consultant shall be prepared to complete the assignment no later than 31 July, 2023.

# Proposed Composition of Team

The consultant can be either an independent or a firm, the composition of the team proposed should be reasonable against the expected deliverables.

# Eligibility, qualification, and experience required

## Essential:

- Technical knowledge on Diaspora and Humanitarian response with a good understanding of the context of the Somalia and the humanitarian aid system in Somalia

- Demonstrated experience of conducting research in sensitive context

- Research background in diaspora/community engagement/humanitarian response/emergency

- Significant experience in qualitative and quantitative research methods

- Proven experience of leading a research project across several geographies

- Track record of written publications on diaspora or humanitarian response

## Desirable:

- Eligibility:

  - The consultant has the authorisation or is eligible to work in Somalia

- Qualification

  - Relevant academic background (Masters level)

- Experience:

  - A minimum of 5-7 years of proven experience in qualitative and quantitative research methods

- Skills and knowledge:

  - Excellent analytical, interpersonal, communication and reporting skills.

  - Strong methodological and analytical skills

- Language requirements:

  - Strong communication skills (oral and written) Somali and English with the ability to conduct interviews and review research in both languages.

# Technical supervision

The consultant will collaborate closely with the DEMAC Project Coordinators – Sofia Jarvis (sofia.jarvis@drc.ngo) and Béatrice Mauconduit (beatrice.mauconduit@drc.ngo).

It is anticipated that the consultant will be in regular contact, on a weekly basis, with the contact point. It is also anticipated that the consultant will confirm the list of KIIs, including geographic locations, with the contact point. The contact point will take responsibility for ensuring timely responses to drafts and inputs to the consultant.

# Location and support

The consultant will be home based, with a preference for being located in Somalia or the region. The Consultant will provide her/his own computer and mobile telephone.

# Travel

If the performance of the research and data collection requires to travel to field missions, the Consultant is expected to arrange transportation, accommodation, insurance, food and to make adequate provision in the Financial Proposal.

# Submission process

Refer to the RFP Invitation Letter

# Evaluation of bids

Please refer to the RFP letter invitation.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.

OCHA (February 2023), Somalia Humanitarian Needs Overview, 2023, https://reliefweb.int/report/somalia/somalia-humanitarian-needs-overview-2023-february-2023?gclid=Cj0KCQjwxYOiBhC9ARIsANiEIfZbRUwIprYmuzyjMorPy7JAArErw4wi54QHzA6v1nXPesKfy6-g4aMaAiyVEALw_wcB

Ibid.

ACAPS (April, 2023), Somalia: Key crises to watch in 2023, https://reliefweb.int/report/somalia/somalia-humanitarian-needs-overview-2023-february-2023?gclid=Cj0KCQjwxYOiBhC9ARIsANiEIfZbRUwIprYmuzyjMorPy7JAArErw4wi54QHzA6v1nXPesKfy6-g4aMaAiyVEALw_wcB

OCHA (April 2023), Somalia: Gu rainy season 2023, Flash Floods Update No. 3, https://reliefweb.int/report/somalia/somalia-gu-rainy-season-2023-flash-floods-update-no-3-13-april-2023

OCHA (February 2023), Somalia Humanitarian Needs Overview, 2023, https://reliefweb.int/report/somalia/somalia-humanitarian-needs-overview-2023-february-2023?gclid=Cj0KCQjwxYOiBhC9ARIsANiEIfZbRUwIprYmuzyjMorPy7JAArErw4wi54QHzA6v1nXPesKfy6-g4aMaAiyVEALw_wcB

ACAPS (April, 2023), Somalia: Key crises to watch in 2023, https://reliefweb.int/report/somalia/somalia-humanitarian-needs-overview-2023-february-2023?gclid=Cj0KCQjwxYOiBhC9ARIsANiEIfZbRUwIprYmuzyjMorPy7JAArErw4wi54QHzA6v1nXPesKfy6-g4aMaAiyVEALw_wcB

OCHA (February 2023), Somalia Humanitarian Needs Overview, 2023, https://reliefweb.int/report/somalia/somalia-humanitarian-needs-overview-2023-february-2023?gclid=Cj0KCQjwxYOiBhC9ARIsANiEIfZbRUwIprYmuzyjMorPy7JAArErw4wi54QHzA6v1nXPesKfy6-g4aMaAiyVEALw_wcB

DEMAC (2016), Diaspora drought response, Somaliland and Puntland, https://media.umbraco.io/demac/ae3il2jr/demac-diaspora-drought-response-2016-somaliland-and-puntland-report.pdf

DEMAC (2021), Diaspora organizations and their humanitarian response in Somalia, https://demac.euwest01.umbraco.io/media/arlhnwpl/demac-report-somalia-final-rz-digital.pdf

Pre-existing templates used by DEMAC for other Real-time-reviews are available for adaptation.