DRC

Terms of Reference (TOR)

for

Toolbox to measure the outcome and impact of anticipatory action

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and  supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The Danish Refugee Council HQ seeks proposals from a consultant to develop a toolbox to enable documentation of the outcomes, impact and value for money of DRC’s anticipatory action responses. The toolbox should provide an overview of the relevant indicators/metrices to measure the approach against, specific data collection tools to gather the relevant data, as well as analysis guidance for turning collected data into evidence.

# Background

Anticipatory action is a growing field in the humanitarian sector. Much work has been already in relations to anticipatory action in response to climate shocks such as typhoons, floods and droughts. There is a growing body of evidence from these interventions that anticipatory action can be both a more dignified and cost- efficient way of doing humanitarian action.

DRC has taken the first nascent steps into anticipatory action through two pilot project. The pilots focus on drought- and conflict-induced displacement.

# Objective of the consultancy

The purpose of this consultancy is to develop a practical toolbox that will specifically include the following:

- Detailed methodology for collecting evidence on outcomes, impact and value for money

- Indicator framework

- Data collection tools (e.g. baseline, mid-line, end-line assessment tools)

- Analysis guidance for turning collected data into evidence

# Scope of work and Methodology

The Consultant will be required to prepare a detailed methodology and work plan indicating how

the objectives of the project will be achieved, and the support required from DRC.

Specifically, the consultant is expected to perform the following tasks:

- Review relevant documentation from DRC and relevant external resources

- Develop an initial set of tools to be presented for a select group of DRC stakeholders

- Support field testing of these tools in Burkina Faso and South Sudan

- Adjust and finalize tools based on field testing

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 Review | Inception report | Kick-off meeting Documentation sourcing and review | 5 working days |
| Phase 2 Development and testing | Draft toolbox | Toolbox development Working meetings, discussions, Field testing in South Sudan and Burkina Faso | 15 working days |
| Phase 3 Finalization | Final report | Prepare and submit draft, final version of toolbox Feedback from DRC to submit the final version | 10 working days |

The Consultant will provide the documentation by email.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 30 days

The consultant shall be prepared to complete the assignment no later than 31 December 2023.

Payments will be made according to the following schedule:

- Approved inception report: 40%

- Approved draft toolbox: 30%

- Approval of all final deliverables: 30 %

# Eligibility, qualification, and experience required

## Essential:

  - At least 7 years of experience with Monitoring, Evaluation and Learning

  - Experience with developing MEL systems, approaches/guidance

## Desirable:

  - Experience with anticipatory action

  - Field-level experience

  - Experience from similar consultancy assignments

- Experience:

  - A minimum of five years of proven experience in humanitarian sector.

- Skills and knowledge:

  - In-depth understanding outcome and impact monitoring and measurement

  - Understanding of the concept of value for money

  - Excellent writing skills

- Language requirements:

  - Written and spoken fluency in English

  - Working knowledge of French is an advantage

# Technical supervision

The selected consultant will work under the supervision of:

- Alexander Kjaerum, Senior Analyst, Evidence, Knowledge and Learning Division

# Location and support

Home-based

# Travel Not Applicable

# Submission process

- Refer to the RFP document name of the document.

# Evaluation of bids

- Please refer to the RFP letter invitation.