DRC

Terms of Reference (TOR)

for

Training Associate for the ASPIRE project

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and  supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The overall purpose of this consultancy is creating and facilitating two trainings:

- An introductory/basic training for field researchers in Kenya

- A refresher ethnographic training for field researchers in Uganda, building on previous trainings performed in September and November 2023.

This will be done by 1) implementing an introductory training for 3 field researchers in Kakuma Refugee Camp in Kenya (using existing training materials) and 2) Designing a programme for a refresher ethnographic, tailored to the needs of the field researcher team and building on existing exercise manual (6-8 South Sudanese refugees from Rhino Camp Refugee Settlement in Uganda).

In addition, 1 report will be prepared following each of the trainings (2 in total). The report will (1) evaluate the training process in and provide recommendations on the further implementation of the training of the field researchers. Moreover, (2) the report will detail recommendations on how to adapt the training to the context of South Sudan, where the training will be implemented in 2025.

# Background

ASPIRE is a unique and progressive research project developed in as a partnership between DRC and  UNHCR. It follows a generation of young refugees in five different countries over a period of 15 years, exploring how they perceive and pursue opportunities for peace in their communities from their point of view. The overall objective of ASPIRE is to provide in-depth new knowledge about how young people, affected by the civil war(s) in South Sudan, over time, contribute to peaceful coexistence in their communities. Simultaneously, the research investigates how interventions by humanitarian actors are used by - and influence - the young people in their trajectories and practices. The research will be implemented alongside UNHCR’s Regional Youth Peacebuilding Project (RYPP), in five of the locations where it is currently active: Rhino Camp Refugee Settlement (Uganda), Kakuma Refugee Camp (Kenya), and among South Sudanese refugees Ethiopia, Sudan and returnees in South Sudan. This will allow the research to capture the effects of this important work as it takes place.

# Objective of the consultancy

The objective of this consultancy is to prepare, design and facilitate trainings for field-based researchers in Kenya and Uganda. The Kenyan staff are new to their job and need more basic training and the Uganda staff need a refresher. By the end of these trainings, the field researchers should be familiar with intermediate level concepts of ethnography and ethnographic methodology including participant observation, writing, managing and sharing ethnographic field notes and bi-weekly reporting, open-ended interview techniques and reflecting on the ethnographic data, with a focus on long term cases.

The consultant will be required to develop a training programme in coordination with the PM. The consultant is not required to come up with exercises from scratch, we have a newly developed catalogue of exercises and focus areas that the programmes should be based on. The Kenya staff will receive more basic training and the Uganda staff will need to re-visit components and learning from 2023 and finetune their work and skills.

The consultant will be required to co-facilitate the training with the PM on specific dates in early May and early September.

The consultant will be required to develop a report based on learning from the training with recommendations for follow-up trainings and how to adapt the package to future trainings in and beyond Kenya and Uganda.

# Scope of work and Methodology

The Consultant will be required to prepare a detailed methodology and work plan indicating how

the objectives of the project will be achieved, and the support required from DRC.

# Deliverables

The Consultant will submit a field report based on the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Training 1: Deliver basic ethnographic training for new team in Kakuma Refugee Camp Settlement (early May) |  |  |  |
| Training preparation | Training programme: based on exercise manual | Pre-meeting with PM about the programme. Deliver draft version of programme for feedback 3 weeks prior to the training. | 3 working day |
| Facilitation | Facilitation workplan | Co-facilitation of the training with the PM (likely 1st-6th May 2024) | 6 working days |
| Reporting | Final report | Report on training including reflections on training for implementation of further training | 1 working days |
| Training 2: Deliver Refresher training in Rhino Camp Refugee Settlement (early September) |  |  |  |
| Training Development | Training programme: based on exercise manual | Pre-meeting with PM about the programme. Deliver draft version of programme for feedback 3 weeks prior to the training. | 2 working days |
| Facilitation | Facilitation Workplan | Co-facilitation of the training with the PM (likely first week of September) | 7 working days |
| Reporting | Final Report | Report on training including reflections on training for implementation of further training | 1 working days |

The Consultant will provide the documentation by email / Word, Excel, PowerPoint, PDF, etc.<

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 20 working days which will be broken into 2 trainings.

Training 1: 10 working days for basic training

Training 2: 10 working days for refresher training

The consultant shall be prepared to complete the full assignment no later than 15th October 2024.

# Proposed Composition of Team

- Training Consultant

# Eligibility, qualification, and experience required

## Essential:

- Expertise in qualitative research methodology/ethnographic methodology

- Experience in conducting research with/via local research assistants

- Experience with education design and implementation

- Experience working in refugee settings (preferably East Africa)

Eligibility:

  - The consultant has the authorisation to work in Uganda and Kenya

Qualification:

  - Educational level: Master or PhD

Experience:

  - A minimum of 5 years of conducting qualitative research proven. Teaching and facilitating ethnographic methodology.

Skills and knowledge:

- Qualitative research methodology/ethnographic methodology

  - (candidates selected for interviews will be invited to share example)

  - A solid understanding of the South Sudan context

Language requirements:

  - Written and spoken fluency in English

# Technical supervision

The selected consultant will work under the supervision of:

- Programme Manager, Ayo Degett, ayo.degett@drc.ngo

# Location and support

Rhino Camp Refugee Settlement

Kakuma Camp Refugee Settlement

The Consultant will provide her/his own computer and mobile telephone.

# Travel

The consultant is expected to conduct 13 working days in the field.

The Consultant will therefore be expected to arrange transportation, accommodation, food and to make adequate provision in the Financial Proposal.

# Submission process

Please refer to the RFP invitation letter.

# Evaluation of bids

Please refer to the RFP invitation letter.