DRC

Terms of Reference (TOR)

for

Cash and Markets Enhanced Preparedness and Response Capacity – Phase II

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The Headquarters of the Danish Refugee Council seeks proposals from to support a Global Consultancy to improve our Cash and Markets Preparedness and Response Capacity processes and tools across DRC’s Response Framework (Phase II).

# Background

DRC promotes Cash and Voucher Assistance (CVA) when appropriate and feasible as an optimal assistance modality – to maximise recipients’ dignity, flexibility, and choice to meet self-prioritised needs. CVA is a tool we leverage to address both immediate basic needs but also durable solution outcomes. DRC implements multipurpose cash assistance as well as sectoral cash assistance across it five core sectors, i.e. Protection, Economic Recovery, Humanitarian Disarmament and Peacebuilding, Shelter & Settlement and Camp Coordination and Camp Management (CCCM).

In early 2023, DRC conducted an internal review of its Emergency Response capacity. The review identified a need for enhanced preparedness and response capacity in order for DRC to be better equipped to address the complexity of the shocks people of concern face.

In late 2023 / early 2024, DRC conducted a first review of its CVA preparedness and response capacity. The review concluded that DRC’s decentralised structure results in a lack of standardised approaches and tools, limited cross-country exchanges and unnecessarily high level of effort to ‘reinvent the wheel’ for each context and specific response. This approach, while ensuring relevance and appropriate contextualisation, comes with risk especially with regards to timeliness and quality of response in case of human resources gaps.

This consultancy will build on this first analysis and seek to address the shortcomings of decentralisation, via the development of global framework and tools that can easily be contextualised.

# Objective of the consultancy

This Consultancy will seek to enhance DRC Cash and Voucher Assistance (CVA) Toolbox (processes and tools) at global level for improved preparedness, emergency response and early recovery.

# Scope of work and Methodology

The Consultancy will be divided into 3 main activities:

Activity 1 – Development of a Global CVA Toolbox

The Consultant will propose an outline and estimated Level of Effort to develop a comprehensive Global CVA Toolbox for MPCA, Sectoral CVA, Small Business Grants and Preparedness.

Using the CALP Program Quality Toolbox as a baseline, the Consultant will develop a Toolbox that is tailored to DRC’s decentralised structure, technical and operational capacities. The Toolbox should be rooted in DRC’s Response Framework, and consider the volatile environments DRC works in. As such, it should consider CVA for anticipatory action, as well as transitioning emergency CVA to durable solutions. It should also consider different ways of operating, including through remote programming, localisation and working through partners, and Rapid Response Mechanism (RRM) through non static presence.

The Toolbox should include (at minimum):

- CVA Preparedness Checklists

- Templates for SOPs, and guidance for contextualization and revision by technical experts (in particular in highly volatile contexts)

- Best practices and lessons learnt, and guidelines to institutionalize exchange of information and lessons learnt at global level

- Financial Services Providers minimum requirements

- Contract templates

To Note: The Consultant will be expected to actively engage with the Emergency Programme working group (comprised of a selection of DRC staff) and needs to build the required time for engagement and alignment in their proposal.

Expected deliverables:

- A DRC-tailored Global CVA Toolbox

- A recorded webinar to introduce the toolbox

Activity 2 – Coding of DRC’s Modality Due Diligence (MDD) tool into an open-source software

After familiarising him/herself with DRC’s existing excel format MDD tool, the Consultant will code the existing tool into Kobo or a similar free and open-source software, with a view to accelerating the uptake of the tool across the organisation. Essentially, you will be transferring the excel into Kobo and quality improving the decision making and modality choice process in parallel.

Note that a coded V1.0 online MDD prototype already exists in Kobo for the Consultant to iterate upon significantly reducing any need for generating coding from scratch.

The result will be a V2.0 online MDD tool that will provide modality recommendation options between direct assistance versus different types of CVA with identified design parameters (e.g. conditionalities, digital vs vouchers, MEB etc).

The Consultant will propose a methodology to collect internal feedback on the usability and functionality of the tool.

The Consultant is expected to focus on the user experience in terms of the design of the tool (content, language, look, integration/reference to related materials) to make sure it meets the needs of field teams.

The Consultant will be expected to explain how best to capture, store and manage the wealth of raw data captured from each online submissions into something useful for DRC. It is expected that the Consultant will also provide examples of back-office analytics of the online tool can be gathered, cleansed and used to provide strategic, operational and programme quality information for HQ and Regional teams. It is expected that the Consultant will provide recommendations on how DRC can utilise rapid access to emergency response analysis data from country level to improve programme quality processes and support to countries.

To note: DRC has started the development of a MDD+ tool, aimed at guiding and incentivising country operations to identify opportunities / entry-points for market support activities (beyond CVA/MPCA) early on in the response. While this consultancy is not expected to contribute directly to this development initiative, it will be important to coordinate efforts to ensure the future MDD+ tool builds on the existing MDD.

Expected deliverables:

- MDD coded in an open-source software

- User feasibility test methodology and survey for MDD

- Centralised data management and storage plan for MDD submissions, including an analysis dashboard to process and visualise the raw data

- Examples and recommendations of data analytics from tool

- Updated guidance note/video/SOP to administer the MDD

Activity 3 – Ad-hoc CVA expertise

Expected deliverable: no concrete outputs can be defined in advance of the work, but the consultant is expected to dedicate up to 5 days to providing ad-how CVA expertise based on country requests.

The Consultant will work directly with the Head of the Global Economic Recovery Unit and the Global Inclusive Markets Advisor, as well as relevant members of the Economic Recovery Core Group (Global and Regional staff focal point for CVA and MBP competency areas).

# Deliverables

The Consultant(s) will submit the following deliverables as mentioned below.

| Phase | Expected deliverables | Maximum expected timeframe |
| --- | --- | --- |
| Activity 1 | - A DRC-tailored Global CVA Toolbox - A recorded webinar to introduce the toolbox | 30 days |
| Activity 2 | - MDD coded in an open-source software | 5 days |
| Activities 1 and 2 | - Test of the toolbox and MDD tool with a selection of countries | 10 days |
| Activity 3 | - Proof of strategic and technical support provided to regional and country offices (e.g. minutes of meeting, reviewed documents, log of calls, etc.) | 5 days |

# Duration, timeline, and payment

The consultant shall be prepared to complete the assignment, preferably by the 15th May 2024, and as such should be able to start initial work in March 2024.

The expected level of efforts is 50 days, though applicants are welcome to suggest a different LoE to deliver the outputs by the delivery deadline.

All work will be done remotely.

Payment will be in tranches, coinciding with the satisfactory completion of deliverables at different stages of the project:

- Tranche 1 – upon completion of Activity 2 (MDD)

- Tranche 2 – upon completion of all deliverables

# Proposed Composition of Team

The composition of the team will be to the discretion of the Consultant. Individuals are encouraged to apply.

Should the Consultant be sub-contracting work to other Consultants rather than submitting a joint proposal, this must be made clear (including the risks of doing so) within the proposal. Quality assurance mechanisms of deliverables must be explained as part of the proposals.

# Eligibility, qualification, and experience required

## Essential:

- Proven experience in conducting an Organisational Cash and Voucher Assistance Readiness Analysis

- Proven experience in designing and implementing or quality assuring CVA programming

- Confidence in applying generic techniques for market-based programming to any sector with assistance from sector specialists if and when needed (it is likely that this Consultancy will focus on programming related to MPCA, food security, livelihoods, protection, WASH, shelter, and Camp Coordination and Camp Management)

- Proven experience / understanding of at least one method of market analysis in emergency contexts – RAM, EMMA, PCMA

- Experience in pivoting programmes from in-kind/direct humanitarian assistance to forms of market-based programming

- Understanding of the institutional, operational and contextual challenges of utilising CVA/MBP

- Understanding of emergency response programming and humanitarian principles

## Desirable:

- Understanding of Emergency Preparedness and Response Plans (EPRPs) to inform market-based programming integration opportunities within preparedness activities

- Understanding of Sphere / HSP companion guides and application to MBP including MiSMA and MERS

- Qualification:

  - At least Degree in Master’s level in relevant degree (Bachelor’s level will be considered if sufficient work experience to support application)

- Experience:

  - A minimum of 7 years of work in the humanitarian sector with large proportion delivering or improving programme quality through application of market-based programming (including CVA)

- Skills and knowledge:

  - Working with displacement-affected communities in emergency and early recovery response environments in different contexts – urban, remote and camps.

- Language requirements:

  - Written and spoken fluency in English

  - Working knowledge of French is an advantage

# Technical supervision

The selected consultant will work under the supervision of:

- Solenne Delga, Head of Global Economic Recovery Unit

# Location and support

The consultancy can be done remotely, but the consultant is free to propose a workplan and associated budget, which cater for field missions to test the toolbox and the MDD tool.

The Consultant will provide her/his own computer and mobile telephone.

# Travel

See above.

# Submission process

Please refer to the invitation letter.

# Evaluation of bids

For the award of this contract, the evaluation criteria below will govern the selection of offers received. The evaluation is made on a technical and financial basis. The proposed offers by bidders will be evaluated using the following criteria, and points will be allocated on a scale from 1 to 10 for each of the criteria below, according to the following weighting:

| Candidate qualifications Documented by the filled-in Supplier Registration Form, and CV | General liability/capacity of the candidate Previous relevant experience 60% |
| --- | --- |
| Proposed services Documented by the technical proposal | Content of the proposal is suitable for the stated requirements Quality of the proposed research methodology 40% |
| Total | 100% |