## Budget Summary
SUMMARY SHEET
No | Bill No | Estimated Amount
1 | Bill No. 14: Kabo
2 | Bill No. 15: Waranqara
3 | Bill No. 19: Safaricom BH
4 | Bill No. 20: Kamor Liban
Grand Total

## Kabo
BOQ No:14
Project : | BORESHA
County | Mandera
Sub County | Lafey
Location | Kabo
Description | Borehole Solarization, Perimeter Fencing, Construction of 50M3 Mansonry Tank, Repair of 2No. Water Kiosks and 1No Animal Trough.
Item No | Item Description | Unit | Qty | Rate | Amount
A | Borehole Solarization
Element No.1: Supply and deliver to site, install, commission and test the following for pumping 6m3/hr with 7.5 Kw Motor size
1.1 | Dayliff SV3 7.5KW 3PH Sunverter | Set | 1
1.2 | Monocrystalline photo voltaic solar modules 665W, 24Vdc | No. | 17
1.3 | Dayliff 4ST 1000 DC/40A PV Disconnect Switch | No. | 1
1.4 | Earth rod complete with clamp | No. | 1
1.5 | Lightning Arrestor | No. | 1
1.6 | Copper Earth Cable 6mm2 | M | 25
1.7 | 6mm2 4 core underground cable (armoured) | M | 28
1.8 | 1.5mm2- 2 core undergroudn armoured cable(elecrode sensor) | M | 28
1.9 | Twin flat10mm cable with earth (Wiring connection) | M | 35
1.1 | GS sunverter steel fabricates enclosure 1000x500x350mm | No. | 1
1.11 | Design as per radiations day angle, fabrication and installation of solar support structure for the specified solar panels. Rate to include for system testing. Use 75mmx 75mmx3mm SHS vertical support, 50mmx50mmx3mm struts and 50mmx50mmx2mm SHS purlins sections to hold panels tight into position. All joints braced. Height of the structure 4m above ground. The structure design must be preapproved before installation by the clients engineers | LS | 1
1.12 | Installation Sundries (cable ties, insulation tape, spacing tape, spicing joints etc) | Item | 1
1.13 | Solar security light (50W LED light, 120W Solar Module, 150Ah Sealed maintenance free battery, Dawn-to dusk controller, 6m high pole c/w battery box |  | 2
1.14 | Manual change over switch 100 Amp the Solar System with a 30KVA generator |  | 1
Sub Total
Element No.2 : Installation and Transportation
2.1 | Installation labour, testing and transportation to site | LS | 1
Sub Total
Total
B | Perimeter Fencing 30mx30m
Element No.1: Supply of Concrete Poles & Other Material Inputs
1.1 | Supply transport to site and install 100mm x100mm thick concrete poles,3000mm long with 500mm cranked length and 6 provisional holes to accomodate straining/barbed wire spaced @ 2500mmc/c. Rate to include for excavation of pole pits and firming with concrete at the poles base. | Pcs | 50
1.2 | Ditto but 100mmx100mm and 2000mm long precast concrete strut posts of grade C-20 placed at corners and after every 15m spacing. Rate to include for excavation of pole pits and firming with concrete at the poles base. | No. | 16
1.3 | Provide materials, fabricate and install purpose made steel grilled double leaf security gate overall size 4000x2000mm high in two equal opening leaves each size 2000x2000mm high with external frame of 50x50x3mm SHS. Vertical bracing of 50x50x3mm spaced @400mm c/c, horizontal frame of 40x40x3mm spaced @ 300mm c/c all fixed to external frame by wielding including all hinged supported by RC columns complete with locking devices all painted with two coats of approved primer and finished with final coat first grade gloss paint. | Pcs | 1
1.3 | G12.5 chainlink 2m high | SM | 240
1.4 | Barbed wire 16g, 25kg -6 strand | LM | 720
Sub Total
Element No.2: Mass concrete class C20/25 in:
2.1 | To concrete poles | CM | 0.918
2.2 | 300mmx300mm Gate columns | CM | 0.5
2.3 | 150mm wide x 150mm deep Concrete pitching to chainlink base ratio 1:3:6 | CM | 2.7
Sub Total
Element No.3: Conceter Ancillary
3.1 | Formwork to;
3.1.1 | Column edges over 150mm but not exceeding 300 mm girth | SM | 21.12
3.2 | Reinforcment Bars
3.2.1 | Provide, cut and place 10mm square twisted steel rebars in gate columns and 600mmx600mm footing | Kg | 20
3.2.2 | 8mm twisted steel rebars as stirrups in column @150mm | Kg | 14
Sub Total
Element No.4: Finishes
4.1 | 20mm thick plastering with cement: sand (1:4) screed to surfaces with 12mm thick lime steel trowelled smooth finish on columns | SM | 21.12
4.2 | Gloss painting to columns- code provided by Engineer | SM | 6
Sub Total
Total
C | Construction of 50m3 of Masonry Tank
Element No.1: Excavation and Filling
1.1 | Excavate over site and remove top soil to an average depth of 150 mm | SM | 30.2
1.2 | Excavation for foundation in from stripped level but not exceeding 1.5m deep and Cart away | SM | 13.6
1.3 | 300mm thick hand packed (stones) Hardcore well rolled and rammed | M3 | 5.8875
Sub Total
Element No. 2 : Sub and Super Structure Walling
2.1 | Provide and construct a 225mm thick Masonry Walls in 1:3 sand and mortar as foundation walling | SM | 10.99
2.1 | Provide and construct a 225mm thick Masonry Walls in 1:3 water proof cement: sand mortar circular In plan | SM | 47.1
Sub Total
Element No. 3: Concreting
3.1 | 150mm thick reinforced concrete class 20/20 for foundation slab. | M3 | 2.9438
3.2 | 100mm lean concrete (1:4:8) foundation footing blinding | M3 | 1.5331
3.3 | 150mm thick reinforced concrete class 20/20 for on roof slab (Include for shuttering). | M3 | 2.9438
3.4 | 150mm thick reinforced concrete class 20/20 for ring beam | M3 | 0.5508
Sub Total
Element No. 4: Concrete Ancillaries
4.1 | Formwork
Provide cut and fix in position sawn timber (150mmx25mm) formwork or equivalent.
4.1.1 | Tank cover slab | m2 | 19.625
4.1.2 | Sided of the water tank ring beam and floor slab | m2 | 4.71
4.1.3 | 4.5m long support props for supporting the cover slab formwork | Pcs | 20
4.2 | Reinforcement
Steel reinforcement cut, bend & placed in position, unit price to include cutting, bending & placing in position with binding wire and concrete seats
4.2.1 | Supply, cut and fix 12mm diameter high tensile steel (0.89kg/m) including binding wire for floor slab concreting | KG | 592
4.2.2 | Provide and place 10mm diamter high tensile steel (0.67kg/m on the the walls in between courses | KG | 260
4.2.3 | Reinforcement for ring beam with 10mm diamter high tensile steel (0.67kg.m) spaced @200mm/cc | KG | 102.3881
4.2.4 | Reinforcement for top cover slab with 10mm diamter high tensile steel (0.67kg.m) spaced @200mm/cc | KG | 315
Sub Total
Element No. 5 : Finishing Works
5.1 | 30mm thick floor slab plaster mixed with cement: sand mortar(1:3) mortar mixed with water proof cement to appropriate slope as directed by the engineer | SM | 15.8963
5.2 | 20mm thick 1:3 cement /sand mortar plaster mixed with water proof cement to wall in three courses of 5mm,5mm and 10mm to both internal and external surfaces of tank | SM | 94.2
5.3 | 20mm thick cement: sand (1:3) mortar screed on top slab to appropriate slope as directed by the engineer | SM | 19.625
5.4 | Apply 2 coats of first grade superfast emulsion emulsion paint (Dura Coat) to the tank external surfaces exlusive of the cover slab | m2 | 68.35
5.5 | Apply 3 coats of supergloss paint (Dura Coat) to the tank external surfaces exlusive of the cover slab | m2 | 47.1
5.6 | Apply 3 coats of supergloss black paint (Dura Coat) to 300m from the ground for skirting on external surface of the foundation walling | m2 | 4.71
Sub Total
Element No. 6 : Plumbing and Piping Works
6.1 | Excavation
6.1.1 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 50 meters long | m3 | 9
5.2 | Pipe works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
5.2.1 | PN10 75mm HDPE pipes as per the specification above | LM | 550
5.3 | Pipe Fittings
Supply, deliver to site, joint and fix the following fittings
5.3.1 | 75mm HDPE Equal Tee PN 10 | Pcs | 4
5.3.2 | 75mmx75mm HDPE male adaptor | Pcs | 10
5.3.3 | 75mmx63mm HDPE male adaptor | Pcs | 2
5.3.4 | 75mm HDPE Equal Couplings | Pcs | 4
5.3.5 | 2" Peggler gate valve | Pcs | 2
6.2.1 | 2" Dia G.I Pipe Class B | No. | 3
6.2.2 | 2" Dia G.I Class B Elbows | No. | 8
6.2.3 | 2" Dia Backnuts | No. | 4
6.2.5 | 2" Valve Sockets | No. | 4
Sub Total
Element No.7: Other Fixtures
7.1 | Construct 1200 x 1200 x900 Valve Chambers with Lockable Steel cover at Inlet and outlet control gate | No. | 2
7.2 | Provide and fix both internal and external access ladders with 11/4" galvanized pipes | No. | 2
7.3 | Provide and fix tank breather pipes with (600mm long 2" GI pipes, 2 pcs elbows) with wall passess. | No. | 2
7.4 | Construct 800mmx 800mm Lockable Inspection Steel cover on the top slab | No. | 1
Sub Total
Total
D | Repair of 2 No. Water Kiosks
Element No. 1 :Hacking & Finishing
1.1 | Hacking the existing platsered area | Lumpsum | 1
1.2 | 20mm thick internal plaster | SM | 22.05
1.3 | 20mm thick smooth finsh external plaster | SM | 10
1.3 | 25mm thick cement/sand screed and smoooth finsh after hacking | SM | 5
1.4 | Preapare and supply 3 coat gloss oil paint (cream white to wall surfaces externaly | SM | 22.05
1.5 | Preapare and supply 3 coat gloss oil pain on the steel door and column surface | SM | 7
Sub Total
Element No. 2 : Fixtures
2.1 | Door
2.1.1 | Intall and Fix 900x2100mm steel door including locks and hinges to details | No. | 1
Sub Total
Element No. 3 : Shelving
3.1 | Provide and fix 3 rows from one piece of MDF (Medium Density Fibre) shelves 400mm wide and supported with 32mmx32mmx 5mm angle lines welded at an angle of 90º and spaced 800mm apart on the internal walls as shall be directed by supervising Engineer. The cost include MDT edge lining strip and boring of 3 holes for afixing the MDF board with 25mm long self tapping screw. | No | 1
Sub Total
Element No.5: Plumbing and Piping Works
4.1 | Excavation
4.11 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 100 meters long | m3 | 11.7
4.2 | Pipe works
Supply, deliver to site, joint and lay the following PPR pipes joned by PPR fusion machine attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
4.21 | Supply and install 5,000lts Plastic tank (Kentak or Equally Aprroved) | No. | 1
4.22 | 1" PPR pipe | M | 57
5423 | 3/4' PPR outlet pipes | No. | 3
Sub Total
Element No.5 : Pipe Fittings
5.1 | 11/4" x1' PPR reducing socket to tank inlet | No. | 1
5.2 | 1'' PPR sockets | No. | 10
5.3 | 1'' PPR Elbows | No. | 1
5.4 | 1'' gate valves (pegler) | No. | 2
5.5 | 40 mm by 1 male adapters | No. | 4
5.6 | 1' water meters (Kent/Dumwel) | No. | 1
5.7 | 1"x 3/4' PPR reducing socket | No. | 1
5,8 | 1' gate valve (Peggler) | No. | 1
5.9 | PTFE Thread tape | Pactes | 2
5.1 | Repair existing lines with minor leaks | Lumpsum | 1
Sub Total
Total for the Rehabilitation of 1No. Water Kiosk
Total for the Rehabilitation of 2No. Water Kiosk
E | Repair of 1No. Animal Trough Repair
Element No. 1: Hacking and Plastering
1.1 | Allow for hacking all internal and external plaster | SM | 53
1.2 | Inject cement mortar to all hacked deep cracks and fix with chicken wire and plaster (1:3) | SM | 9
1.3 | 20mm thick plaster, cement and sand mortar (1:3) to floor with water proof cement steel trowelled to smooth finish. | SM | 8
1.4 | 20mm thick plaster, cement and sand mortar (1:3) to internal side of walls with water proof steel trowelled to smooth finish. | SM | 10
1.5 | 20mm thick plaster, cement and sand mortar (1:3) to external side of walls with water proof steel trowelled to smooth finish. | SM | 17
1.6 | Hack and provide 100mm thick C20 mass Concrete benching laid to appropriate fall on all directions at animal stepping platform. | SM | 2.3
1.7 | Sub Total
Element 2: Plumbing and Pipeworks
Elment No. 1 : Excavation
1.1 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 200 meters long | m3 | 36
Sub Total
Element No. 2 : Pipe Works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
2.1 | 75mm HDPE pipe 10 bars with to channell water from the Masonry tank to the troughs | LM | 200
Sub Total
ElementNo. 3 : Pipe Fittings
2.1 | 75mm HDPE Equal Couplings | Pcs | 4
2.2 | Supply and install 75mm HDPE male adpaters | Pcs | 8
2.3 | Supply and install 75mm HDPE Tee | Pcs | 4
2,4 | Supply and install 75mmx 63mm reducing adaptor | Pcs | 4
2.5 | Supply, install and test 2'' GI pegler (England) Gater Valves | No. | 3
Sub Total
Total
| SUMMARY |  |  |  | AMOUNT
A | BOREHOLE SOLARIZATION
B | PERIMETER FENCING
C | CONSTRUCTION OF 50M3 MASONRY TANK
D | REPAIR OF WATER KIOSK
E | REPAIR OF ANIMAL TROUGH
GRAND TOTAL

## Waranqara
BOQ No:15
Project : | BORESHA
County | Mandera
Sub County | Lafey
Location | Waranqara
Description | Borehole Solarization, Construction of 50M3 Masonry Tank, Construction of Cattle Trough and Water Kiosk.
Item No | Item Description | Unit | Qty | Rate | Amount
A | Borehole Solarization
Element No.1: Supply and deliver to site, install, commission and test the following for pumping 6m3/hr with 7.5 Kw Motor size
1.1 | Dayliff SV3 7.5KW 3PH Sunverter | Set | 1
1.2 | Monocrystalline photo voltaic solar modules 665W, 24Vdc | No. | 17
1.3 | Dayliff 4ST 1000 DC/40A PV Disconnect Switch | No. | 1
1.4 | Earth rod complete with clamp | No. | 1
1.5 | Lightning Arrestor | No. | 1
1.6 | Copper Earth Cable 6mm2 | M | 25
1.7 | 6mm2 4 core underground cable (armoured) | M | 28
1.8 | 1.5mm2- 2 core undergroudn armoured cable(elecrode sensor) | M | 28
1.9 | Twin flat10mm cable with earth (Wiring connection) | M | 35
1.1 | GS sunverter steel fabricates enclosure 1000x500x350mm | No. | 1
1.11 | Design as per radiations day angle, fabrication and installation of solar support structure for the specified solar panels. Rate to include for system testing. Use 75mmx 75mmx3mm SHS vertical support, 50mmx50mmx3mm struts and 50mmx50mmx2mm SHS purlins sections to hold panels tight into position. All joints braced. Height of the structure 4m above ground. The structure design must be preapproved before installation by the clients engineers | LS | 1
1.12 | Installation Sundries (cable ties, insulation tape, spacing tape, spicing joints etc) | Item | 1
1.13 | Solar security light (50W LED light, 120W Solar Module, 150Ah Sealed maintenance free battery, Dawn-to dusk controller, 6m high pole c/w battery box |  | 2
1.14 | Manual change over switch 100 Amp the Solar System with a 30KVA generator |  | 1
Sub Total
Element No.2 : Installation and Transportation
2.1 | Installation labour, testing and transportation to site | LS | 1
Sub Total
Total
B | Construction of 50m3 of Masonry Tank
Element No.1: Excavation and Filling
1.1 | Excavate over site and remove top soil to an average depth of 150 mm | SM | 30.2
1.2 | Excavation for foundation in from stripped level but not exceeding 1.5m deep and Cart away | SM | 13.6
1.3 | 300mm thick hand packed (stones) Hardcore well rolled and rammed | M3 | 5.8875
Sub Total
Element No. 2 : Sub and Super Structure Walling
2.1 | Provide and construct a 225mm thick Masonry Walls in 1:3 sand and mortar as foundation walling | SM | 10.99
2.1 | Provide and construct a 225mm thick Masonry Walls in 1:3 water proof cement: sand mortar circular In plan | SM | 47.1
Sub Total
Element No. 3: Concreting
3.1 | 150mm thick reinforced concrete class 20/20 for foundation slab. | M3 | 2.9438
3.2 | 100mm lean concrete (1:4:8) foundation footing blinding | M3 | 1.5331
3.3 | 150mm thick reinforced concrete class 20/20 for on roof slab (Include for shuttering). | M3 | 2.9438
3.4 | 150mm thick reinforced concrete class 20/20 for ring beam | M3 | 0.5508
Sub Total
Element No. 4: Concrete Ancillaries
4.1 | Formwork
Provide cut and fix in position sawn timber (150mmx25mm) formwork or equivalent.
4.1.1 | Tank cover slab | m2 | 19.625
4.1.2 | Sided of the water tank ring beam and floor slab | m2 | 4.71
4.1.3 | 4.5m long support props for supporting the cover slab formwork | Pcs | 20
4.2 | Reinforcement
Steel reinforcement cut, bend & placed in position, unit price to include cutting, bending & placing in position with binding wire and concrete seats
4.2.1 | Supply, cut and fix 12mm diameter high tensile steel (0.89kg/m) including binding wire for floor slab concreting | KG | 592
4.2.2 | Provide and place 10mm diamter high tensile steel (0.67kg/m on the the walls in between courses | KG | 260
4.2.3 | Reinforcement for ring beam with 10mm diamter high tensile steel (0.67kg.m) spaced @200mm/cc | KG | 102.3881
4.2.4 | Reinforcement for top cover slab with 10mm diamter high tensile steel (0.67kg.m) spaced @200mm/cc | KG | 315
Sub Total
Element No. 5 : Finishing Works
5.1 | 30mm thick floor slab plaster mixed with cement: sand mortar(1:3) mortar mixed with water proof cement to appropriate slope as directed by the engineer | SM | 15.8963
5.2 | 20mm thick 1:3 cement /sand mortar plaster mixed with water proof cement to wall in three courses of 5mm,5mm and 10mm to both internal and external surfaces of tank | SM | 94.2
5.3 | 20mm thick cement: sand (1:3) mortar screed on top slab to appropriate slope as directed by the engineer | SM | 19.625
5.4 | Apply 2 coats of first grade superfast emulsion emulsion paint (Dura Coat) to the tank external surfaces exlusive of the cover slab | m2 | 68.35
5.5 | Apply 3 coats of supergloss paint (Dura Coat) to the tank external surfaces exlusive of the cover slab | m2 | 47.1
5.6 | Apply 3 coats of supergloss black paint (Dura Coat) to 300m from the ground for skirting on external surface of the foundation walling | m2 | 4.71
Sub Total
Element No. 6 : Plumbing and Piping Works
6.1 | Excavation
6.1.1 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 50 meters long | m3 | 9
5.2 | Pipe works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
5.2.1 | PN10 75mm HDPE pipes as per the specification above | LM | 550
5.3 | Pipe Fittings
Supply, deliver to site, joint and fix the following fittings
5.3.1 | 75mm HDPE Equal Tee PN 10 | Pcs | 4
5.3.2 | 75mmx75mm HDPE male adaptor | Pcs | 10
5.3.3 | 75mmx63mm HDPE male adaptor | Pcs | 2
5.3.4 | 75mm HDPE Equal Couplings | Pcs | 4
5.3.5 | 2" Peggler gate valve | Pcs | 2
6.2.1 | 2" Dia G.I Pipe Class B | No. | 3
6.2.2 | 2" Dia G.I Class B Elbows | No. | 8
6.2.3 | 2" Dia Backnuts | No. | 4
6.2.5 | 2" Valve Sockets | No. | 4
| Sub Total |  |  |  | 0
Element No.7: Other Fixtures
7.1 | Construct 1200 x 1200 x900 Valve Chambers with Lockable Steel cover at Inlet and outlet control gate | No. | 2
7.2 | Provide and fix both internal and external access ladders with 11/4" galvanized pipes | No. | 2
7.3 | Provide and fix tank breather pipes with (600mm long 2" GI pipes, 2 pcs Elbows) with wall passess. | No. | 2
7.4 | Construct 800mmx 800mm Lockable Inspection Steel cover on the top slab | No. | 1
Sub Total
Total
C | Cattle Trough (10.4M Long X1.4M Wide)
Element No.1: Earth Works
1.1 | Site cleaning up to 5cm of the top soil for the construction of construction of animal troughs | m2 | 37.12
1.2 | Foundation excavation for the animal troughs 30cm deep | m3 | 9.048
1.3 | Chart away surplus material more than 100m from the construction site or as directed by the Engineer . | m3 | 9.048
Sub Total
Element No.2: Masonry Works
2.1 | 20cm hard core used for the foundation base of the cattle trough.The unit price include supplying of basaltic stone material or equivalent with crushing, placing and compacing of the stone on the site. | m3 | 7.54
2.2 | Construction of 200mm thick masonry wall 400mm high in cement & sand mortar1:4 mix | m2 | 9.44
2.3 | Supply and construct inspection chamber/gate valve chamber with dimensions 1m long x 1m wide and 0.4 m height using block wall, with 60cm x60cm lockable, painted steel plate manhole cover for housing the control valves next to the animal trough. | No | 1
Sub Total
Element No.3: Concrete Works
3.1 | 15cm RCC concrete base slab reinforced with heavy gauge mesh wire and concrete mix ratio 1:2:4. Unit cost includes mixing, form work, placing, compacting and curing of RCC structure. | m3 | 4.524
Sub Total
Element No.4: Plastering
4.1 | Two coats of 20mm plastering to the internal and external part of the walls. The inner surface and floor of the trough should be mixed with water proof cement | m2 | 32.8
Sub Total
Element No.5: Plumbing and Piping Works
5.1 | Excavation
5.11 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 100 meters long | m3 | 18
5.2 | Pipe works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
5.2.1 | PN10 75mm HDPE pipes as per the specification above | LM | 100
5.3 | Pipe Fittings
Supply, deliver to site, joint and fix the following fittings
5.3.1 | 75mm HDPE Equal Tee PN 10 | Pcs | 4
5.3.2 | 75mmx75mm HDPE male adaptor | Pcs | 10
5.3.3 | 75mmx63mm HDPE male adaptor | Pcs | 2
5.3.4 | 75mm HDPE Equal Couplings | Pcs | 4
5.3.5 | 2" Peggler gate valve | Pcs | 4
5.3.6 | 2" G.I sockets | Pcs | 5
5.3.7 | 2" Hexaganol Nipple | Pcs | 6
5.3.8 | 2" G.I Elbow | Pcs | 6
5.3.9 | 2" G.I Union | Pcs | 6
5.3.10 | 3"x2" reducing bush | Pcs | 6
5.3.11 | 3: G.I sockets | Pcs | 4
5.3.12 | 2" G.I Pipe class B (6m long) | Pcs | 2
5.3.13 | PTFE tapes (Packet of 10) | Packet | 4
5.3.14 | Supply all materials, and construct standard masonry lockable valve chamber of 1000mm wide x1000mm long x 1000mm deep | No | 3
Sub Total
Total
D | Construction of a Standard Water Kiosk with 5,000 Liters Ovehead Plastic Tank
Element 1: Excavation
1.1 | General excavation to remove top soil to an average depth of 250mm | m2 | 17
1.2 | Excavation for wall footing depth not exceeding 1200mm deep | m3 | 5.5
1.3 | Excavation for front area depth not exceeding 250mm | m3 | 4.5
1.4 | Cart away surplus excavated material & deposit at recommended area | m3 | 2.5
1.5 | 300mm thick approved hard-core, well compacted in layers not exceeding 150mm and blinded using 50mm murrum/quarry dust | m2 | 11
1.6 | Gauge 1000 polythene Damp proof on 50mm murrum blinding | m2 | 11
Sub Total
Element No.2: Masonry Work
2.1 | 200x225x450mm natural stone to walls to superstructures walling in 1:3 sand/cement mortar finished with steel finished on one side. Rate to included mild all reinforcement at every course | m2 | 16
2.2 | 200x225x450 natural stone to walls to Substructures walling in 1:3 sand/cement mortar. Rate to included mild all reinforcement at every course | m2 | 12
2.3 | 6" x 8" X 8" Concrete ventilation blocks | no. | 20
2.4 | 150mm wide DPM to walls | m | 9.5
Sub Total
Element No.3: Concrete Works
3.1 | Concrete grade 15/20 - 400 mm thick Plinth | m3 | 0.3
3.2 | Concrete grade 15/20 - 100mm thick slanting front area | m3 | 0.6
3.3 | Reinforced concrete grade 25/20 - 125mm thick floor slab | m3 | 0.8
3.4 | Reinforced concrete grade 25/20 - 150mm thick roof slab | m3 | 1
3.5 | Reinforced concrete grade 25/20 - 450 X 250mm footing | m3 | 1.1
3.6 | Concrete grade 15/20 - to soak pit cover 100mm THK | m3 | 0.75
3.7 | Concrete grade 15/20 - to catch pit base slab | m3 | 0.05
3.8 | Reinforced concrete grade 25/20 - 150mm thick roof slab | m3 | 1
3.9 | Reinforced concrete grade 25/20 - 300 X 150Thk ring beam | m3 | 0.5
3.1 | Reinforced concrete grade 25/20 - 250 X 250mm columns | m3 | 1
Sub Total
Element No. 4: Concrete Ancillaries
4.1 | Formwork
Provide cut and fix in position sawn timber formwork or equivalent.
4.11 | a) side of foundation footing 150mm wide | m | 20
4.12 | b) edges ground slab 125mm wide | m | 10
4.13 | c) Side of lintel 20mm deep | m | 2
4.14 | d) Edge of 400mm deep plinth | m | 4.5
4.15 | e) Edges of roof slab | m | 10
4.16 | f) Underneath roof slab, including vertical support props | m2 | 6
4.17 | e) Edges of ring beam | m | 20
Reinforcement
Steel reinforcement cut, bend & placed in position, unit price to include cutting, bending & placing in position with binding wire and concrete seats
4.21 | a) Mesh 142 mild steel reinforcement mesh (0.40kg/m2) in foundation wall | m2 | 7
4.22 | b) 10mm diameter high tensile steel (0.62kg/m2) in foundation wall | Kg | 45
4.23 | a) 8mm diameter mild steel (0.40kg/m) in foundation wall | Kg | 10
4.24 | b) 12mm diameter high tensile steel (0.89kg/m) in ring beam | Kg | 42.72
4.25 | c) 8mm diameter mild steel (0.40kg/m) in ring beam | Kg | 27.72
4.26 | d) 12mm diameter high tensile steel (0.89kg/m) in column footing | Kg | 24
4.27 | e) 12mm diameter high tensile steel (0.89kg/m) in columns | Kg | 49
4.28 | f) 8mm diameter mild steel (0.40kg/m) in columns | Kg | 21
4.29 | g) 10mm diameter high tensile steel (0.62kg/m2) in roof slab | Kg | 70
Sub Total
Element No.5: Roofing
5.1 | Steel work and G.I Sheets
5.11 | Provide steel structure mounted on top of the slab to cover the tank | LS | 1
5.12 | Roof cover in Gauge 30 CIS Nailed to 50 X 75mm purlins. | m2 | 15
5.2 | Timber Work
All structure truss members shall be in seasoned eucalyptus wood and painted two coats of anti termite solution and shall be tight fixed with top tie beam with 6mm diameter plain bar.
5.21 | a) 150 X 50mm wall plate | m | 5
5.22 | b) 50X 100mm timber to rafter | m | 25
5.23 | e) 50x50mm roof purlin | m | 20
5.24 | e) 250x15mm fascia board | m | 15
Sub Total
Element No.6: Fittings and Fixtures
Doors
6.1 | 2000mm x1000mm steel door including locks and hinges to details | No | 1
6.2 | 1000mm x1000mm steel swing window including locks and hinges to details. | No | 1
6.3 | Provide and fix 3 rows from one piece of MDF (Medium Density Fibre) shelves 400mm wide and supported with 32mmx32mmx 5mm angle lines welded at an angle of 90º and spaced 800mm apart on the internal walls as shall be directed by supervising Engineer. The cost include MDT edge lining strip and boring of 3 holes for afixing the MDF board with 25mm long self tapping screw. | No | 1
Sub Total
Element No.7: Pipes and Fittings
All pipes and pipe fittings to be Galvanised Iron with Screw
7.1 | 1” G.I pipe class B | Pcs | 1
7.2 | 1” G.I Elbows | No. | 8
7.3 | 1” G.I sockets | No. | 8
7.4 | 1” dia. Gate Valve as Peglar | No. | 3
7.5 | 1" x¾” reducing bush | No. | 3
7.6 | 1” G.I tee | No. | 4
7.7 | 1” G.I union | No. | 4
7.8 | 1” G.I hexganol nipple | No. | 8
7.9 | 1" water meter | Pcs | 1
7.1 | 1' non return valve | Pcs | 1
7.11 | 2" G.I Pipe class B | Pcs | 4
7.12 | 2" back nut class B | Pcs | 4
7.13 | 2" long screw nipple | Pcs | 2
7.14 | 2" ball valve | Pcs | 1
7.15 | 2" G.I union class B | Pcs | 3
7.16 | 2" G.I elbow class B | Pcs | 8
7.17 | 2" G.I Socket | Pcs | 5
7.18 | 2'x1" reducing bush | Pcs | 1
7.19 | 2" Peggler gate valve | Pcs | 4
7.2 | Provide and install 5,000 Litres approved plastic tank on top of the kiosk roof complete with all fitting (its nipples, back nuts and float/ball valve) | No. | 1
Sub Total
Element No.8: Finishes
8.1 | Pointing to all External wall surfaces with cement sand mortar 1:2 | m2 | 16
8.2 | Apply plastering to lintel surfaces | m2 | 0.4
8.3 | Apply plastering to all wall faces | m2 | 16
8.4 | Provide three coats of gloss paint to all plastered wall faces | m2 | 16
8.5 | Provide 3 coats of bituminous paint to all exposed concreted faces | m2 | 0.4
Sub Total
Element No.9: Drainage and Tank Protection Shade
9.1 | Excavate for 400mm square X 900mm catch pit to detail | No. | 1
9.2 | 4" X 8 X 18" lining block to the site of the catch pit | m | 2.4
9.3 | 100mm thick mass concrete for catch pit base slab | m2 | 0.4
9.4 | Catch pit grating made from welded to form 25mm square mesh on 50mm steel frame | No. | 1
9.5 | Graded approved free draining hard-core/rubble stone filling the soak pit | m3 | 2
9.6 | 225mm Dia. Precast Concrete drainage pipes | m | 6
9.7 | Provide and install roof using Gauge 30 corrugated iron sheets and provide for its its supporting structure (Using HSS Tubes, welded appropriately to cover the tank on top of the water kiosk as shall be directed by Engineer on site. Bracing of the support structure to include strainers for preventing movement of tank. | LS | 1
Sub Total
3 | Total for One(1) Kiosks
| SUMMARY |  |  |  | AMOUNT
A | BOREHOLE SOLARIZATION
B | CONSTRUCTION OF 50M3 MASONRY TANK
C | CONSTRUCTION OF CATTLE TROUGH
D | CONSTRUCTION OF WATER KIOSK
GRAND TOTAL

## Safaricom BH
BOQ No:19
Project : | BORESHA
County | Mandera
Sub County | Lafey
Location | Safaricom BH
Description | Construction of Pump/Generator House and Repair of Elevated Steel Tank
Item No | Item Description | Unit | Qty | Rate | Amount
A | Pump House/ Generator House (4150mmx4000mm)
Element No.1:Site clearance:
1.1 | Clear the site from the debris and commence site establishment | 1 | 25
Sub Total
Element No.2: Excavation and Backfilling
2.1 | Excavation of substructure foundation (0.6mx0.5mx16m) the excavation of pipe trenches | M3 | 2.28
2.2 | Supply and backfill with150mm approved hardcore and rashed Stone, supply and fill (imported or Excavated selected material over the ground floor compact AS PER Specification | M3 | 2.4
2.3 | Supply and fill 100mm thick approved murram over the selected material, level with hammer | M3 | 1.6
Sub Total
Element No.3: Masonry Work
3.1 | Substructure Walling
3.1.1 | Construct 3 courses of 225mmX225mm natural cut stone foundation wall bedded in cement sand mortar 1:3. Rate to include reinforcement with hoop iron at every 2 courses and at the last course to hold the 100mmx 50mm wall plate | M2 | 7.2
3.2 | Superstructure Walling - Masonry
3.2.1 | Construct 5 courses of 150mmX225mm well dressed natural cut stone superstructural wall bedded in cement sand mortar 1:3 with one side left for plastering. Rate to include reinforcement with hoop iron at every 2 courses | m2 | 16.8
3.2.2 | 150mm wide DPM to walls | m | 16
3.3 | Superstructure Walling - Timber Work
All structure members shall be in seasoned cypress wood and painted two coats of anti termite solution
3.3.1 | 100mm X 50mm bottom wall plate | m | 16
3.3.2 | 100mm X 50mm top wall plate | m | 16
3.3.3 | 100mm X 50mm studs (vertical height -2400mm from the bottom wall plate) | m | 38.4
3.3.4 | 100mm X 50mm girts | m | 32
3.3.5 | Heavy gauge mesh wire | Pcs | 14
Sub Total
Element No.4: Concrete Works
4,1 | 100mm thick concrete class 25 (1:2:4) for blinding the 600mm wide foundation wall footing | m3 | 0.456
4.2 | 150mm concrete class 25 (1:2:4) in floor slab | m3 | 2.4
4.3 | 75mm Concrete Grade 15 (1:3:6) fort disabled person access ramp, sloping at 1:7 | m3 | 0.252
4.4 | Construct a concrete plinth1.2m wideX2m longX0.5m thick with concrete class 25(1:2:4) with double strand10mm reinforcement bars. | m3 | 1.5
Sub Total
Element No. 5: Concrete Ancillaries
5.1 | Formwork
Provide cut and fix in position sawn timber formwork or equivalent.
5.1.1 | b) Edges of floor slab with 50mm x150mm | m2 | 16
5.1.2 | e) Tree props to support the 50mm x 150mm timbers of the flooor slab | Poles | 5
5.2 | Reinforcement
Steel reinforcement cut, bend & placed in position, unit price to include cutting, bending & placing in position with binding wire and concrete seats
5.2.1 | d) 10mm diameter high tensile steel (0.617kg/m) in channel base and both wallings spaced @200mm C/C | Kgs | 145
Sub Total
Element No.6: Roofing
6.1 | Currugated Sheets
6.1 | Corrugated sheets and BP760 Boxed profiled sheets (3000mm long X762mm wide) Nailed to 50 X50 mm purlins. | Pcs | 16
6.2 | Timber Work
All structure truss members shall be in seasoned cypress wood and painted two coats of anti termite solution and shall be tight fixed with top tie beam with 6mm diameter plain bar.
6.2.1 | 100mmX50mm timber to rafter and tie beam | LM | 30
6.2.2 | 50mmX50mm timber to fasten the truss members | LM | 6.8
6.3.3 | 100 X 50mm vertical member (King Post) | LM | 6
6.3.4 | 50mmX50mm roof purlins | LM | 36
6.3.5 | 200mmx 25mm prepainted Fascia Board | LM | 16
6.3.6 | 50mmX50mm Ceiling buttens | LM | 77.4
6.3.7 | Supply and fix 4mm laminated ceiling board in rooms with appropriate ceils nails | M2 | 16
Sub Total
Element No.7: Finishing Works
7.1 | Apply 20mm thick plaster to internal surfaces with cement & sand mortar 1:2 | M2 | 15.36
7.2 | Apply 20mm thick plaster to external surfaces as skirting with cement & sand mortar 1:2 | M2 | 6.4
7.3 | Apply 2 coats of first grade superfast emulsion paint (Dura Coat) to the pump house internal surfaces | m2 | 15.36
7.4 | Apply 2coats of first grade plastic emulsion paint on the ceiling surface. | m2 | 16
7.5 | Apply 3 coats of supergloss paint (Dura Coat) external keyed block wall grooves. | m2 | 17.4
Sub Total
Element N.8: Fixture and Fittings
8.1 | Door
8.1.1 | Fabricate 2000mmx2100mm double door made of 16 gauge steel plate welded to the frame, 38x38x3mm thick steel angles for door main frame, 25mmx25mm x 2mm RHS welded to steel plate. Make provisionof 100mm wall passes for anchoring the door frame on the wall | PCS | 1
Sub Total
Element No.9: Electrical Installations
9.1 | Carry out elctrical installation using white rectangular electrical conduits and 2.5mm single cable including double electrical (2pcs) sockets, 1 double gang switch (1pcs) as well flouresent holder and bulb (2 set) | Lumpsum | 1
Sub Total
Total
B | BILL No.2: Repair of Existing Elevated of Existing Steel Tank
Element No. 1: Tank Dis-assembly
1.1 | Supply and install and disassemble appropriate scaffold under and around the Tank | Item | 1
1.2 | Remove the whole roof cover of the Tank | SM | 25
1.3 | Remove all damaged tank steel plates | No | 12
1.4 | Remove all steel Stays, braces, struts and Ties from the tank structure | Item | 1
1.5 | Remove the Old Water Level Gauge | Item | 1
1.6 | Scrub both the internal & external surfaces of the tank to render surfaces clean | SM | 118
Sub Total
Element No. 2. Tank Reassembly
2.1 | Replace earlier removed steel Stays braces and Clips and fasten (Bolt/ weld) these in positions | Item | 1
2.2 | Replace earlier removed tank plates with 6mm thick plates and fasten these with appropriate bolts, nuts and washers | No | 12
Sub Total
Element No. 3. Finishing Works
3.1 | Apply 2 coats of bordex along all the internal joints between tank plates | Lumspusm | 1
3.2 | Replace the whole tank roof cover with 2mm thick Plain Galvanized Steel Sheets and provide and fit a new Manhole with lockable cover. | SM | 16
3.3 | Apply 3 coats of bituminous paint over tank floor and walls internally | SM | 56
3.4 | Apply 3 Coats of metallic aluminum paint over tank surfaces externally (Tank floor soffit, Sides, roof, tank support beams and whole tank tower structure) | SM | 118
Sub Total
Element No. 4 : Site Clearance
4.1 | Clear site of any material remains, debris, objects, litter e.t.c. on site | Item | 1
Sub Total
Total
| SUMMARY |  |  |  | AMOUNT
A | PUMP/GEN HOUSE CONSTRUCTION
B | REPAIR OF ELEVATED STEEL TANK
GRAND TOTAL

## Kamor Liban
BOQ No:20
Project : | BORESHA
County | Mandera
Sub County | Lafey
Location | Kamor Liban
Description | Repair of Cattle Trough, 50M3 Masonry Tank and Solar System
Item No | Item Description | Unit | Qty | Rate | Amount
A | Rehabilitation of 2No. Cattle Troughs
Element No. 1: Hacking & Excavation
1.1 | Hacked deep cracks as appropriate | SM | 11
Sub Total
Element No. 2: Plastering
2.1 | 20mm thick plaster, cement and sand mortar (1:3) to floor with water proof cement steel trowelled to smooth finish. | SM | 10
2.2 | 20mm thick plaster, cement and sand mortar (1:3) to internal side of walls with water proof steel trowelled to smooth finish. | SM | 10
2.3 | 12mm thick plaster, cement and sand mortar (1:3) to external side of walls | SM | 15
Sub Total
Element No.3: Plumbing and Piping Works
3.1 | Excavation
3.1.1 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 100 meters long | m3 | 36
3.2 | Pipe works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
3.2.1 | PN10 75mm HDPE pipes as per the specification above | LM | 550
5.3 | Pipe Fittings
3.3.1 | Supply, deliver to site, joint and fix the following fittings
3.3.2 | 75mm HDPE Equal Tee PN 10 | Pcs | 4
3.3.3 | 75mmx75mm HDPE male adaptor | Pcs | 10
3.3.4 | 75mmx63mm HDPE male adaptor | Pcs | 2
3.3.5 | 75mm HDPE Equal Couplings | Pcs | 4
3.3.6 | 2" Peggler gate valve | Pcs | 3
3.3.7 | 2" G.I sockets | Pcs | 5
3.3.8 | 2" Hexaganol Nipple | Pcs | 6
3.3.9 | 2" G.I Elbow | Pcs | 6
3.3.10 | 2" G.I Union | Pcs | 6
3.3.11 | 3"x2" reducing bush | Pcs | 6
3.3.12 | 3: G.I sockets | Pcs | 4
3.3.13 | 2" G.I Pipe class B (6m long) | Pcs | 1
3.3.14 | PTFE tapes (Packet of 10) | Packet | 4
3.3.15 | Supply all materials, and construct standard masonry lockable valve chamber of 1000mm wide x1000mm long x 1000mm deep | No | 1
Sub Total
Total
Total for the Rehabilitation of 2 No. Troughs
B | Bill No. 2: Repair of 1No 50M3 Masonry Tank
Element No. 1: Hacking and Lining
1.1 | Hack and demolish existing wall finishes on internal,external walls and floor surfaces including deep cracks and cart away debris. | SM | 80
1.2 | Inject cement mortar to all hacked surfaces and fix with chicken wire appropriate re-bars staples and mortar (1:3) | SM | 45
Sub Total
Element No. 2: Plastering and Finishing
2.1 | 20mm thick plaster mixed with Sika or equivalent water proofing admixture to walls and concrete surfaces internally and externally. | SM | 80
2.2 | 25mm thick plaster screed to base slab and roof slab with waterproof cement | SM | 34
2.3 | Prepare and apply three coats gloss paint to all plastered external wall surfaces | SM | 64
Sub Total
Element No. 3: Pipework and Plumbing Fixtures
3.1 | Provide 75mm GI inlet pipe class "B" with and including joining fittings to tank and fix as described | LM | 8
3.2 | Provide 50mm GI outlet pipes class "B" with and including joining fittings to tank and fix as described | LM | 8
3.3 | Construct 1200mm x 1200mm x 900mm valve chambers with lockable steel cover at inlet and outlet complete with control valves and adjoining fittings | No. | 2
3.4 | Provide and fix tank breather pipes with (600mm long 2" GI pipes, 2 pcs Elbows) with wall passess. | No. | 2
Sub Total
Total
C | Repair of the Solar System
Element No. 1: Supply and deliver to site, install and commission test the following:
1.1 | Replacement of damaged pannels, 10 No. with similar pannels, polycrystalline solar panels with power rating 250 W | Item | 10
1.2 | Replacement of Hybrid inverter 7.5 KW 3PH | Item | 1
1.3 | Repair or replacement of other solar accessories at the site | LS | 1
Sub Total
Element No.2 : Installation and Transportation
2.1 | Installation labour, testing and transportation to site | LS | 1
Sub Total
Total
| SUMMARY |  |  |  | AMOUNT
A | REPAIR OF CATTLE TROUGHS
B | REPAIR OF MASONRY TANK
C | REPAIR OF SOLAR SYSTEM
GRAND TOTAL