## Budget Summary
SUMMARY SHEET
No | Bill No | Estimated Amount
1 | Bill No. 3: Fincharo
2 | Bill No. 4 : Shimbir Fatuma
3 | Bill No. 5 : Qarsadamu
4 | Bill No. 6 : Wargadud
5 | Bill No. 16: Qalanqalesa
6 | Bill No. 17: Chachabole
7 | Bill No. 18: Harsanga
Grand Total

## Fincharo
BOQ No:3
Project : | BORESHA
County | Mandera
Sub County | Mandera South
Location | Fincharo
Description | Borehole Solarization, Construction of 2No. Cattle Troughs, Construction of 1No Pump House and Community Water Point
Item No | Item Description | Unit | Qty | Rate | Amount
A | Borehole Solarization
Element No.1: Supply and deliver to site, install and commission test the following:
1.1 | Dayliff DSD 8/40, 7.5 KW 3PH Pump c/w Pump End and Sub-mortar or its approved equivalent including pump installation | Set | 1
1.2 | Dayliff SV3 7.5KW 3PH Sunverter | Set | 1
1.3 | Dayliff 2" Adaptor Set | No. | 1
1.4 | Borehole cover 2"x6" complete with fittings | No. | 1
1.5 | Adaptor Box 4x4x3mm | No. | 1
1.6 | PVC conduit pipe 25mm Class D | No. | 26
1.7 | Monocrystalline photo voltaic solar modules 665W, 24Vdc | No. | 17
1.8 | Dayliff 4ST 1000 DC/40A PV Disconnect Switch | No. | 1
1.9 | Earth rod complete with clamp | No. | 1
1.1 | Lightning Arrestor | No. | 1
1.11 | Copper Earth Cable 6mm2 | M | 25
1.12 | IMeter PVC Cooling sleeve "4" | No. | 1
1.13 | 6mm2 4 core underground cable (armoured) | M | 28
1.14 | 1.5mm2- 2 core undergroudn armoured cable(elecrode sensor) | M | 28
1.15 | 6mm2 - 4 core standard PVC flat submersible drop cable | M | 160
1.16 | Londex standard dual core cable (probe sensor) | M | 160
1.17 | Twin flat10mm cable with earth (Wiring connection) | M | 35
1.18 | Well probe sensor | No. | 1
1.19 | GS sunverter steel fabricates enclosure 1000x500x350mm | No. | 1
1.2 | Design as per radiations day angle, fabrication and installation of solar support structure for the specified solar panels. Rate to include for system testing. Use 75mmx 75mmx3mm SHS vertical support, 50mmx50mmx3mm struts and 50mmx50mmx2mm SHS purlins sections to hold panels tight into position. All joints braced. Height of the structure 4m above ground. The structure design must be preapproved before installation by the clients engineers | LS | 1
1.21 | Installation Sundries (cable ties, insulation tape, spacing tape, spicing joints etc) | Item | 1
1.22 | Solar security light (50W LED light, 120W Solar Module, 150Ah Sealed maintenance free battery, Dawn-to dusk controller, 6m high pole c/w battery box |  | 2
1.23 | Manual change over switch 100 Amp the Solar System with a 30KVA generator |  | 1
Sub Total
Element No.2 : Installation and Transportation
2.1 | Installation labour, testing and transportation to site | LS | 1
Sub Total
Total
B | Cattle Trough (10.4M Long X1.4M Wide)
Element No.1: Earth Works
1.1 | Site cleaning up to 5cm of the top soil for the construction of construction of animal troughs | m2 | 37.12
1.2 | Foundation excavation for the animal troughs 30cm deep | m3 | 9.048
1.3 | Chart away surplus material more than 100m from the construction site or as directed by the Engineer . | m3 | 9.048
Sub Total
Element No.2: Masonry Works
2.1 | 20cm hard core used for the foundation base of the cattle trough.The unit price include supplying of basaltic stone material or equivalent with crushing, placing and compacing of the stone on the site. | m3 | 7.54
2.2 | Construction of 200mm thick masonry wall 400mm high in cement & sand mortar1:4 mix | m2 | 9.44
2.3 | Supply and construct inspection chamber/gate valve chamber with dimensions 1m long x 1m wide and 0.4 m height using block wall, with 60cm x60cm lockable, painted steel plate manhole cover for housing the control valves next to the animal trough. | No | 1
Sub Total
Element No.3: Concrete Works
3.1 | 15cm RCC concrete base slab reinforced with heavy gauge mesh wire and concrete mix ratio 1:2:4. Unit cost includes mixing, form work, placing, compacting and curing of RCC structure. | m3 | 4.524
Sub Total
Element No.4: Plastering
4.1 | Two coats of 20mm plastering to the internal and external part of the walls. The inner surface and floor of the trough should be mixed with water proof cement | m2 | 32.8
Sub Total
Element No.5: Plumbing and Piping Works
5.1 | Excavation
5.1.1 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 100 meters long | m3 | 18
5.2 | Pipe works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
5.2.1 | PN10 75mm HDPE pipes as per the specification above | LM | 550
5.3 | Pipe Fittings
5.3.1 | Supply, deliver to site, joint and fix the following fittings
5.3.2 | 75mm HDPE Equal Tee PN 10 | Pcs | 4
5.3.3 | 75mmx75mm HDPE male adaptor | Pcs | 10
5.3.4 | 75mmx63mm HDPE male adaptor | Pcs | 2
5.3.5 | 75mm HDPE Equal Couplings | Pcs | 4
5.3.6 | 2" Peggler gate valve | Pcs | 4
5.3.7 | 2" G.I sockets | Pcs | 5
5.3.8 | 2" Hexaganol Nipple | Pcs | 6
5.3.9 | 2" G.I Elbow | Pcs | 6
5.3.10 | 2" G.I Union | Pcs | 6
5.3.11 | 3"x2" reducing bush | Pcs | 6
5.3.12 | 3: G.I sockets | Pcs | 4
5.3.13 | 2" G.I Pipe class B (6m long) | Pcs | 2
5.3.14 | PTFE tapes (Packet of 10) | Packet | 4
5.3.15 | Supply all materials, and construct standard masonry lockable valve chamber of 1000mm wide x1000mm long x 1000mm deep | No | 3
Sub Total
Total
Total for 2 Cattle Troughs
C | Pump House/ Generator House (4150mmx4000mm)
Element No.1:Site clearance:
1.1 | Clear the site from the debris and commence site establishment | 1 | 25
Sub Total
Element No.2: Excavation and Backfilling
2.1 | Excavation of substructure foundation (0.6mx0.5mx16m) the excavation of pipe trenches | M3 | 2.28
2.2 | Supply and backfill with150mm approved hardcore and rashed Stone, supply and fill (imported or Excavated selected material over the ground floor compact AS PER Specification | M3 | 2.4
2.3 | Supply and fill 100mm thick approved murram over the selected material, level with hammer | M3 | 1.6
Sub Total
Element No.3: Masonry Work
3.1 | Substructure Walling
3.1.1 | Construct 3 courses of 225mmX225mm natural cut stone foundation wall bedded in cement sand mortar 1:3. Rate to include reinforcement with hoop iron at every 2 courses and at the last course to hold the 100mmx 50mm wall plate | M2 | 7.2
3.2 | Superstructure Walling - Masonry
3.2.1 | Construct 5 courses of 150mmX225mm well dressed natural cut stone superstructural wall bedded in cement sand mortar 1:3 with one side left for plastering. Rate to include reinforcement with hoop iron at every 2 courses | m2 | 16.8
3.2.2 | 150mm wide DPM to walls | m | 16
3.3 | Superstructure Walling - Timber Work
All structure members shall be in seasoned cypress wood and painted two coats of anti termite solution
3.3.1 | 100mm X 50mm bottom wall plate | m | 16
3.3.2 | 100mm X 50mm top wall plate | m | 16
3.3.3 | 100mm X 50mm studs (vertical height -2400mm from the bottom wall plate) | m | 38.4
3.3.4 | 100mm X 50mm girts | m | 32
3.3.5 | Heavy gauge mesh wire | Pcs | 14
Sub Total
Element No.4: Concrete Works
4,1 | 100mm thick concrete class 25 (1:2:4) for blinding the 600mm wide foundation wall footing | m3 | 0.456
4.2 | 150mm concrete class 25 (1:2:4) in floor slab | m3 | 2.4
4.3 | 75mm Concrete Grade 15 (1:3:6) fort disabled person access ramp, sloping at 1:7 | m3 | 0.252
4.4 | Construct a concrete plinth1.2m wideX2m longX0.5m thick with concrete class 25(1:2:4) with double strand10mm reinforcement bars. | m3 | 1.5
Sub Total
Element No. 5: Concrete Ancillaries
5.1 | Formwork
Provide cut and fix in position sawn timber formwork or equivalent.
5.1.1 | b) Edges of floor slab with 50mm x150mm | m2 | 16
5.1.2 | e) Tree props to support the 50mm x 150mm timbers of the flooor slab | Poles | 5
5.2 | Reinforcement
Steel reinforcement cut, bend & placed in position, unit price to include cutting, bending & placing in position with binding wire and concrete seats
5.2.1 | d) 10mm diameter high tensile steel (0.617kg/m) in channel base and both wallings spaced @200mm C/C | Kgs | 145
Sub Total
Element No.6: Roofing
6.1 | Currugated Sheets
6.1 | Corrugated sheets and BP760 Boxed profiled sheets (3000mm long X762mm wide) Nailed to 50 X50 mm purlins. | Pcs | 16
6.2 | Timber Work
All structure truss members shall be in seasoned cypress wood and painted two coats of anti termite solution and shall be tight fixed with top tie beam with 6mm diameter plain bar.
6.2.1 | 100mmX50mm timber to rafter and tie beam | LM | 30
6.2.2 | 50mmX50mm timber to fasten the truss members | LM | 6.8
6.3.3 | 100 X 50mm vertical member (King Post) | LM | 6
6.3.4 | 50mmX50mm roof purlins | LM | 36
6.3.5 | 200mmx 25mm prepainted Fascia Board | LM | 16
6.3.6 | 50mmX50mm Ceiling buttens | LM | 77.4
6.3.7 | Supply and fix 4mm laminated ceiling board in rooms with appropriate ceils nails | M2 | 16
Sub Total
Element No.7: Finishing Works
7.1 | Apply 20mm thick plaster to internal surfaces with cement & sand mortar 1:2 | M2 | 15.36
7.2 | Apply 20mm thick plaster to external surfaces as skirting with cement & sand mortar 1:2 | M2 | 6.4
7.3 | Apply 2 coats of first grade superfast emulsion paint (Dura Coat) to the pump house internal surfaces | m2 | 15.36
7.4 | Apply 2coats of first grade plastic emulsion paint on the ceiling surface. | m2 | 16
7.5 | Apply 3 coats of supergloss paint (Dura Coat) external keyed block wall grooves. | m2 | 17.4
Sub Total
Element N.8: Fixture and Fittings
8.1 | Door
8.1.1 | Fabricate 2000mmx2100mm double door made of 16 gauge steel plate welded to the frame, 38x38x3mm thick steel angles for door main frame, 25mmx25mm x 2mm RHS welded to steel plate. Make provisionof 100mm wall passes for anchoring the door frame on the wall | PCS | 1
Sub Total
Element No.9: Electrical Installations
9.1 | Carry out elctrical installation using white rectangular electrical conduits and 2.5mm single cable including double electrical (2pcs) sockets, 1 double gang switch (1pcs) as well flouresent holder and bulb (2 set) | Lumpsum | 1
Sub Total
Total
(D) | Communal Water Point - 6 TapTap Stand
Element No.1: Excavation/ Earthworks
1.1 | Site cleaning up to 5cm of the top soil for the construction of public water collection point. | m2 | 25
1.2 | Bulk excavation in the top soil (300cm) for the tap stand. | m3 | 1.701
1.3 | Dispose away surplus material more than 10Om from the construction site or as directed by the Engineer . | m3 | 1.301
Sub Total
Element No.2; Masonry Work
2.1 | 200mmx225mm x450mm natural stone to walls to substructures and sub substructure for both the water kiosk and access ramp retention walling, 1:3 sand/cement mortar. Rate to included mild all reinforcement at every course | m2 | 8.52
2.2 | Fill with approved hardcore the kiosk capartment and the ramps to height of 45cm on and 70cm respectively from the foundation base. The unit price include supplying of basaltic stone material or equivalent with crushing, placing and compacting for water kiosk base | m3 | 0.85
2.3 | Supply all materials, and construct standard masonry lockable valve chamber of 1000mm wide x1000mm long x 1000mm deep with 150mmx225mm blocks and install 600mmx600mm lockable, painted steel plate manhole cover for housing the control valves next to the water kiosk. | No | 1
Sub Total
Element No.3: Concreting
3.1 | 5cm thick blinding layer under foundations with class15: mix 1:3:6 , cement: sand:aggregate | m3 | 1.134
3.2 | 20mm reinforced concrete vertical wall for tap stand 150cm from the foundation base reinforced with 10mm twisted bars spaced@20mm c/c concrete mix ratio 1:2:4. Unit cost includes mixing, form work, placing, compacting and curing of RCC structure. | m3 | 0.57
3.3 | 150cm RCC concrete water kiosk floor slab reinforced with heavy gauge mesh and concrete mix ratio 1:2:4. Unit cost includes mixing, form work, placing, compacting and curing of RCC structure. | m3 | 0.38
3.4 | 10cm RCC concrete access ramp reinforced with heavy gauge mesh and concrete mix ratio 1:2:4. Unit cost includes mixing, form work, placing, compacting and curing of RCC structure. | m3 | 0.292
3.5 | Construction of RCC 100mm thick with mesh wire sand, aggregate and cement ratio of 1:2:4 to cover the soak away pit | m3 | 0.11304
Sub Total
Element No.4: Finishes
4.1 | Plaster with 20mm thick mortar mix ratio of 1:3 on the foundation wall surfaces, vertical concrete wall and slabwith smooth metal float finish. | m2 | 8.47
4.2 | Provide for 110mm waste pipe with 2 elbow for the water drainage and 110mm diameter metallic vent grille at the drainage main inlet | lumpsum | 1
Sub Total
Element No.5 Soak Away Pit
5.1 | Excavation of soak away pit for water drainage 1000mm deep x 1000m diameter fed with 110mm heavy gauge waste pipe and it accessories. | m3 | 3.14
5.2 | Backfilling of the soak away pit with approved rubble stones/hardcore | m3 | 1.2
Sub Total
Element No.6: Plumbing and Piping Works
6.1 | 1" GI nipple Class B | Pcs | 6
6.2 | 1" Hexagonal nipple class B | Pcs | 6
6.3 | 1"G.I union class B | Pcs | 3
6.4 | 1"x3/4"reducing bush class B | Pcs | 6
6.5 | 1" GI Socket class B | Pcs | 10
6.6 | 1" GI pipe Class B | Pcs | 1
6.7 | 1" GI elbow class B | Pcs | 5
6.8 | 1" GI Cross Tee | Pcs | 4
6.9 | 1' Hexagonal nipple | Pcs | 4
6.1 | Push/Self closing cock's/taps | Pcs | 12
6.11 | 1" water meter | Pcs | 1
6.12 | Supply all materials, and construct standard masonry lockable valve chamber of 1000mm wide x1000mm long x 1000mm deep | No | 1
Sub Total
7 | Element No.7: Tap Stand Protection Fence (5000mm x5000mm)
7.1 | Poles and ancillary items
7.11 | Supply transport to site and install 100mmx100mm thick concrete poles 2200mm tall with provision for barbed wire line holes. Rate to include for excavation of pole pits | Pcs | 13
7.12 | Supply and install 1500mm wide x1.8mm high single leave steel grill gate to the concrete poles complete with iron mongery (use 50mmx25mmx6mm SHS with 38mmx25mmx6mm vertical members). Provide for epoxy primer paint with 2 coats of final gloss paint | Pcs | 1
7.13 | G12.5 chainlink 1.8m high | SM | 40
7.14 | Barbed wire 16g, 25kg -6 strand | LM | 120
Sub Total
7.2 | Element No.8: Mass concrete class C20/25 in:
7.21 | To poles | CM | 0.67513
7.22 | Column edges over 150mm but not exceeding 300 mm girth | SM | 7
7.23 | 150mm wide x 150mm deep Concrete pitching to chainlink base ratio 1:3:6 | CM | 0.45
Sub Total
Total for One (1) Communal Tap Stand
| SUMMARY |  |  |  | AMOUNT
A | BOREHOLE SOLARIZATION
B | CATTLE TROUGH CONSTRUCTION
C | PUMP HOUSE/GENERATOR HOUSE CONSTRUCTION
D | COMMUNAL WATER POINT CONSTRUCTION
GRAND TOTAL

## Shimbir Fatuma
BOQ No:4
County | Mandera
Sub County | Mandera South
Location | Shimbir Fatuma
Description | Borehole Solarization &Equiping and Perimeter Fencing
Item No | Item Description | Unit | Qty | Rate | Amount
A | Borehole Equiping and Solarization Works
Element No.1:Supply and deliver to site, install and commission test the following:
1.1 | Dayliff DSD 8/40, 7.5 KW 3PH Pump c/w Pump End and Sub-mortar or its approved equivalent | Set | 1
1.2 | Dayliff SV3 7.5KW 3PH Sunverter | Set | 1
1.3 | Dayliff 2" Adaptor Set | No. | 1
1.4 | Borehole cover 2"x6" complete with fittings | No. | 1
1.5 | Adaptor Box 4x4x3mm | No. | 1
1.6 | PVC conduit pipe 25mm Class D | No. | 26
1.7 | Monocrystalline photo voltaic solar modules 665W, 24Vdc | No. | 17
1.8 | Dayliff 4ST 1000 DC/40A PV Disconnect Switch | No. | 1
1.9 | Earth rod complete with clamp | No. | 1
1.1 | Lightning Arrestor | No. | 1
1.11 | Copper Earth Cable 6mm2 | M | 25
1.12 | IMeter PVC Cooling sleeve "4" | No. | 1
1.13 | 6mm2 4 core underground cable (armoured) | M | 28
1.14 | 1.5mm2- 2 core undergroudn armoured cable(elecrode sensor) | M | 28
1.15 | 6mm2 - 4 core standard PVC flat submersible drop cable | M | 160
1.16 | Londex standard dual core cable (probe sensor) | M | 160
1.17 | Twin flat10mm cable with earth (Wiring connection) | M | 35
1.18 | Well probe sensor | No. | 1
1.19 | GS sunverter steel fabricates enclosure 1000x500x350mm | No. | 1
1.2 | Design as per radiations day angle, fabrication and installation of solar support structure for the specified solar panels. Rate to include for system testing. Use 75mmx 75mmx3mm SHS vertical support, 50mmx50mmx3mm struts and 50mmx50mmx2mm SHS purlins sections to hold panels tight into position. All joints braced. Height of the structure 4m above ground. The structure design must be preapproved before installation by the clients engineers | LS | 1
1.21 | Installation Sundries (cable ties, insulation tape, spacing tape, spicing joints etc) | Item | 1
1.22 | Solar security light (50W LED light, 120W Solar Module, 150Ah Sealed maintenance free battery, Dawn-to dusk controller, 6m high pole c/w battery box |  | 2
1.23 | Manual change over switch 100 Amp the Solar System with a 30KVA generator |  | 1
Sub Total
Element No.2 : Installation and Transportation
2.1 | Installation labour, testing and transportation to site | LS | 1
Sub Total
Total
B | Perimeter Fencing 30mx30m
Element No.1: Supply of Concrete Poles & Other Material Inputs
1.1 | Supply transport to site and install 100mm x100mm thick concrete poles,3000mm long with 500mm cranked length and 6 provisional holes to accomodate straining/barbed wire spaced @ 2500mmc/c. Rate to include for excavation of pole pits and firming with concrete at the poles base. | Pcs | 50
1.2 | Ditto but 100mmx100mm and 2000mm long precast concrete strut posts of grade C-20 placed at corners and after every 15m spacing. Rate to include for excavation of pole pits and firming with concrete at the poles base. | No. | 16
1.3 | Provide materials, fabricate and install purpose made steel grilled double leaf security gate overall size 4000x2000mm high in two equal opening leaves each size 2000x2000mm high with external frame of 50x50x3mm SHS. Vertical bracing of 50x50x3mm spaced @400mm c/c, horizontal frame of 40x40x3mm spaced @ 300mm c/c all fixed to external frame by wielding including all hinged supported by RC columns complete with locking devices all painted with two coats of approved primer and finished with final coat first grade gloss paint. | Pcs | 1
1.3 | G12.5 chainlink 2m high | SM | 240
1.4 | Barbed wire 16g, 25kg -6 strand | LM | 720
Sub Total
Element No.2: Mass concrete class C20/25 in:
2.1 | To concrete poles | CM | 0.918
2.2 | 300mmx300mm Gate columns | CM | 0.5
2.3 | 150mm wide x 150mm deep Concrete pitching to chainlink base ratio 1:3:6 | CM | 2.7
Sub Total
Element No.3: Conceter Ancillary
3.1 | Formwork to;
3.1.1 | Column edges over 150mm but not exceeding 300 mm girth | SM | 21.12
3.2 | Reinforcment Bars
3.2.1 | Provide, cut and place 10mm square twisted steel rebars in gate columns and 600mmx600mm footing | Kg | 20
3.2.2 | 8mm twisted steel rebars as stirrups in column @150mm | Kg | 14
Sub Total
Elememnt No.4: Finishes
4.1 | 20mm thick plastering with cement: sand (1:4) screed to surfaces with 12mm thick lime steel trowelled smooth finish on columns | SM | 21.12
4.2 | Gloss painting to columns- code provided by Engineer | SM | 6
Sub Total
Total
| SUMMARY |  |  |  | AMOUNT
A | BOREHOLE SOLARIZATION & EQUIPING
B | PERIMETER FENCING
GRAND TOTAL

## Qarsadamu
BOQ No:5
Project : | BORESHA
County | Mandera
Sub County | Mandera South
Location | Qarsadamu
Description | Installation of Perimeter Fencing
Item No | Item Description | Unit | Qty | Rate | Amount
A | Perimeter Fencing 30mx30m
Element No.1: Supply of Concrete Poles & Other Material Inputs
1.1 | Supply transport to site and install @2500mmc/c concrete poles 2600mm tall and 500 cranked length with 100mmx100mm cross sectional area with 6 provisional holes for barbed wire. Rate to include for excavation of pole pits and strainers (8) and firming with concrete at the poles base. | Pcs | 60
1.2 | Provide materials, fabricate and install purpose made steel grilled double leaf security gate overall size 4000x2000mm high in two equal opening leaves each size 2000x2000mm high with external frame of 50x50x3mm SHS. Vertical bracing of 50x50x3mm spaced @400mm c/c, horizontal frame of 40x40x3mm spaced @ 300mm c/c all fixed to external frame by wielding including all hinged supported by RC columns complete with locking devices all painted with two coats of approved primer and finished with final coat first grade gloss paint. | Pcs | 1
1.3 | G12.5 chainlink 2m high | SM | 240
1.4 | Barbed wire 16g, 25kg -6 strand | LM | 720
Sub Total
Element No.2: Mass concrete class C20/25 in:
2.1 | To concrete poles | CM | 0.918
2.2 | 300mmx300mm Gate columns | CM | 0.5
2.3 | 150mm wide x 150mm deep Concrete pitching to chainlink base ratio 1:3:6 | CM | 2.7
Sub Total
Element No.3: Conceter Ancillary
3.1 | Formwork to;
3.1.1 | Column edges over 150mm but not exceeding 300 mm girth | SM | 21.12
3.2 | Reinforcment Bars
3.2.1 | Provide, cut and place 10mm square twisted steel rebars in gate columns and 600mmx600mm footing | Kg | 20
3.2.2 | 8mm twisted steel rebars as stirrups in column @150mm | Kg | 14
Sub Total
Elememnt No.4: Finishes
4.1 | 20mm thick plastering with cement: sand (1:4) screed to surfaces with 12mm thick lime steel trowelled smooth finish on columns | SM | 21.12
4.2 | Gloss painting to columns- code provided by Engineer | SM | 6
Sub Total
Total
| SUMMARY |  |  |  | AMOUNT
A | PERIMETER FENCING
GRAND TOTAL

## Wargadud
BOQ No:6
Project : | BORESHA
County | Mandera
Sub County | Mandera South
Location | Wargadud
Description | Borehole Solarization, 1No. Water Kiosk Construction and 2No.Cattle Trough Construction
Item No | Item Description | Unit | Qty | Rate | Amount
A | Borehole Equiping and Solarization Works
Element No.1:Supply and deliver to site, install and commission test the following:
1.1 | Dayliff DSD 8/40, 7.5 KW 3PH Pump c/w Pump End and Sub-mortar or its approved equivalent | Set | 1
1.2 | Dayliff SV3 7.5KW 3PH Sunverter | Set | 1
1.3 | Dayliff 2" Adaptor Set | No. | 1
1.4 | Borehole cover 2"x6" complete with fittings | No. | 1
1.5 | Adaptor Box 4x4x3mm | No. | 1
1.6 | PVC conduit pipe 25mm Class D | No. | 26
1.7 | Monocrystalline photo voltaic solar modules 665W, 24Vdc | No. | 17
1.8 | Dayliff 4ST 1000 DC/40A PV Disconnect Switch | No. | 1
1.9 | Earth rod complete with clamp | No. | 1
1.1 | Lightning Arrestor | No. | 1
1.11 | Copper Earth Cable 6mm2 | M | 25
1.12 | IMeter PVC Cooling sleeve "4" | No. | 1
1.13 | 6mm2 4 core underground cable (armoured) | M | 28
1.14 | 1.5mm2- 2 core undergroudn armoured cable(elecrode sensor) | M | 28
1.15 | 6mm2 - 4 core standard PVC flat submersible drop cable | M | 160
1.16 | Londex standard dual core cable (probe sensor) | M | 160
1.17 | Twin flat10mm cable with earth (Wiring connection) | M | 35
1.18 | Well probe sensor | No. | 1
1.19 | GS sunverter steel fabricates enclosure 1000x500x350mm | No. | 1
1.2 | Design as per radiations day angle, fabrication and installation of solar support structure for the specified solar panels. Rate to include for system testing. Use 75mmx 75mmx3mm SHS vertical support, 50mmx50mmx3mm struts and 50mmx50mmx2mm SHS purlins sections to hold panels tight into position. All joints braced. Height of the structure 4m above ground. The structure design must be preapproved before installation by the clients engineers | LS | 1
1.21 | Installation Sundries (cable ties, insulation tape, spacing tape, spicing joints etc) | Item | 1
1.22 | Solar security light (50W LED light, 120W Solar Module, 150Ah Sealed maintenance free battery, Dawn-to dusk controller, 6m high pole c/w battery box |  | 2
1.23 | Manual change over switch 100 Amp the Solar System with a 30KVA generator |  | 1
Sub Total
Element No.2 : Installation and Transportation
2.1 | Installation labour, testing and transportation to site | LS | 1
Sub Total
Total
B | Element No.2: Standard Water Kiosk with 5,000 Liters Ovehead Tank
Element 1: Excavation
1.1 | General excavation to remove top soil to an average depth of 250mm | m2 | 17
1.2 | Excavation for wall footing depth not exceeding 1200mm deep | m3 | 5.5
1.3 | Excavation for front area depth not exceeding 250mm | m3 | 4.5
1.4 | Cart away surplus excavated material & deposit at recommended area | m3 | 2.5
1.5 | 300mm thick approved hard-core, well compacted in layers not exceeding 150mm and blinded using 50mm murrum/quarry dust | m2 | 11
1.6 | Gauge 1000 polythene Damp proof on 50mm murrum blinding | m2 | 11
Sub Total
Element No.2: Masonry Work
2.1 | 200x225x450mm natural stone to walls to superstructures walling in 1:3 sand/cement mortar finished with steel finished on one side. Rate to included mild all reinforcement at every course | m2 | 16
2.2 | 200x225x450 natural stone to walls to Substructures walling in 1:3 sand/cement mortar. Rate to included mild all reinforcement at every course | m2 | 12
2.3 | 6" x 8" X 8" Concrete ventilation blocks | no. | 20
2.4 | 150mm wide DPM to walls | m | 9.5
Sub Total
Element No.3: Concrete Work
3.1 | Concrete grade 15/20 - 400 mm thick Plinth | m3 | 0.3
3.2 | Concrete grade 15/20 - 100mm thick slanting front area | m3 | 0.6
3.3 | Reinforced concrete grade 25/20 - 125mm thick floor slab | m3 | 0.8
3.4 | Reinforced concrete grade 25/20 - 150mm thick roof slab | m3 | 1
3.5 | Reinforced concrete grade 25/20 - 450 X 250mm footing | m3 | 1.1
3.6 | Concrete grade 15/20 - to soak pit cover 100mm THK | m3 | 0.75
3.7 | Concrete grade 15/20 - to catch pit base slab | m3 | 0.05
3.8 | Reinforced concrete grade 25/20 - 150mm thick roof slab | m3 | 1
3.9 | Reinforced concrete grade 25/20 - 300 X 150Thk ring beam | m3 | 0.5
3.1 | Reinforced concrete grade 25/20 - 250 X 250mm columns | m3 | 1
Sub Total
Element No. 4: Concrete Ancillaries
4.1 | Formwork
Provide cut and fix in position sawn timber formwork or equivalent.
4.11 | a) side of foundation footing 150mm wide | m | 20
4.12 | b) edges ground slab 125mm wide | m | 10
4.13 | c) Side of lintel 20mm deep | m | 2
4.14 | d) Edge of 400mm deep plinth | m | 4.5
4.15 | e) Edges of roof slab | m | 10
4.16 | f) Underneath roof slab, including propos | m2 | 6
4.17 | e) Edges of ring beam | m | 20
4.2 | Reinforcement
Steel reinforcement cut, bend & placed in position, unit price to include cutting, bending & placing in position with binding wire and concrete seats
4.21 | a) Mesh 142 mild steel reinforcement mesh (0.40kg/m2) in foundation wall | m2 | 7
4.22 | b) 10mm diameter high tensile steel (0.62kg/m2) in foundation wall | Kg | 45
4.23 | a) 8mm diameter mild steel (0.40kg/m) in foundation wall | Kg | 10
4.24 | b) 12mm diameter high tensile steel (0.89kg/m) in ring beam | Kg | 42.72
4.25 | c) 8mm diameter mild steel (0.40kg/m) in ring beam | Kg | 27.72
4.26 | d) 12mm diameter high tensile steel (0.89kg/m) in column footing | Kg | 24
4.27 | e) 12mm diameter high tensile steel (0.89kg/m) in columns | Kg | 49
4.28 | f) 8mm diameter mild steel (0.40kg/m) in columns | Kg | 21
4.29 | g) 10mm diameter high tensile steel (0.62kg/m2) in roof slab | Kg | 70
Sub Total
Element No.5: Roofing
5.1 | Steel work and G.I Sheets
5.1.1 | Provide steel structure mounted on top of the slab to cover the tank | LS | 1
5.1.2 | Roof cover in Gauge 30 CIS Nailed to 50 X 75mm purlins. | m2 | 15
5.2 | Timber Work
All structure truss members shall be in seasoned eucalyptus wood and painted two coats of anti termite solution and shall be tight fixed with top tie beam with 6mm diameter plain bar.
5.2.1 | a) 150 X 50mm wall plate | m | 5
5.2.1 | b) 50X 100mm timber to rafter | m | 25
5.2.3 | e) 50x50mm roof purlin | m | 20
5.2.4 | e) 250x15mm fascia board | m | 15
Sub Total
Element No.6: Fittings and Fixtures
6.1 | Doors
6.1.1 | 2000mm x1000mm steel door including locks and hinges to details | No | 1
6.2 | Windows
6.2.1 | 1000mm x1000mm steel swing window including locks and hinges to details. | No | 1
6.3 | Storage Shelves
6.3.1 | Provide and fix 3 rows from one piece of MDF (Medium Density Fibre) shelves 400mm wide and supported with 32mmx32mmx 5mm angle lines welded at an angle of 90º and spaced 800mm apart on the internal walls as shall be directed by supervising Engineer. The cost include MDT edge lining strip and boring of 3 holes for afixing the MDF board with 25mm long self tapping screw. | No | 1
Sub Total
Element No.7: Pipes and Fittings
All pipes and pipe fittings to be Galvanised Iron with Screw
7.1 | 1” G.I pipe class B | Pcs | 1
7.2 | 1” G.I Elbows | No. | 8
7.3 | 1” G.I sockets | No. | 8
7.4 | 1” dia. Gate Valve as Peglar | No. | 3
7.5 | 1" x¾” reducing bush | No. | 3
7.6 | 1” G.I tee | No. | 4
7.7 | 1” G.I union | No. | 4
7.8 | 1” G.I hexganol nipple | No. | 8
7.9 | 1" water meter | Pcs | 1
7.1 | 1' non return valve | Pcs | 1
7.11 | 2" G.I Pipe class B | Pcs | 4
7.12 | 2" back nut class B | Pcs | 4
7.13 | 2" long screw nipple | Pcs | 2
7.14 | 2" ball valve | Pcs | 1
7.15 | 2" G.I union class B | Pcs | 3
7.16 | 2" G.I elbow class B | Pcs | 8
7.17 | 2" G.I Socket | Pcs | 5
7.18 | 2'x1" reducing bush | Pcs | 1
7.19 | 2" Peggler gate valve | Pcs | 4
7.2 | Provide and install 5,000 Litres approved plastic tank on top of the kiosk roof complete with all fitting (its nipples, back nuts and float/ball valve) | No. | 1
Sub Total
8 | Element No.8: Finishes
8.1 | Pointing to all External wall surfaces with cement sand mortar 1:2 | m2 | 16
8.2 | Apply plastering to lintel surfaces | m2 | 0.4
8.3 | Apply plastering to all wall faces | m2 | 16
8.4 | Provide three coats of gloss paint to all plastered wall faces | m2 | 16
8.5 | Provide 3 coats of bituminous paint to all exposed concreted faces | m2 | 0.4
Sub Total
9 | Element No.9: Drainage and Tank Protection Shade
9.1 | Excavate for 400mm square X 900mm catch pit to detail | No. | 1
9.2 | 4" X 8 X 18" lining block to the site of the catch pit | m | 2.4
9.3 | 100mm thick mass concrete for catch pit base slab | m2 | 0.4
9.4 | Catch pit grating made from welded to form 25mm square mesh on 50mm steel frame | No. | 1
9.5 | Graded approved free draining hard-core/rubble stone filling the soak pit | m3 | 2
9.6 | 225mm Dia. Precast Concrete drainage pipes | m | 6
9.7 | Provide and install roof using Gauge 30 corrugated iron sheets and provide for its its supporting structure (Using HSS Tubes, welded appropriately to cover the tank on top of the water kiosk as shall be directed by Engineer on site. Bracing of the support structure to include strainers for preventing movement of tank. | LS | 1
Sub Total
Total for One(1) Kiosk
Total for Two (2) Kiosks
C | Cattle Trough (10.4M Long X1.4M Wide)
Element No.1: Earth Works
1.1 | Site cleaning up to 5cm of the top soil for the construction of construction of animal troughs | m2 | 37.12
1.2 | Foundation excavation for the animal troughs 30cm deep | m3 | 9.048
1.3 | Chart away surplus material more than 100m from the construction site or as directed by the Engineer . | m3 | 9.048
Sub Total
Element No.2: Masonry Works
2.1 | 20cm hard core used for the foundation base of the cattle trough.The unit price include supplying of basaltic stone material or equivalent with crushing, placing and compacing of the stone on the site. | m3 | 7.54
2.2 | Construction of 200mm thick masonry wall 400mm high in cement & sand mortar1:4 mix | m2 | 9.44
2.3 | Supply and construct inspection chamber/gate valve chamber with dimensions 1m long x 1m wide and 0.4 m height using block wall, with 60cm x60cm lockable, painted steel plate manhole cover for housing the control valves next to the animal trough. | No | 1
Sub Total
Element No.3: Concrete Works
3.1 | 15cm RCC concrete base slab reinforced with heavy gauge mesh wire and concrete mix ratio 1:2:4. Unit cost includes mixing, form work, placing, compacting and curing of RCC structure. | m3 | 4.524
Sub Total
Element No.4: Plastering
4.1 | Two coats of 20mm plastering to the internal and external part of the walls. The inner surface and floor of the trough should be mixed with water proof cement | m2 | 32.8
Sub Total
Element No.5: Plumbing and Piping Works
5.1 | Excavation
5.11 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 100 meters long | m3 | 18
5.2 | Pipe works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
5.2.1 | PN10 75mm HDPE pipes as per the specification above | LM | 550
5.3 | Pipe Fittings
Supply, deliver to site, joint and fix the following fittings
5.3.1 | 75mm HDPE Equal Tee PN 10 | Pcs | 4
5.3.2 | 75mmx75mm HDPE male adaptor | Pcs | 10
5.3.3 | 75mmx63mm HDPE male adaptor | Pcs | 2
5.3.4 | 75mm HDPE Equal Couplings | Pcs | 4
5.3.5 | 2" Peggler gate valve | Pcs | 4
5.3.6 | 2" G.I sockets | Pcs | 5
5.3.7 | 2" Hexaganol Nipple | Pcs | 6
5.3.8 | 2" G.I Elbow | Pcs | 6
5.3.9 | 2" G.I Union | Pcs | 6
5.3.10 | 3"x2" reducing bush | Pcs | 6
5.3.11 | 3: G.I sockets | Pcs | 4
5.3.12 | 2" G.I Pipe class B (6m long) | Pcs | 2
5.3.13 | PTFE tapes (Packet of 10) | Packet | 4
5.3.14 | Supply all materials, and construct standard masonry lockable valve chamber of 1000mm wide x1000mm long x 1000mm deep | No | 3
Sub Total
Total
Total for 2 Cattle Troughs
D | Repair of 3 Existing Cattle Troughs
Element No.1: Hacking
1.1 | Hack the existing plastering and dispose off the materials | Units | 3
Element No.2: Plastering
2.1 | Apply 20mm thick plastering to the internal and external part of the walls. The internal and external surface and floor of the trough should be mixed with water proof cement | m2 | 36.64
Sub Total
Total for 3 Cattle Trough Repiar
| SUMMARY |  |  |  | AMOUNT
A | BOREHOLE SOLARIZATION & EQUIPING
B | WATER KIOSK CONSTRUCTION
C | CONSTRUCTION OF CATTLE TROUGHS
D | REPAIR OF CATTLE TROUGHS
GRAND TOTAL

## Chachabole
BOQ No:16
Project : | BORESHA
County | Mandera
Sub County | Mandera South
Location | Chachabole
Description | Borehole Solarization, Construction of Pump/Generator House and Repair of 1No. Animal Trough
Item No | Item Description | Unit | Qty | Rate | Amount
A | Borehole Solarization (Yield 8 m3/hr, Motor Size 7.5 Kw)
Element No.1: Supply and deliver to site, install, commission and test the following for pumping 8m3/hr with 7.5 Kw Motor size
1.1 | Dayliff SV3 7.5KW 3PH Sunverter | Set | 1
1.2 | Monocrystalline photo voltaic solar modules 665W, 24Vdc | No. | 17
1.3 | Dayliff 4ST 1000 DC/40A PV Disconnect Switch | No. | 1
1.4 | Earth rod complete with clamp | No. | 1
1.5 | Lightning Arrestor | No. | 1
1.6 | Copper Earth Cable 6mm2 | M | 25
1.7 | 6mm2 4 core underground cable (armoured) | M | 28
1.8 | 1.5mm2- 2 core undergroudn armoured cable(elecrode sensor) | M | 28
1.9 | Twin flat10mm cable with earth (Wiring connection) | M | 35
1.1 | GS sunverter steel fabricates enclosure 1000x500x350mm | No. | 1
1.11 | Design as per radiations day angle, fabrication and installation of solar support structure for the specified solar panels. Rate to include for system testing. Use 75mmx 75mmx3mm SHS vertical support, 50mmx50mmx3mm struts and 50mmx50mmx2mm SHS purlins sections to hold panels tight into position. All joints braced. Height of the structure 4m above ground. The structure design must be preapproved before installation by the clients engineers | LS | 1
1.12 | Installation Sundries (cable ties, insulation tape, spacing tape, spicing joints etc) | Item | 1
1.13 | Solar security light (50W LED light, 120W Solar Module, 150Ah Sealed maintenance free battery, Dawn-to dusk controller, 6m high pole c/w battery box |  | 2
1.14 | Manual change over switch 100 Amp the Solar System with a 30KVA generator |  | 1
Sub Total
Element No.2 : Installation and Transportation
2.1 | Installation labour, testing and transportation to site | LS | 1
Sub Total
Total
B | Pump House/ Generator House (4150mmx4000mm)
Element No.1:Site clearance:
1.1 | Clear the site from the debris and commence site establishment | 1 | 25
Sub Total
Element No.2: Excavation and Backfilling
2.1 | Excavation of substructure foundation (0.6mx0.5mx16m) the excavation of pipe trenches | m3 | 2.28
2.2 | Supply and backfill with150mm approved hardcore and rashed Stone, supply and fill (imported or Excavated selected material over the ground floor compact AS PER Specification | m3 | 2.4
2.3 | Supply and fill 100mm thick approved murram over the selected material, level with hammer | m3 | 1.6
Sub Total
Element No.3: Masonry Work
3.1 | Substructure Walling
3.1.1 | Construct 3 courses of 225mmX225mm natural cut stone foundation wall bedded in cement sand mortar 1:3. Rate to include reinforcement with hoop iron at every 2 courses and at the last course to hold the 100mmx 50mm wall plate | M2 | 7.2
3.2 | Superstructure Walling - Masonry
3.2.1 | Construct 5 courses of 150mmX225mm well dressed natural cut stone superstructural wall bedded in cement sand mortar 1:3 with one side left for plastering. Rate to include reinforcement with hoop iron at every 2 courses | m2 | 16.8
3.2.2 | 150mm wide DPM to walls | m | 16
3.3 | Superstructure Walling - Timber Work
All structure members shall be in seasoned cypress wood and painted two coats of anti termite solution
3.3.1 | 100mm X 50mm bottom wall plate | m | 16
3.3.2 | 100mm X 50mm top wall plate | m | 16
3.3.3 | 100mm X 50mm studs (vertical height -2400mm from the bottom wall plate) | m | 38.4
3.3.4 | 100mm X 50mm girts | m | 32
3.3.5 | Heavy gauge mesh wire | Pcs | 14
Sub Total
Element No.4: Concrete Works
4,1 | 100mm thick concrete class 25 (1:2:4) for blinding the 600mm wide foundation wall footing | m3 | 0.456
4.2 | 150mm concrete class 25 (1:2:4) in floor slab | m3 | 2.4
4.3 | 75mm Concrete Grade 15 (1:3:6) fort disabled person access ramp, sloping at 1:7 | m3 | 0.252
4.4 | Construct a concrete plinth1.2m wideX2m longX0.5m thick with concrete class 25(1:2:4) with double strand10mm reinforcement bars. | m3 | 1.5
Sub Total
Element No. 5: Concrete Ancillaries
5.1 | Formwork
Provide cut and fix in position sawn timber formwork or equivalent.
5.1.1 | b) Edges of floor slab with 50mm x150mm | m2 | 16
5.1.2 | e) Tree props to support the 50mm x 150mm timbers of the flooor slab | Poles | 5
5.2 | Reinforcement
Steel reinforcement cut, bend & placed in position, unit price to include cutting, bending & placing in position with binding wire and concrete seats
5.2.1 | d) 10mm diameter high tensile steel (0.617kg/m) in channel base and both wallings spaced @200mm C/C | Kgs | 145
Sub Total
Element No.6: Roofing
6.1 | Currugated Sheets
6.1 | Corrugated sheets and BP760 Boxed profiled sheets (3000mm long X762mm wide) Nailed to 50 X50 mm purlins. | Pcs | 16
6.2 | Timber Work
All structure truss members shall be in seasoned cypress wood and painted two coats of anti termite solution and shall be tight fixed with top tie beam with 6mm diameter plain bar.
6.2.1 | 100mmX50mm timber to rafter and tie beam | LM | 30
6.2.2 | 50mmX50mm timber to fasten the truss members | LM | 6.8
6.3.3 | 100 X 50mm vertical member (King Post) | LM | 6
6.3.4 | 50mmX50mm roof purlins | LM | 36
6.3.5 | 200mmx 25mm prepainted Fascia Board | LM | 16
6.3.6 | 50mmX50mm Ceiling buttens | LM | 77.4
6.3.7 | Supply and fix 4mm laminated ceiling board in rooms with appropriate ceils nails | M2 | 16
Sub Total
Element No.7: Finishing Works
7.1 | Apply 20mm thick plaster to internal surfaces with cement & sand mortar 1:2 | M2 | 15.36
7.2 | Apply 20mm thick plaster to external surfaces as skirting with cement & sand mortar 1:2 | M2 | 6.4
7.3 | Apply 2 coats of first grade superfast emulsion paint (Dura Coat) to the pump house internal surfaces | m2 | 15.36
7.4 | Apply 2coats of first grade plastic emulsion paint on the ceiling surface. | m2 | 16
7.5 | Apply 3 coats of supergloss paint (Dura Coat) external keyed block wall grooves. | m2 | 17.4
Sub Total
Element N.8: Fixture and Fittings
8.1 | Door
8.1.1 | Fabricate 2000mmx2100mm double door made of 16 gauge steel plate welded to the frame, 38x38x3mm thick steel angles for door main frame, 25mmx25mm x 2mm RHS welded to steel plate. Make provisionof 100mm wall passes for anchoring the door frame on the wall | PCS | 1
Sub Total
Element No.9: Electrical Installations
9.1 | Carry out elctrical installation using white rectangular electrical conduits and 2.5mm single cable including double electrical (2pcs) sockets, 1 double gang switch (1pcs) as well flouresent holder and bulb (2 set) | Lumpsum | 1
Sub Total
Total
C | Repair of 1No. Animal Trough Repair
Element No. 1: Hacking and Plastering
1.1 | Allow for hacking all internal and external plaster | SM | 53
1.2 | Inject cement mortar to all hacked deep cracks and fix with chicken wire and plaster (1:3) | SM | 53
1.3 | 20mm thick plaster, cement and sand mortar (1:3) to floor with water proof cement steel trowelled to smooth finish. | SM | 30
1.4 | 20mm thick plaster, cement and sand mortar (1:3) to internal side of walls with water proof steel trowelled to smooth finish. | SM | 12
1.5 | 20mm thick plaster, cement and sand mortar (1:3) to external side of walls | SM | 11
1.6 | Hack and provide 100mm thick C20 mass Concrete benching laid to appropriate fall on all directions at animal stepping platform. | SM | 2
1.7 | Sub Total
Element 2: Plumbing and Pipeworks
Elment No. 1 : Excavation
1.1 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 200 meters long | m3 | 36
Sub Total
Element No. 2 : Pipe Works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
2.1 | 75mm HDPE pipe 10 bars with to channell water from the Masonry tank to the troughs | LM | 200
Sub Total
ElementNo. 3 : Pipe Fittings
2.1 | 75mm HDPE Equal Couplings | Pcs | 4
2.2 | Supply and install 75mm HDPE male adpaters | Pcs | 8
2.3 | Supply and install 75mm HDPE Tee | Pcs | 4
2,4 | Supply and install 75mmx 63mm reducing adaptor | Pcs | 4
2.5 | Supply, install and test 2'' GI pegler (England) Gater Valves and 2'' float valves | No. | 3
Sub Total
Total
| SUMMARY |  |  |  | AMOUNT
A | BOREHOLE SOLAIZATION |  |  |  | 0
B | PUMP/GENERATOR HOUSE |  |  |  | 0
C | REPAIR OF ANIMAL TROUGH |  |  |  | 0
| GRAND TOTAL |  |  |  | 0

## Qalanqalesa
BOQ No:17
Project : | BORESHA
County | Mandera
Sub County | Mandera South
Location | Qalanqalesa
Description | Borehole Solarization and Installaton of Perimeter Fence tor Servicing
Item No | Item Description | Unit | Qty | Rate | Amount
Element No.1: Supply and deliver to site, install, commission and test the following for pumping 8m3/hr with 7.5 Kw Motor size
1.1 | Dayliff SV3 7.5KW 3PH Sunverter | Set | 1
1.2 | Monocrystalline photo voltaic solar modules 665W, 24Vdc | No. | 17
1.3 | Dayliff 4ST 1000 DC/40A PV Disconnect Switch | No. | 1
1.4 | Earth rod complete with clamp | No. | 1
1.5 | Lightning Arrestor | No. | 1
1.6 | Copper Earth Cable 6mm2 | M | 25
1.7 | 6mm2 4 core underground cable (armoured) | M | 28
1.8 | 1.5mm2- 2 core undergroudn armoured cable(elecrode sensor) | M | 28
1.9 | Twin flat10mm cable with earth (Wiring connection) | M | 35
1.1 | GS sunverter steel fabricates enclosure 1000x500x350mm | No. | 1
1.11 | Design as per radiations day angle, fabrication and installation of solar support structure for the specified solar panels. Rate to include for system testing. Use 75mmx 75mmx3mm SHS vertical support, 50mmx50mmx3mm struts and 50mmx50mmx2mm SHS purlins sections to hold panels tight into position. All joints braced. Height of the structure 4m above ground. The structure design must be preapproved before installation by the clients engineers | LS | 1
1.12 | Installation Sundries (cable ties, insulation tape, spacing tape, spicing joints etc) | Item | 1
1.13 | Solar security light (50W LED light, 120W Solar Module, 150Ah Sealed maintenance free battery, Dawn-to dusk controller, 6m high pole c/w battery box |  | 2
1.14 | Manual change over switch 100 Amp the Solar System with a 30KVA generator |  | 1
Sub Total
Element No.2 : Installation and Transportation
2.1 | Installation labour, testing and transportation to site | LS | 1
Sub Total
Total
B | Perimeter Fencing 30mx30m
Element No.1: Supply of Concrete Poles & Other Material Inputs
1.1 | Supply transport to site and install 100mm x100mm thick concrete poles,3000mm long with 500mm cranked length and 6 provisional holes to accomodate straining/barbed wire spaced @ 2500mmc/c. Rate to include for excavation of pole pits and firming with concrete at the poles base. | Pcs | 50
1.2 | Ditto but 100mmx100mm and 2000mm long precast concrete strut posts of grade C-20 placed at corners and after every 15m spacing. Rate to include for excavation of pole pits and firming with concrete at the poles base. | No. | 16
1.3 | Provide materials, fabricate and install purpose made steel grilled double leaf security gate overall size 4000x2000mm high in two equal opening leaves each size 2000x2000mm high with external frame of 50x50x3mm SHS. Vertical bracing of 50x50x3mm spaced @400mm c/c, horizontal frame of 40x40x3mm spaced @ 300mm c/c all fixed to external frame by wielding including all hinged supported by RC columns complete with locking devices all painted with two coats of approved primer and finished with final coat first grade gloss paint. | Pcs | 1
1.3 | G12.5 chainlink 2m high | SM | 240
1.4 | Barbed wire 16g, 25kg -6 strand | LM | 720
Sub Total
Element No.2: Mass concrete class C20/25 in:
2.1 | To concrete poles | CM | 0.918
2.2 | 300mmx300mm Gate columns | CM | 0.5
2.3 | 150mm wide x 150mm deep Concrete pitching to chainlink base ratio 1:3:6 | CM | 2.7
Sub Total
Element No.3: Conceter Ancillary
3.1 | Formwork to;
3.1.1 | Column edges over 150mm but not exceeding 300 mm girth | SM | 21.12
3.2 | Reinforcment Bars
3.2.1 | Provide, cut and place 10mm square twisted steel rebars in gate columns and 600mmx600mm footing | Kg | 20
3.2.2 | 8mm twisted steel rebars as stirrups in column @150mm | Kg | 14
Sub Total
Elememnt No.4: Finishes
4.1 | 20mm thick plastering with cement: sand (1:4) screed to surfaces with 12mm thick lime steel trowelled smooth finish on columns | SM | 21.12
4.2 | Gloss painting to columns- code provided by Engineer | SM | 6
Sub Total
Total
| SUMMARY |  |  |  | AMOUNT
A | BOREHOLE SOLARIZATION |  |  |  | 0
B | PERIMETER FENCING |  |  |  | 0
| GRAND TOTAL |  |  |  | 0

## Harsanga
BOQ No:18
Project : | BORESHA
County | Mandera
Sub County | Mandera South
Location | Harsanga
Description | Cattle Trough Construction and 1No. Mansonry Tank Repair
Item No | Item Description | Unit | Qty | Rate | Amount
A | Cattle Trough (10.4M Long X1.4M Wide)
Element No.1: Earth Works
1.1 | Site cleaning up to 5cm of the top soil for the construction of construction of animal troughs | m2 | 37.12
1.2 | Foundation excavation for the animal troughs 30cm deep | m3 | 9.048
1.3 | Chart away surplus material more than 100m from the construction site or as directed by the Engineer . | m3 | 9.048
Sub Total
Element No.2: Masonry Works
2.1 | 20cm hard core used for the foundation base of the cattle trough.The unit price include supplying of basaltic stone material or equivalent with crushing, placing and compacing of the stone on the site. | m3 | 7.54
2.2 | Construction of 200mm thick masonry wall 400mm high in cement & sand mortar1:4 mix | m2 | 9.44
2.3 | Supply and construct inspection chamber/gate valve chamber with dimensions 1m long x 1m wide and 0.4 m height using block wall, with 60cm x60cm lockable, painted steel plate manhole cover for housing the control valves next to the animal trough. | No | 1
Sub Total
Element No.3: Concrete Works
3.1 | 15cm RCC concrete base slab reinforced with heavy gauge mesh wire and concrete mix ratio 1:2:4. Unit cost includes mixing, form work, placing, compacting and curing of RCC structure. | m3 | 4.524
Sub Total
Element No.4: Plastering
4.1 | Two coats of 20mm plastering to the internal and external part of the walls. The inner surface and floor of the trough should be mixed with water proof cement | m2 | 32.8
Sub Total
Element No.5: Plumbing and Piping Works
5.1 | Excavation
5.11 | Excavation of pipe trench 300mm wide x600mm deep in soft soil and backfill for a pipeline trench 100 meters long | m3 | 18
5.2 | Pipe works
Supply, deliver to site, joint and lay the following PN10 HDPE pipes. Jointing by butt fusion on HDPE pipes to attain parent material strength at the joints. All fittings should be removable for ease of replacement or servicing. Tee-off points with gate valves should be supplied as per pipeline.
5.2.1 | PN10 75mm HDPE pipes as per the specification above | LM | 550
5.3 | Pipe Fittings
Supply, deliver to site, joint and fix the following fittings
5.3.1 | 75mm HDPE Equal Tee PN 10 | Pcs | 4
5.3.2 | 75mmx75mm HDPE male adaptor | Pcs | 10
5.3.3 | 75mmx63mm HDPE male adaptor | Pcs | 2
5.3.4 | 75mm HDPE Equal Couplings | Pcs | 4
5.3.5 | 2" Peggler gate valve | Pcs | 4
5.3.6 | 2" G.I sockets | Pcs | 5
5.3.7 | 2" Hexaganol Nipple | Pcs | 6
5.3.8 | 2" G.I Elbow | Pcs | 6
5.3.9 | 2" G.I Union | Pcs | 6
5.3.10 | 3"x2" reducing bush | Pcs | 6
5.3.11 | 3: G.I sockets | Pcs | 4
5.3.12 | 2" G.I Pipe class B (6m long) | Pcs | 2
5.3.13 | PTFE tapes (Packet of 10) | Packet | 4
5.3.14 | Supply all materials, and construct standard masonry lockable valve chamber of 1000mm wide x1000mm long x 1000mm deep | No | 3
Sub Total
Total
B | Bill No. 2: Repair of 1No 50M3 Masonry Tank
Element No. 1: Hacking and Lining
1.1 | Hack and demolish existing wall finishes on internal,external walls and floor surfaces including deep cracks and cart away debris. | SM | 102
1.2 | Inject cement mortar to all hacked surfaces and fix with chicken wire appropriate re-bars staples and mortar (1:3) | SM | 55
Sub Total
Element No. 2: Plastering & Finishing
2.1 | 20mm thick plaster mixed with Sika or equivalent water proofing admixture to walls and concrete surfaces internally and externally. | SM | 102
2.2 | 25mm thick plaster screed to base slab and roof slab with waterproof cement | SM | 34
2.3 | Prepare and apply three coats gloss paint to all plastered external wall surfaces | SM | 64
Sub Total
Element No. 3: Pipework and Plumbing Fixtures
3.1 | Provide 75mm GI inlet pipe class "B" with and including joining fittings to tank and fix as described | LM | 8
3.2 | Provide 50mm GI outlet pipes class "B" with and including joining fittings to tank and fix as described | LM | 8
3.3 | Construct 1200mm x 1200mm x 900mm valve chambers with lockable steel cover at inlet and outlet complete with control valves and adjoining fittings | No. | 2
3.4 | Provide and fix tank breather pipes with (600mm long 2" GI pipes, 2 pcs Elbows) with wall passess. | No. | 2
Sub Total
Total
| SUMMARY |  |  |  | AMOUNT
A | CATTLE TROUGH CONSTRUCTION
B | MASONRY TANK REPAIR
GRAND TOTAL